## AMO
| TV-F1-2023 |  |  |  |  | Ameren MO Transmission Lines - 2023
| Please date any notes added |  |  |  |  | Scheduled Work Listed By Miles Unless Otherwise Noted
[7 empty] | Aerial Side Trim Maintenance |  |  |  | Aerial Herbicide Maintenance |  |  |  | Ground Herbicide (L,H,B) Maintenance |  |  |  | Mowing Maintenance |  |  |  | Tree Trimming Maintenance |  |  |  | Tree Trimming Hotspot
Circuit Miles | Alpha Code | Line # | Line Name | ROW Name | Volt | VM Supv | 1st Q | 2nd Q | 3rd Q | 4th Q | 1st Q | 2nd Q | 3rd Q | 4th Q | 1st Q | 2nd Q | 3rd Q | 4th Q | 1st Q | 2nd Q | 3rd Q | 4th Q | 1st Q | 2nd Q | 3rd Q | 4th Q | 1st Q | 2nd Q | 3rd Q | 4th Q
1.34 | AU |  | Adair-Appanoose-2 |  | 161 | RB | [9 empty] | 1 | [12 empty] | 0
25 | FD |  | Apache Flats-Mariosa Delta |  | 161 | SG | [21 empty] | 2
14.9 | DN |  | Apache Flats-Sub Tap-1 (Barnett-California - 1 to Apache Flats) |  | 161 | SG | [21 empty] | 1
0.42 | DK |  | Ashley-Sub Tap - 2 (Cahokia-Venice-2 to Ashley) |  | 138 | TS | [21 empty] | 0 | 0 | 1
12.29 | AC |  | Atchinson-Outlaw |  | 345 | RB
0.73 | EH |  | Baumgartner Sub Tap (Meramec-Watson - 2 to Baumgartner) |  | 138 | TS | [22 empty] | 1
43.24 | WA |  | Belleau-Montgomery-6 |  | 345 | SG | [20 empty] | 1 |  | 2 | 4
55.2 | FF |  | Belleau-Pike-1 |  | 161 | RB | 0 |  | 54 | [9 empty] | 0 | [7 empty] | 2 | 5
11.18 | EO |  | Big River-Rockwood |  | 138 | TS |  | 0 | 11 | [7 empty] | 11 | [10 empty] | 0 | 0 | 1
13.5 | DS |  | Big River-Tyson 3 & 4 |  | 138 | TS | [20 empty] | 1 | 2
1.09 | EU |  | Blanchette-Sub Tap |  | 138 | TS | [21 empty] | 0 | 0 | 1
44.2 | BF |  | Bland-Franks-3 |  | 345 | SG | [20 empty] | 10
28.7 | QQ |  | Buck Knob-Rivermines-2 |  | 138 | RT | [22 empty] | 6 | 2
9 | O |  | Cahokia-Central 1 & 2 |  | 138 | TS | [20 empty] | 0 |  |  | 1
0.48 | AD |  | Cahokia-Meramec |  | 138 | TS
2.47 | CL |  | Cahokia-Popplar-5 |  | 138 | TS | [20 empty] | 1
31.6 | CD |  | Callaway-Bland-1 (Paralleled Circuits) |  | 345 | SG | [22 empty] | 1 | 5
16.6 | FH |  | Callaway-Loose Creek |  | 345 | SG | [9 empty] | 16 | [11 empty] | 1 | 1
1 | CO |  | Calumet-Sub Tap 3 & 4 (Pike-Dundee 3 & 4 to Calumet) |  | 161 | RB
3.23 | DO |  | Camden-Sub Tap - 2 (Camdenton - 2 - Lakeview to Camden) |  | 161 | SG | [20 empty] | 1 | 1
2.8 | Q |  | Campbell-Euclid - 4 (Partially Paralleled Circuits) |  | 138 | TS | [23 empty] | 2
3.2 | BX |  | Campbell-Maline-1 & 2 |  | 138 | TS | [20 empty] | 1 |  | 0 | 1
1.6 | BZ |  | Campbell-Sub Tap-4 (Cahokia-Roxford - 4 to Campbell) |  | 345 | TS
6.36 | UU |  | Cape-Joppa-1 - (MO side) |  | 161 | RT | [23 empty] | 2
6.1 | CS |  | Cape-Kelso - 2 East Line |  | 161 | RT | [21 empty] | 1
7.1 | CW |  | Cape-Kelso -3 (West line) |  | 161 | RT | [21 empty] | 1
4.5 | AF |  | Cape-Viaduct Tap |  | 138 | RT
19.2 | DL |  | Cape-Wedekind-2 |  | 161 | RT | [21 empty] | 2 |  | 1
8.5 | BP |  | Carbide-Sub Tap - 2 (Palmyra-Viele-2) |  | 161 | RB | [22 empty] | 0 | 1
5.9 | AJ |  | Central-Watson-1 |  | 138 | TS | [21 empty] | 1 | 1
24.1 | DT |  | Clark-Cominco-2 |  | 161 | RT | [12 empty] | 4 | [9 empty] | 8 | 3
95.4 | AE |  | Clark-Osage-2 |  | 138 | RT | [20 empty] | 4 |  | 10 | 8
17.7 | PP |  | Clark-Pea Ridge 3 & 4 |  | 138 | RT | [15 empty] | 6 |  |  |  |  | 1
27.8 | EB |  | Clark-Pilot Knob-1 |  | 161 | RT | [15 empty] | 16 | [6 empty] | 3
46 | E |  | Conway-Tyson 3 & 4 |  | 138 | TS | [20 empty] | 1 |  | 1 | 1
2.74 | CH |  | Dillon-Alfermann | ITC | 138 | RT
3.5 | D |  | Dorsette-Sub Tap 4 |  | 138 | TS | [21 empty] | 0 | 1 | 1
2 | AG |  | Dorsette-Sub Tap 8 |  | 138 | TS | [20 empty] | 1 | 0 | 0 | 1
2.2 | ET |  | Dupo Ferry-Selma |  | 138 | RT | [22 empty] | 1
13.5 | DU |  | Fletcher-Cominco - 1 |  | 161 | RT | [12 empty] | 11 | [9 empty] | 8
30.5 | EA |  | Fletcher-Pilot Knob - 2 |  | 161 | RT | [22 empty] | 6 | 4
9.4 | DZ |  | Fletcher-Sweetwater - 3 |  | 161 | RT
0.9 | AH |  | Ft. Zumwalt-Sub Tap |  | 138 | TS | [20 empty] | 1 |  |  | 1
56.6 | AI |  | Gasco-Osage-2 |  | 138 | SG | [22 empty] | 3
12.13 | CG |  | General Motors-Sub Tap |  | 161 | SG | [22 empty] | 2 | 1
6.1 | R |  | Gray Summit-Franklin 1 & 2 |  | 138 | RT
21.84 | EF |  | Gray Summit-Rockwood 3 & 4 |  | 138 | TS | [21 empty] | 1 |  | 1
14.2 | CP |  | Guthrie-Moreau-1 |  | 161 | SG | [20 empty] | 1 | 4 |  | 1
30.7 | CC |  | Guthrie-Overton-3 |  | 161 | SG | [21 empty] | 2 | 2 | 1
1.7 | DJ |  | Hall Street-Ashley 1 |  | 138 | TS | [23 empty] | 1
8.28 | FA | 4549 | Herlman-Maywood(Missouri) | ITC | 345 | RB | [9 empty] | 0 |  |  | 8 | [7 empty] | 1
1 | FE |  | Hughes-High Prairie Wind |  | 345 | RB | [22 empty] | 1 | 1
5.2 | BL |  | Hunter-Sub Tap 1 & 2 (Page-Mason 1 & 2 to Hunter) |  | 138 | TS | [20 empty] | 1 | 1 |  | 1
18.86 | HA |  | Joachim-St. Francis 1&2 |  | 138 | RT | [23 empty] | 7
5.14 | ES |  | Joppa-Kelso (MO side) |  | 345 | RT | [15 empty] | 4 |  |  |  |  | 1
17.7 | EX |  | Kelso-Lutesville-1 |  | 345 | RT | [20 empty] | 1 | 13 | 4
19.1 | CT |  | Kelso-Miner-2 |  | 161 | RT | [20 empty] | 0 | 2 |  | 4
29.41 | CX |  | Kelso-Stoddard-3 |  | 161 | RT | [23 empty] | 4
40.2 | BE |  | Labadie-Bland-3 |  | 345 | RT | [20 empty] | 2
6 | AP |  | Labadie-Gray Summit-3 |  | 138 | TS
50 | AS |  | Labadie-Montgomery-4 |  | 345 | RT | [20 empty] | 6 | 2 | 1
60 | AV |  | Labadie-Tyson 1 & 2 |  | 345 | TS | [20 empty] | 1 |  | 2 | 2
0.25 | DP |  | Lathrop-Sub Tap (NW Electric Co-op to Lathrop) |  | 161 | RB
5 | J |  | Lemay-Sub Tap 1 & 2 (Cahokia-Meramec 1 & 2 to Lemay) |  | 138 | TS | [20 empty] | 1 |  |  | 1
37.29 | FI |  | Loose Creek-Franks-2 |  | 345 | SG | [9 empty] | 37 | [11 empty] | 1 | 1
12 | FM |  | Loose Creek-Mariosa Delta |  | 345 | SG | [9 empty] | 12 | [12 empty] | 1
13 | AK |  | Lutesville-Heritage |  | 345 | RT | [14 empty] | 13 | [8 empty] | 4
63 | AQ |  | Lutesville-St. Francois-1 |  | 345 | RT | [20 empty] | 4 |  |  | 10
9.6 | DD |  | Marion Tap-2 (Pike-Palymyra - 2 to Marion Sub) |  | 161 | RB | [21 empty] | 0
8.3 | BV |  | Marshall-Lakeshire-4 |  | 138 | TS | [20 empty] | 1 | 0 | 2
8.2 | ED |  | Marshall-Sub Tap-1 (Central-Watson - 1 to Marshall) |  | 138 | TS | [20 empty] | 1 |  | 2
14.6 | AW |  | Marshall-Tyson 1 & 2 |  | 138 | TS | [22 empty] | 1
11.16 | DH |  | Mason-Carrollton-8 |  | 138 | TS | [20 empty] | 1 | 0 |  | 1
26.3 | LL |  | Mason-Gray Summit 1 & 2 |  | 138 | TS | [20 empty] | 1 | 0
50 | AR |  | Mason-Labadie 3 & 4 |  | 345 | TS | [20 empty] | 1 | 1 | 4 | 1
11.17 | ER |  | Mason-McClay -9 |  | 138 | TS | [21 empty] | 1 |  | 1
47 | C |  | Mason-Meramec 1 & 2 |  | 138 | TS | [20 empty] | 1 |  | 2 | 3
26.9 | BQ |  | Mason-Sioux-7 |  | 345 | TS | [20 empty] | 1 |  |  | 1
3 | DQ |  | Maurer Lake Sub Supply (MO City-Carrollton to M. Lake) |  | 161 | RB
121.75 | I |  | Maywood-Hills |  | 345 | RB | [12 empty] | 0 | [7 empty] | 2 |  |  | 2
65.22 | FB |  | Maywood-Zachary | ITC | 345 | RB | [9 empty] | 65 | [12 empty] | 0
5.3 | DC |  | McClay-Sub Tap 1 & 3 (Huster-Belleau 1 & 3 to McClay) |  | 138 | TS | [21 empty] | 1 | 1
4.69 | F |  | Meramec-Baumgartner - 1 |  | 138 | TS | [20 empty] | 1 | 0 |  | 1
16.27 | H |  | Meramec-Joachim 1 & 2 |  | 138 | TS | [20 empty] | 3 |  | 1 | 1
13.9 | G |  | Meramec-Watson - 2 |  | 138 | TS | [20 empty] | 1 | 4 | 5 | 1
18.6 | CR |  | Miller-Zion-1 |  | 138 | SG | [20 empty] | 1 | 1 | 1 | 1
10 | CV |  | Miner-Charleston-1 |  | 161 | RT
10 | CU |  | Miner-Sikeston-1 |  | 161 | RT
1.41 | AL |  | Mississippi-Sub Tap-1 & 2 MO |  | 138 | TS | [23 empty] | 1
46.44 | CB |  | Montgomery-Callaway 7 & 8 |  | 345 | SG | [20 empty] | 2 | 0 |  | 5
38 | AT |  | Montgomery-Guthrie-3 |  | 161 | SG | [20 empty] | 1 |  | 2 | 1
64.7 | II |  | Montgomery-Maywood |  | 345 | SG | [20 empty] | 4 |  |  | 2
64 | ZZ |  | Montgomery-Overton-5 |  | 345 | SG | [20 empty] | 4 | 0 | 1 | 3
5 | EL |  | Moreau-Mariosa Delta |  | 161 | SG | [21 empty] | 1 |  | 1
1 | CF |  | O'Fallon Sub Tap 1 & 3 (Huster-Belleau 1 & 3 to O'Fallon) |  | 138 | TS
52.26 | VV |  | Osage-Overton |  | 138 | SG |  |  | 5 | [17 empty] | 1 |  | 5 | 1
35.9 | BS |  | Overton-Moberly-1 |  | 161 | RB |  |  | 40 | [9 empty] | 0 | 30 | 10 | [5 empty] | 1
10.1 | BT |  | Overton-Sedalia-1 |  | 161 | SG | [21 empty] | 1 | 1 | 1
2.5 | P |  | Page-Euclid-1 (Paralleled Circuits) |  | 138 | TS | [23 empty] | 1
19.6 | A |  | Page-Mason 1 & 2 |  | 138 | TS | [20 empty] | 1 |  | 2 | 1
21.6 | U |  | Page-Sioux-4 |  | 138 | TS | [20 empty] | 3 | 1 | 2 | 2
11.6 | B |  | Page-Warson 5 & 6 |  | 138 | TS | [21 empty] | 1 | 4 | 2
2.5 | BM |  | Palmyra Sub Supply - 1 (Montgomery Sub T-1 to Palmyra) |  | 345 | RB
6.2 | BN |  | Palmyra-North Marblehead-1 |  | 161 | RB | 0 | 6 | [11 empty] | 4 | [6 empty] | 1
70 | BH |  | Palmyra-Viele-2 |  | 161 | RB | [13 empty] | 0 | [8 empty] | 0 | 2
16.4 | CN |  | Pike-Dundee 3 & 4 |  | 161 | RB | [12 empty] | 0 | [7 empty] | 0 |  | 1 | 1
40 | GG |  | Pike-Palmyra-2 |  | 161 | RB | 0 | 39 | 1 | [10 empty] | 0 | [7 empty] | 2 | 1
72.89 | CI |  | Rivermines-Alfermann | ITC | 138 | RT
71 | TT |  | Rivermines-Cape-1 |  | 138 | RT | [10 empty] | 71 | [9 empty] | 1 | 3 |  | 7
24.9 | NN |  | Rivermines-Clark-2 |  | 138 | RT | [10 empty] | 25 | [9 empty] | 1 | 6
29.8 | SS |  | Rivermines-Taum Sauk 1 & 2 |  | 138 | RT | [10 empty] | 30 | [10 empty] | 1
1.7 | EK |  | Rush Island-Holcim-1 (Distribution) |  | 345 | RT | [20 empty] | 0 | 1
17 | BO |  | Rush Island-St. Francois-1 |  | 345 | RT | [20 empty] | 1
66.2 | BI |  | Rush Island-Tyson 1 & 2 |  | 345 | TS | [21 empty] | 3 | 2 | 2
11.9 | JJ |  | Salisbury-Moberly - 10 |  | 161 | RB | [21 empty] | 4
23.34 | W |  | Sioux-Belleau-6 |  | 345 | TS | [20 empty] | 1 |  |  | 2
32 | AB |  | Sioux-Maline 3 & 4 |  | 138 | TS | [20 empty] | 1 |  | 1 | 2
4.82 | AO |  | Sioux-Meppen MO |  | 138 | TS | [22 empty] | 1
28.6 | AA |  | Sioux-Roxford 5 MO |  | 345 | TS | [20 empty] | 1 |  |  | 1
24.46 | EP |  | St. Francois-New Bourbon |  | 138 | RT | [20 empty] | 3
10 | BC |  | St. Francois-Rivermines 1 |  | 138 | RT | [20 empty] | 8 | 2
10 | BC |  | St. Francois-Rivermines 2 |  | 138 | RT | [21 empty] | 2
10 | BC |  | St. Francois-Rivermines 3 |  | 138 | RT | [21 empty] | 1
1.04 | BD |  | St. Francois-Sub Tap-2 |  | 138 | RT | [21 empty] | 1
12.4 | CZ |  | Stoddard-Berntie - 1 (Includes Stoddard to Richland) |  | 161 | RT | [23 empty] | 6
6.25 | CQ |  | Tegeler-Explorer-1 |  | 138 | SG | [21 empty] | 1
44.1 | AM |  | Thomas Hill-Adair-1 |  | 161 | RB |  |  | 44 | [6 empty] | 44 | [11 empty] | 2
1.45 | CY |  | Trail of Tears-Charmin |  | 161 | RT
0 | EW |  | Troy sub Tap (C.E.P.C. owned) |  | 161 | SG
11.96 | AX |  | Tyson-Meramec-4 |  | 138 | TS | [20 empty] | 1 |  | 1
3.15 |  |  | Venice-Campbell 1 |  | 138 | TS | [23 empty] | 1
3.91 | BW |  | Venice-Campbell-1 & 2 MO |  | 138 | TS | [20 empty] | 1
4.56 | YY |  | Wedekind-Sub Tap-1 |  | 161 | RT | [20 empty] | 1 | 0
11.36 | AN |  | Wedekind-Trail of Tears |  | 161 | RT | [20 empty] | 1 |  |  | 3
31.03 | FC | 5944 | Zachary-Ottumwa | ITC | 345 | RB | [9 empty] | 31 | [12 empty] | 0
Follow up ground crew to be charged to aerial trimming, not tree crew work. | [5 empty] | Totals | 0 | 45 | 155 | 0 | 0 | 0 | 0 | 0 | 0 | 206 | 137 | 0 | 23 | 34 | 23 | 26 | 0 | 0 | 0 | 0 | 98 | 84 | 110 | 141
[29 empty] | 1Q | 121
[29 empty] | 2Q | 369
Radial Taps | [28 empty] | 3Q | 425
[29 empty] | 4Q | 167
1082
Note on AD5: Breece, Rachel: non priority work
Note on D8: Strauss, Anthony D: includes Cahokia - Ashley 2 (MO Side) and Ashley - Venice 2 (MO Side)
Note on AC8: Campos Alfaro, Salvador: Moved to 3rd quarter due to crew availability
Note on AD8: Campos Alfaro, Salvador: Move to 4rth quarter due to crew availability
Note on D10: Strauss, Anthony D: Meramec Watson from str 40 to Baumgartner
Note on H12: Breece, Rachel: moved to 3rd quarter due to helicopter availabity
Note on T12: Breece, Rachel: non priority work
Note on AB12: Breece, Rachel: work identified on 2nd period 2022 patrol
Note on AC12: Breece, Rachel: work identified on 2nd period patrol 2023
Note on I13: Henderson, Michelle: pushed to 3rdQ due to helicopter availability
Note on AC13: Campos Alfaro, Salvador:Moved to 3rd due to recently being trimmed by helicopter.
Note on AD13: Campos Alfaro, Salvador: Move to 4th quarter due to crew availability
Note on D15: Strauss, Anthony D: Includes Mason-McClay from str 53 to Blanchette
Note on AC15: Campos Alfaro, Salvador: Moved to 3 quarter due to customer permission
Note on AD15: Campos Alfaro, Salvador: Moved to 4th Quarter due costumer permission
Note on AB18: Strauss, Anthony D: work completed in q4 of 2022
Note on D20: Strauss, Anthony D: Includes Cahokia Russell 2 & 4 (MO side). Includes Cahokia Gratiot str 6 to Gratiot sub. Includes Cahokia - Central Str 9-1010-1011-Gratiot
Note on AD26: Campos Alfaro, Salvador: move to 4 quarter due to crew availabilty
Note on D27: Strauss, Anthony D: Includes Cahokia Roxford from str 1150 to Campbell sub
Note on AD33: Breece, Rachel: non priority work
Note on AB36: Thurman, Ralph E: Additional work completed in 1sr QTR, due to crew availability
Note on AB37: Thurman, Ralph E: Work completed in 1sr QTR, due to crew availability
Note on D39: Porcelli, Jennifer L: Includes portion of Marshall-Tyson
Note on AB39: Strauss, Anthony D: permitted removals
Note on D41: Strauss, Anthony D: Includes Warson - Mason from str 57 to Dorsette sub. Includes Mason - Carrolton from Dorsette sub to str 129
Note on AC41: Campos Alfaro, Salvador: Moved to 3rd quarter due to crew availability
Note on AC42: Campos Alfaro, Salvador: Moved to 4rt quarter due to crew availability
Note on AD42: Strauss, Anthony D: moved to q4 due to crew availability
Note on D49: Graham, Sharon K: includes Belleau-GM-3 and GM-Point Prairie-3
Note on Q55: Breece, Rachel: non priority work
Note on T55: Breece, Rachel: work identified on 1st period patrol 2023
Note on D57: Strauss, Anthony D: Includes Page-Mason from Str 22 to Hunter sub. Includes Central - Watson str 55-2056-1079. Includes Marshall Lakeshire from structure 1079 to Hunter sub
Note on AC60: Thurman, Ralph E: Reclamation work identified by survey able to complete some work due to crew availabilty
Note on AD60: Thurman, Ralph E: Reclamation work identified by survey able to complete work due to crew availabilty
Note on AB61: Thurman, Ralph E: Moved to 2nd Qtr. Due to crew location
Note on AC65: Thurman, Ralph E: able to complete P-4 work due to crew availabilty
Note on AD65: Thurman, Ralph E: able to complete P-4 work due to crew availabilty
Note on AB66: Strauss, Anthony D: work identified on 2022 patrol
Note on D68: Strauss, Anthony D: Includes Meramec-Watson from Mackenzie Switch to str 86
Note on AC73: Breece, Rachel: non priority work
Note on D74: Strauss, Anthony D: Str 37A to Lakeshire sub
Note on AB74: Strauss, Anthony D: priority work moved to q1 due to avaiability of crews
Note on AC74: Strauss, Anthony D: priority work moved to q1 due to availability of crews.
Note on D75: Strauss, Anthony D: Includes Central - Watson and Marshall - Lakeshire from Marshall to str 1079
Note on D77: Strauss, Anthony D: Includes Mason - Carrolton and Carrollton Sioux from str 52 to carrolton sub
Note on AB77: Strauss, Anthony D: priority work moved up from q2 due to availability of crews
Note on AC77: Strauss, Anthony D: priority work moved to q1 due to avialability of crews
Note on D78: Strauss, Anthony D: only includes isolated section of Mason Gray Summit from str 98 to 327
Note on AB78: Strauss, Anthony D: Priority work moved up from q2 due to availability of crews.
Note on AC78: Strauss, Anthony D: moved to q1 due to availability of crews
Note on D79: Strauss, Anthony D: Includes Mason-Wildwood and Wildwood - Gray Summit from wildwood sub to Str 98
Note on AB79: Strauss, Anthony D: work moved up from q2 due to access issues.
Note on AC79: Strauss, Anthony D: some work moved to q1 due to access issuess
Note on AB81: Strauss, Anthony D: Priority work found on 2022 patrol
Note on D82: Strauss, Anthony D: Includes Mason Carrolton from Mason Sub to str 52. Includes Carrolton - Sioux from Sioux to str 52.
Note on T84: Breece, Rachel: lack of resources
Note on AB84: Breece, Rachel: work identified on 2nd period 2022 patrol
Note on AD85: Breece, Rachel: non prioroity work
Note on D87: Strauss, Anthony D: Includes Baumgartner Watson from Baumgartner to str 54
Note on AB87: Strauss, Anthony D: priority work moved to q1 due to availability of crews
Note on AC87: Strauss, Anthony D: moved to q1 due to availability of crews
Note on D88: Porcelli, Jennifer L: Includes Meramec-Sandy Creek and Sandy Creek-St. Francois
Note on AB88: Strauss, Anthony D: priority work from 2022 patrol
Note on D89: Strauss, Anthony D: Includes Baumgartner Watson from str 54 to Watson
Note on AC89: Campos Alfaro, Salvador: more work was found
Note on D93: Strauss, Anthony D: Includes Sioux - Roxford 1 & 2 from str 51 to 57
Note on AC94: Graham, Sharon K: completed in 1st qurter due to crew availability
Note on D96: Graham, Sharon K: include Montgomery-Spencer Creek, Spencer Creek-Maywood
Note on AC97: Graham, Sharon K: work completed in 1st quarter do to crew availabilty
Note on D100: Graham, Sharon K: includes: Osage Plant-Osage Sub (4 circuits), Osage-Eldon, Eldon-Barnett, Barnett-California, California-Overton
Note on J101: Breece, Rachel: work performed ahead of schedule
Note on T101: Breece, Rachel: lack of resources
Note on AB101: Breece, Rachel: work performed ahead of schedule
Note on D104: Strauss, Anthony D: Includes Warson - Mason
Note on D105: Strauss, Anthony D: Runs from Page to str 50 on Mason - Sioux.Includes Page - Berkeley and Berkeley - Sioux
Note on AD105: Campos Alfaro, Salvador: moved 1 mile to 4th quarter due to crew availability
Note on AD106: Campos Alfaro, Salvador: DONE WITH BUGLE CONSTRUCTION
Note on H108: Breece, Rachel: moved to 2nd quarter due to helicopter availablility
Note on AB108: Breece, Rachel: work identified on 2nd period 2022 patrol
Note on U109: Breece, Rachel: lack of resources
Note on AD109: Breece, Rachel: non priority work
Note on T110: Breece, Rachel: lack of resources
Note on AB110: Breece, Rachel: non prioority work
Note on AD110: Breece, Rachel: work identified on 2nd period 2023 patrol
Note on AE110: Breece, Rachel: work identified on 2nd period 2023 patrol
Note on H111: Breece, Rachel: moved to 2nd/3rd quarter due to helicopter availability
Note on U111: Breece, Rachel: lack of resources
Note on AC111: Breece, Rachel: work identified on 2nd period patrol 2023
Note on AD111: Breece, Rachel: work identified on 2nd period 2023 patrol
Note on AB113: Thurman, Ralph E: Additional work completed in 1sr QTR, due to crew availability
Note on AB114: Thurman, Ralph E: Additional work completed in 1sr QTR, due to crew availability
Note on AB116: Thurman, Ralph E: Low priority work moved to 2nd QTR.
Note on D118: Porcelli, Jennifer L: Includes portion of Rush Island Subtap
Note on AB120: Strauss, Anthony D: Work identified on 2022 patrol
Note on D122: Strauss, Anthony D: Includes Sioux - Meppen North 4 From str 176E to Str 146. Includes Out of Service lines from 146 to 122
Note on D123: Strauss, Anthony D: Runs from Sioux to str 77. Includes Sioux - Roxford 1 & 2
Note on AB124: Thurman, Ralph E: Additional work completed in 1sr QTR, due to crew availability
Note on AB125: Thurman, Ralph E: Reclamation work identified by survey able to complete some work due to crew availabilty
Note on AC125: Thurman, Ralph E: Finished reclamation work
Note on J131: Breece, Rachel: work performed ahead of schedule
Note on AC131: Breece, Rachel: non priority work
Note on D134: Porcelli, Jennifer L: Includes Tyson-Arnold and Arnold-Meramec
Note on AB134: Strauss, Anthony D: Capital
Note on D136: Strauss, Anthony D: Include Venice - Campbell from st 2020 to Campbell. Includes Venice Hall st from str 2020 to 1020
Note on AB136: Strauss, Anthony D: priority work found 2022 patrol
Note on AB137: Thurman, Ralph E: Work completed in 1st QTR, due to crew availability
Note on AD139: Breece, Rachel: non priority work

## MO
MO - 2023 - Scheduled vs. Completed Work
Quarter | Scheduled Miles | Completed Miles | Percentage Completed
1 | 390 | 121 | 31.03%
2 | 360 | 369 | 102.5%
3 | 224 | 425 | 189.7%
4 | 0 | 167 | #DIV/0!
Totals | 974 | 1082 | 111.1%

## AIC
| TV-F1-2023 |  |  | AMEREN IL TRANSMISSION LINES - 2023
|  |  | Please date any notes added |  | Scheduled Work Listed By Miles Unless Otherwise Noted
[7 empty] | Aerial Side Trimming Maintenance |  |  |  | Aerial Herbicide Maintenance |  |  |  | Ground Herbicide (L,H,B) Maintenance |  |  |  | Mowing Maintenance |  |  |  | Tree Trimming Maintenance |  |  |  | Tree Trimming Hotspot
Circuit Miles | Alpha Code | Line # | Line Name | ROW Name | Volt | VM Supv | 1st Q | 2nd Q | 3rd Q | 4th Q | 1st Q | 2nd Q | 3rd Q | 4th Q | 1st Q | 2nd Q | 3rd Q | 4th Q | 1st Q | 2nd Q | 3rd Q | 4th Q | 1st Q | 2nd Q | 3rd Q | 4th Q | 1st Q | 2nd Q | 3rd Q | 4th Q
1.95 | NJ | 1590 | ADM Faries Parkway-Hans |  | 138 | JM | [20 empty] | 1
1.27 | TE | 1651 | ADM North-ADM Faries Parkway |  | 138 | JM | [20 empty] | 1
8.23 | TG | 1616 | ADM North-Mount Zion Route 121 |  | 138 | JM | [20 empty] | 0 | 1
17.25 | BI |  | Albion South-Gibson, P.S. Indiana |  | 345 | JP | [20 empty] | 1
39.87 | AL |  | Albion South-Norris City North |  | 138 | JP
2.63 | AE | 1452B | American Steel-Sub Tap |  | 138 | TJM | [9 empty] | 0 | 3 | [11 empty] | 1
12.17 | SE | 1486 | Ashley-Mount Vernon West |  | 138 | JP | [20 empty] | 1
35.44 | SM | 1536 | Ashley-West Frankfort |  | 138 | JP | [21 empty] | 1 | 1 | 1
9.73 | T | 1619 | Auburn North-Austin |  | 138 | JM | [9 empty] | 10
36.5 | U | 1306 | Auburn North-Jacksonville Ind. Park |  | 138 | JM | [9 empty] | 37
5.35 | ZD | 4522 | Austin-Kincaid |  | 345 | JM | [20 empty] | 1
76.5 | JD | 4527 | Austin-Meredosia | ITC | 345 | JM
6.13 | BC |  | Avena-Sub Tap |  | 138 | JM | [20 empty] | 1
10.56 | BQ | 1482A | Aviston-Sub Tap |  | 138 | TJM | [20 empty] | 0 |  | 1 | 1
12.92 | TV | 4538/4531 | Baldwin-Prairie State-4538 |  | 345 | TJM
13.81 | TX | 4548 | Baldwin-Prairie State-4548 |  | 345 | TJM
2 | BR | 1526A | Baldwin-Sub Tap |  | 138 | TJM | 2 | [8 empty] | 0 | 2
20.78 | TM | 4521 | Baldwin-Turkey Hill |  | 345 | TJM | [9 empty] | 21 | [10 empty] | 5 | 0 | 0 | 5
0.99 | BS | 1586A | Belleville 17TH. ST. Spur |  | 138 | TJM | [9 empty] | 0 | 1
3.37 | BT | 1586B | Belleville 65TH ST Spur |  | 138 | TJM | [9 empty] | 0 | 3 | [9 empty] | 1
43.57 | SD | 1482 | Belleville Turkey Hill-Ashley |  | 138 | TJM | [20 empty] | 5 | 1 | 1 | 1
2.29 | SL | 1532 | Belleville Turkey Hill-South Belleville |  | 138 | TJM | [20 empty] | 1
13.16 | FF |  | Benton Northwest-Ina |  | 138 | JP | [20 empty] | 1 | 1 | 1
5.72 | CH | 1462 | Blue Mound-Sub Tap |  | 138 | JM
6.53 | ZH | 1638 | Bondville-SW Campus |  | 138 | MCH
28.54 | SX | 1582 | Brokaw-Gibson City |  | 138 | MCH | [21 empty] | 1
34.66 | RK | 1376 | Brokaw-Mahomet |  | 138 | MCH |  | 34.66 | [20 empty] | 2
9.1 | SW | 1578 | Brokaw-Normal East |  | 138 | JWM | [21 empty] | 1 | 1 | 1
5.63 | CB | 4555 | Brokaw-S Bloomington |  | 345 | JWM | [10 empty] | 6 | [10 empty] | 1 | 1 | 1
9.28 | SV | 1576 | Bunsonville-Tilton Energy Center |  | 138 | MCH
13.75 | KA |  | Cahoka-Dupo Ferry - 1 (Paralleled Circuits) |  | 138 | TJM | [9 empty] | 0 | 14 | [12 empty] | 1
36.23 | TL | 4511 | Cahokia-Baldwin |  | 345 | TJM | [20 empty] | 7 |  | 2 | 1
5.93 | TY | 1492A | Cahokia-Centerville |  | 138 | TJM
1 | VA |  | Cahokia-Central |  | 138 | TJM | [20 empty] | 1
1 | CX |  | Cahokia-Gratiot - 3 & Cahokia - Russell - 2 |  | 138 | TJM
18.2 | IB |  | Cahokia-Meramec 1 & 2 |  | 138 | TJM | [9 empty] | 0 | 18 | [9 empty] | 1 |  |  | 1
36.4 | LA | 4574 | Cahokia-Prairie State |  | 345 | TJM | [20 empty] | 2 | 1
3.2 | ML |  | Cahokia-Ridge 1& 2 |  | 138 | TJM | [22 empty] | 1
17.6 | AC |  | Cahokia-Roxford - 4 (Paralleled Circuits) |  | 345 | TJM | [9 empty] | 18 | [10 empty] | 1 | 3 |  | 1
0.63 | CY |  | Cahokia-Russell - 4 & Cahokia-Poplar - 5 |  | 138 | TJM
18.89 | SF | 4597 | Cahokia-Turkey Hill |  | 345 | TJM | [20 empty] | 4 | 4 | 1
4.5 | NA |  | Cahokia-Venice 1 & 2 |  | 138 | TJM | [22 empty] | 1
40.3 | UU |  | Cape-Joppa-1 |  | 161 | JP | 40 | [5 empty] | 40 | [13 empty] | 1 | 1 | 1
27.58 | K |  | Carbondale Northwest-W. Frankfort |  | 138 | JP | [16 empty] | 0 |  |  | 1 | 1 | 1 | 1 | 1
27.45 | BA |  | Casey West-Breed |  | 345 | MCH | [20 empty] | 1 | 1 | 1 | 1
21.16 | BF | 4525 | Casey West-Kansas West |  | 345 | MCH
21.13 | AZ | 4587 | Casey West-Neoga South |  | 345 | MCH
26.54 | BE |  | Casey West-Newton |  | 345 | MCH |  | 26.54 | [18 empty] | 1 | 1 | 1 | 1
11.63 | AG | 1540 | Castro-Canton South |  | 138 | JWM | [20 empty] | 1
28.51 | MK | 1394 | Caterpillar Mapleton-Sub Tap |  | 138 | JWM | [20 empty] | 1
20.06 | RB | 1313 | Clinton Rt. 54-N. Decatur |  | 138 | MCH
22.41 | TP | 4535 | Clinton-Brokaw |  | 345 | MCH |  | 22.41 | [8 empty] | 22 | [9 empty] | 1 | 1 | 1 | 1
43.16 | TR | 4545 | Clinton-Goose Creek |  | 345 | MCH | [20 empty] | 1
5.3 | ZI | 4571 | Clinton-Oreana |  | 345 | MCH | [17 empty] | 1 |  | 1 | 1
8.46 | NC | 1372B | Clinton-Sub Tap |  | 138 | MCH |  | 8 | [19 empty] | 1 |  | 1
22.34 | AX | 4557 | Coffeen North-Ramsey East |  | 345 | JM | [20 empty] | 1
0.28 | I | 4595 | Coffeen-Coffeen North |  | 345 | JM
4.74 | TH | 1626 | Coffeen-Midway |  | 138 | JM
30.4 | AW | 4516 | Coffeen-Pana North |  | 345 | JM |  | 30 | [18 empty] | 1
50.07 | TS | 4551 | Coffeen-Roxford |  | 345 | TJM | [16 empty] | 1 |  |  |  | 2 | 4 | 1 | 1
15.88 | LB | 4513 | Commodore-Aster |  | 345 | TJM | [20 empty] | 1 | 0
6.39 | AI |  | Crab Orchard-Marion North |  | 138 | JP | [20 empty] | 1 | 0
19.11 | VV |  | Crab Orchard-Muddy |  | 138 | JP | [20 empty] | 1 | 0
2.32 | RH | 1364A | Diamond Star-Sub Tap |  | 138 | JWM
0.83 | RC | 1326A | Diamond Star-Sub Tap |  | 138 | JWM
21.07 | BH | 4573 | Duck Creek-Ipava South |  | 345 | JWM | [20 empty] | 3
34.72 | ND | 4563 | Duck Creek-Tazewell |  | 345 | JWM | [20 empty] | 1 | 3
23.52 | CE |  | Dupo Ferry-Buck Knob - 1 (Paralleled Circuits) |  | 138 | TJM | [9 empty] | 0 | 24 | [9 empty] | 1 |  |  | 1
6.48 | AR |  | E. Quincy-Quincy South |  | 138 | JWM |  | 6
4.92 | SB | 1472 | East Belleville-Turkey Hill |  | 138 | TJM
5.87 | RT | 1432 | East Collinsville-O'Fallon Porter Road |  | 138 | TJM | [9 empty] | 0 | 6 | [9 empty] | 1 | 1
2.44 | RQ | 1416 | East Main Street-Route 51 Decatur |  | 138 | JM
30.5 | HB |  | East Quincy-Hamilton - 4 |  | 138 | JWM | [20 empty] | 0 | 1 | 1 | 1
14.63 | MN | 1422 | East Springfield-Sub Tap |  | 138 | JM | [16 empty] | 1
23.51 | MJ | 1358 shared | Edwards-Fargo 2 |  | 138 | JWM
4.7 | MP | 1374 | Edwards-Caterpillar 1 |  | 138 | JWM | [21 empty] | 1
5.81 | MD | 1345 | Edwards-Caterpillar Mapleton |  | 138 | JWM |  | 6 | [18 empty] | 1
14.62 | MX | 1397 | Edwards-Keystone |  | 138 | JWM | [20 empty] | 0
21.94 | PP |  | Effingham-Newton |  | 138 | MCH | [10 empty] | 22 | [9 empty] | 2
2.68 | MO | 1382A | El Paso-Sub Tap |  | 138 | JWM
7.46 | JB | 1385 | Faraday-Mount Zion PPG 1385 & 1637 |  | 138 | JM
33 | JA | 4507 | Faraday-Pana | ITC | 345 | JM | [20 empty] | 1
12 | MR | 1377 | Fargo-Moss Cat |  | 138 | JWM |  | 12 | [18 empty] | 1
5.54 | MF | 1347/1326 | Fargo-Pioneer |  | 138 | JWM | [20 empty] | 1 | 1
4.09 | MQ | 1526D | Fayetteville Bee Hollow-Sub Tap |  | 138 | TJM | 4 | [8 empty] | 0 | 4
14.28 | MU | 1526E | Fayetteville Bee Hollow-Sub Tap |  | 138 | TJM | 14 | [8 empty] | 0 | 14 | [9 empty] | 0
5.36 | ME | 1672 | Fogarty-Kickapoo |  | 138 | JM
2.84 | BK |  | Gibson City S-Gibson City PP |  | 138 | MCH
5.75 | NK | 1436A | Gillespie Macoupin St-Sub Tap |  | 138 | TJM | [23 empty] | 1
15.23 | ZJ | 1388 | Gilman-Watseka |  | 138 | MCH | [21 empty] | 0
14.71 | NL | 4575 | Goose Creek-Rising |  | 345 | MCH
16.66 | J |  | Grand Tower-Carbondale Northwest |  | 138 | JP | [14 empty] | 1 | [5 empty] | 1 |  | 2 | 1
30.54 | TT |  | Grand Tower-Marion South |  | 138 | JP | [21 empty] | 1 | 1
0.26 | BO |  | Grand Tower-Perryville |  | 138 | JP
1.99 | NM | 1674 | Hans-ADM North |  | 138 | JM
53.9 | RG | 1362 | Havana-Galesburg Monmouth Blvd |  | 138 | JWM | [23 empty] | 1
14.91 | ZA | 1356 | Havana-Ipava South |  | 138 | JWM | [20 empty] | 1
20.2 | RP | 1406 | Havana-Mason City West |  | 138 | JM | [9 empty] | 20 | [10 empty] | 1
46.48 | RF | 1352 | Havana-Huff |  | 138 | JWM | [10 empty] | 46 | [5 empty] | 1 | 1 |  |  | 1 |  |  | 1
48.17 | MY | 1422 | Havana-Shockey |  | 138 | JM | [9 empty] | 48 | [10 empty] | 2
0.65 | TI | 6101 | Hennepin-ComEd |  | 138 | JWM | [20 empty] | 1
31.39 | SP | 1552 | Hennepin-East Kewanee |  | 138 | JWM | [10 empty] | 31 | [9 empty] | 2
13.38 | SQ | 1556 | Hennepin-Oglesby |  | 138 | JWM | [20 empty] | 1
14.51 | SI | 1516 | Hennepin-Oglesby |  | 138 | JWM | [20 empty] | 1 | 1 | 1
26.27 | MZ | 1512 | Hennepin-Spring Bay |  | 138 | JWM | [10 empty] | 26
5.5 | ZC | 4549 | Herleman-Maywood(Illinois) | ITC | 345 | JWM |  | 6 | [8 empty] | 6
20.8 | MI | 1357 | Hines-Caterpillar Sub. 2 |  | 138 | JWM | [20 empty] | 0 | 1
20.88 | LL |  | Hoopeston-Paxton East |  | 138 | MCH
22.08 | KK | 1305 | Hoopeston-Vermilion |  | 138 | MCH | [23 empty] | 1
20.35 | DH |  | Huff-W. Washington |  | 138 | JWM | [10 empty] | 20 | [5 empty] | 1 | 1 | 1 |  | 1 | 1 |  | 1
7 | EA |  | Hull-Sub Tap-1 (Sioux S.Quincy to River) |  | 138 | TJM
33.66 | W | 1448 | Hutsonville-Kansas West |  | 138 | MCH | [20 empty] | 1 | 1 |  | 1
45.44 | O |  | Hutsonville-Neoga South |  | 138 | MCH | [20 empty] | 1 | 1
12.51 | XX |  | Hutsonville-Robinson (Marathon Oil) |  | 138 | MCH | [10 empty] | 11
11.04 | GG |  | Ina-Mt. Vernon 42nd St. (note Ip tap at structure 763) Same Circuit as HH) |  | 138 | JP | [23 empty] | 1
21.18 | AF | 1348 | Ipava South-Canton South |  | 138 | JWM | [10 empty] | 21 | [9 empty] | 1
21.41 | NN |  | Ipava South-Macomb West |  | 138 | JWM | [10 empty] | 21 | [9 empty] | 1
0.67 | CZ | 1401 | Ipava-Ipava South |  | 138 | JWM
0.71 | NO | 1512A | J&L-Sub Tap |  | 138 | JWM
1.71 | NP | 1552A | J&L-Sub Tap |  | 138 | JWM
19.81 | V | 1612 | Jacksonville Industrial Park-Meredosia East |  | 138 | JM
0.37 | DB | 1533 | Jarvis-Canteen |  | 138 | TJM
2.38 | DC | 1316 | Jarvis-Kren |  | 138 | TJM | [20 empty] | 1
41.7 | H |  | Jerseyville Northeast-Virden |  | 138 | JM | [9 empty] | 42 | [10 empty] | 2
0 | BL |  | Joppa,E.E.I -Joppa |  | 161 | JP
32.6 | ES |  | Joppa-Kelso |  | 345 | JP | [20 empty] | 1 |  | 2 | 2
32.44 | AU |  | Joppa-Marion South |  | 161 | JP | 32 | [19 empty] | 1 | 2 | 1 | 1
23.42 | AV |  | Joppa-Mound City West |  | 161 | JP | 23 | [5 empty] | 23 | [13 empty] | 2 | 1 | 1
10.8 | ZK |  | Kansas West-Charleston NE |  | 138 | MCH | [23 empty] | 1
18.98 | XA |  | Kansas West-Murdock |  | 138 | MCH | [19 empty] | 1
15.02 | Y |  | Kansas West-Paris South |  | 138 | MCH | [10 empty] | 15 | [9 empty] | 1 |  |  | 1
62 | ZL | 4559 | Kansas-Faraday | ITC | 345 | MCH | [20 empty] | 1 | 1
3.25 | NQ | 1366A | Kewanee South St-Sub Tap |  | 138 | JWM
1.57 | MA | 1325 | Kickapoo-Mcgrath |  | 138 | JM
27.6 | BM |  | Kinmundy-Louisville South |  | 138 | JM |  | 28 | [18 empty] | 2 | 1
31.06 | II |  | Kinmundy-Mt Vernon West |  | 138 | JP | [20 empty] | 3
29.5 | BN |  | Kinmundy-Ramsey East |  | 138 | JM | [20 empty] | 1 | 1
1 | WA | 1436/1456 | Laclede Steel Supply - 1 & 2 |  | 138 | TJM
23.85 | NF | 1646 | LaSalle N.-Fox River |  | 138 | JWM | [20 empty] | 1
24.82 | ZM | 4515 | Latham-Oreana |  | 345 | MCH | [20 empty] | 1
22.8 | AB |  | Lawrenceville South-Olney North |  | 138 | MCH | [10 empty] | 23 | [12 empty] | 1
21.63 | ZZ |  | Lawrenceville South-Robinson |  | 138 | MCH | [10 empty] | 22
9.89 | AD |  | Lawrenceville South-Vincennes |  | 138 | MCH | [10 empty] | 10
7.2 | TY | 1446A | Litchfield-Sub Tap |  | 138 | TJM | [23 empty] | 1
20.49 | N |  | Louisville South-Newton |  | 138 | JM | [20 empty] | 1
22.5 | BU |  | Louisville South-Olney North |  | 138 | JM | [20 empty] | 1
41.37 | C |  | Macomb Northeast-Niota |  | 138 | JWM | [16 empty] | 1 |  | 0 |  | 1
41 | DA |  | Macomb-Sub Tap |  | 138 | JWM | [10 empty] | 41
2.82 | OO |  | Macomb West-Macomb Northeast |  | 138 | JWM | [20 empty] | 1
6.82 | TZ | 1452A | Madison Industrial-Stallings |  | 138 | TJM | [9 empty] | 0 | 7
0.19 | AE | 1452 T | Madison State St-Sub Tap |  | 138 | TJM
1.55 | BV | 1592A | Mahomet-Sub Tap |  | 138 | MCH
15.71 | CA | 4505 | Mapleridge-Fargo |  | 345 | JWM | [23 empty] | 1
6.8 | DE |  | Marion North-Herrin East |  | 138 | JP | [16 empty] | 1 |  | 2 | 2 | 1
9.1 | UA |  | Marion South-Crab Orchard |  | 138 | JP | [20 empty] | 1 | 0
6.6 | TJ | 6102 | Marseilles-ComEd |  | 138 | JWM | [20 empty] | 2
35.3 | RE | 1346 | Mason City West-Latham |  | 138 | JM |  | 35 | [7 empty] | 35
15.4 | G |  | Mattoon West-Charleston NE |  | 138 | MCH |  | 15 | [18 empty] | 1 | 1 |  | 1
14.2 | RR |  | Mattoon West-Neoga |  | 138 | MCH |  | 14 | [8 empty] | 14 | [9 empty] | 1 | 1 |  | 1
1.55 | MB | 1325 | McGrath-Limit |  | 138 | JM
53.05 | RL | 1382 | McLean-Oglesby |  | 138 | JWM |  | 53 | [20 empty] | 1
41.31 | MM |  | Meredosia East-Ipava South |  | 138 | JWM |  | 41 | [8 empty] | 41 | [5 empty] | 1 |  |  |  | 3
31 | D |  | Meredosia East-Roodhouse West |  | 138 | TJM | [20 empty] | 0 | 1 |  | 3
45.55 | DD |  | Meredosia-East Quincy (North Line No. 1) |  | 138 | JWM | [20 empty] | 0 | 1
45.43 | AJ |  | Meredosia-East Quincy (South Line No. 2) |  | 138 | JWM | [20 empty] | 2
45.8 | NH | 4503 | Meredosia-Herleman | ITC | 345 | JWM
46.9 | NG | 4539 | Meredosia-Ipava | ITC | 345 | JWM | [20 empty] | 1
0.65 | F |  | Meredosia-Meredosia East Lines 1,2,3,4 |  | 138 | JWM
28.23 | SN | 1542 | Midway-South Centralia |  | 138 | JP | [20 empty] | 1
0.66 | RM | 1386B | Mira-Sub Tap |  | 138 | MCH
0.9 | DM |  | Mississippi Sub 3rd Supply (Laclede - 1 (1436) to Mississippi) |  | 138 | TJM
1 | BX |  | Mississippi Sub Supply 1 & 2 (Sioux-Roxford 1 & 2 to Mississippi) |  | 138 | TJM | [21 empty] | 1
0.14 | RD | 1342A | Monsanto-Sub Tap |  | 138 | JM | [24 empty] | 182-180A, 176-175, 170-169, 167A-166, 165B-165, 164A-164, 159B-159A, 158B-158A
5.23 | MV | 1395 | Moss-Cat-Hallock |  | 138 | JWM | [20 empty] | 1
39 | BG | 4591 | Mount Vernon West-Xenia |  | 345 | JP | [20 empty] | 1 | 1 | 1
4.43 | BY | 1462A | Mount Zion PPG-Sub Tap |  | 138 | JM | [20 empty] | 1
2.36 | BZ | 1574 | Mount Zion Route 121-Mount Zion PPG |  | 138 | JM | [20 empty] | 0 | 1
3.37 | AN |  | Moweaqua North-Sub Tap |  | 138 | JM | [20 empty] | 1
12.55 | CD | 1462B | Mt. Auburn-Sub Tap |  | 138 | JM | [20 empty] | 1 | 0
3.14 | HH |  | Mt. Vernon 42nd St.-Mt. Vernon West (Structure 763 to MT Vernon IP sub) |  | 138 | JP | [23 empty] | 1
40.8 | SS |  | Murdock-Mattoon |  | 138 | MCH | [21 empty] | 3 | 1 | 1
15.46 | Z |  | Murdock-Sidney |  | 138 | MCH
4.35 | AT |  | N. Marblehead-Quincy, 3rd & Jefferson |  | 138 | JWM | [20 empty] | 1 |  | 1
13.36 | QQ |  | Neoga-Effingham |  | 138 | MCH
12 | MS | 1318 | New Holland-Kickapoo |  | 138 | JM
34.32 | YY |  | Newton-Robinson |  | 138 | MCH | [10 empty] | 34
27.81 | CV |  | Newton-Xenia |  | 345 | JM | [16 empty] | 1 | 2 |  |  | 1
23.14 | AM |  | Norris City North-Muddy |  | 138 | JP | [20 empty] | 1
1.93 | TC | 1604 | North 27th Street Decatur-ADM North |  | 138 | JM
2.54 | CF | 1522A | North 27th Street Decatur-Sub Tap |  | 138 | JM
16.55 | RM | 1386 | North Champaign-Sidney |  | 138 | MCH | [21 empty] | 1
17.5 | SC | 1476 | North Coulterville-Steeleville |  | 138 | JP | [20 empty] | 1
0.47 | EU | 2303 | North Coulterville-Sub Tap |  | 345 | TJM
2.67 | SJ | 1522 | North Decatur-East Main Street |  | 138 | JM
16.9 | CG | 1350 | North Decatur-Latham - 1350 |  | 138 | JM | [9 empty] | 17 | [10 empty] | 1
14.99 | ST | 1566 | North Decatur-Latham - 1566 |  | 138 | JM | [20 empty] | 1
2.18 | TB | 1602 | North Decatur-North 27th Street Decatur |  | 138 | JM
32.89 | RD | 1342 | North Decatur-West Illiopolis |  | 138 | JM |  | 33 | [7 empty] | 33 | [6 empty] | 1 |  |  |  | 1
10.51 | CH | 1556A | North LaSalle-Sub Tap |  | 138 | JWM
22.93 | RW | 1446 | North Staunton-Midway |  | 138 | TJM | [22 empty] | 1 | 2
3.89 | SG | 1496 | Oglesby-LaSalle |  | 138 | JWM | [20 empty] | 2 | 1 | 1
16.4 | CI | 1516B | Oglesby-Ottawa |  | 138 | JWM | [10 empty] | 16
28.01 | AK |  | Olney North-Albion South |  | 138 | JP | [20 empty] | 2
3.24 | TD | 1606 | Oreana-ADM North - 1606 |  | 138 | JM
3.93 | TF | 1610 | Oreana-ADM North - 1610 |  | 138 | JM
8.49 | ZN | 4571A /4545A | Oreana-Sub Tap |  | 345 | MCH | [21 empty] | 1
9.1 | NE | 1652 | Ottawa-Fox River |  | 138 | JWM | [20 empty] | 1
1.89 | B |  | Palmyra-N. Marblehead |  | 161 | JWM | [20 empty] | 1
18.43 | JJ | 1408 | Pana North-Ramsey East |  | 138 | JM |  | 18 | [18 empty] | 1
33.6 | JC | 4553 | Pana-Austin | ITC | 345 | JM | [20 empty] | 1
31.8 | SA | 1466 | Pana-Midway |  | 138 | JM | [9 empty] | 32
34.2 | P |  | Pana-Neoga South |  | 138 | JM
1.34 | ZE | 1390 | Pana-Pana North - 1390 |  | 138 | JM
33.49 | RZ | 1462 | Pana-Route 51 Decatur |  | 138 | JM | [9 empty] | 33 | [10 empty] | 1
11.7 | Q | 1549 | Pana-Taylorville South |  | 138 | JM
1.27 | ZF | 1423 | Pawnee West-Austin |  | 138 | JM
18 | S |  | Pawnee West-Taylorville South |  | 138 | JM | [12 empty] | 1
16.79 | CC |  | Paxton East-Gibson City South |  | 138 | MCH | [10 empty] | 17 | [9 empty] | 1 | 1 |  | 1
22.13 | AP |  | Paxton East-Gilman |  | 138 | MCH | [20 empty] | 1 | 1
32.6 | ET |  | Pickneyville-W. Frankfort |  | 230 | JP | 33 | [19 empty] | 1 | 1 | 2 | 2
| DF |  | Pioneer-Hines |  | 138 | JWM | [20 empty] | 0 | 1
4.38 | RU | 1434 | Porter Rd-E Belleville |  | 138 | TJM | [20 empty] | 1 | 1
7.22 | LC | 4552 | Prairie State-Aster |  | 345 | TJM | [20 empty] | 1 | 0
39.43 | TQ | 4541 | Prairie State-Mount Vernon West-4541 |  | 345 | TJM | [16 empty] | 1 |  |  |  |  | 1
46.29 | TO | 4531 | Prairie State-Stallings |  | 345 | TJM | 46 | [19 empty] | 6 | 1 | 2 | 1
16.46 | CJ | 1552B | Princeton-Sub Tap |  | 138 | JWM | [16 empty] | 1 | 1 | 1 |  | 2 | 1
4.6 | AS |  | Quincy South-N. Marblehead |  | 138 | JWM |  | 5
30.45 | AY | 4509 | Ramsey East-Neoga South |  | 345 | JM | [16 empty] | 1 |  |  |  | 1
16.5 | BB |  | Rantoul-Rising |  | 138 | MCH | [20 empty] | 0 | 1
6.9 | ZO |  | Rantoul-Sub Tap |  | 138 | MCH
5.72 | ZP | 1642 | Rising-Bondville |  | 138 | MCH
9.02 | SZ | 1592 | Rising-N. Champaign |  | 138 | MCH | [20 empty] | 0 | 1
1.7 | ZR |  | Robinson Marathon North-Sub Tap |  | 138 | MCH
0.25 | ZQ |  | Robinson Marathon-Robinson Marathon North |  | 138 | MCH
28.24 | E |  | Roodhouse West-Jerseyville Northwest |  | 138 | TJM | [20 empty] | 1
1 | ZX |  | Roxford-Wood River Refinery-2 (SOUTH LINE TO CONOCO) |  | 138 | TJM
29.67 | ZY | 4585 | Rush Island-Baldwin |  | 345 | TJM | [23 empty] | 1
8.34 | SY | 1586 | S. Belleville-Centerville |  | 138 | TJM | [9 empty] | 0 | 8 | [9 empty] | 2 | 2 | 1
4.93 | SR | 1562 | S. Bloomington-Brokaw |  | 138 | JWM | [20 empty] | 1 |  | 1
5.63 | TA | 1596 | S. Bloomington-Brokaw 1596 |  | 138 | JWM | [21 empty] | 1
23.01 | RJ | 1372 | S. Bloomington-Clinton Rt. 54 |  | 138 | MCH | [10 empty] | 23 | [11 empty] | 1
7.28 | RC | 1544 | S. Bloomington-McLean |  | 138 | JWM
0.2 | RI | 1614 | Sandburg-E Galesburg |  | 138 | JWM
32.13 | RI | 1366 | Sandburg-East Kewanee |  | 138 | JWM | [20 empty] | 1
44.13 | ZB | 4547 | Sandburg-Fargo | ITC | 345 | JWM | [10 empty] | 44 | [9 empty] | 1
8.63 | RN | 1392 | Sandburg-Galesburg Monmouth Blvd |  | 138 | JWM
5.75 | CK | 1380 | Schram City-Sub Tap |  | 138 | JM | [9 empty] | 6
7.6 | AO |  | Shawnee-Joppa-1 |  | 345 | JP | [22 empty] | 1 | 1
51.96 | BD | 4565 | Shawnee-West Frankfort East |  | 345 | JP | [20 empty] | 0 |  | 1
6.64 | CM | 1704 | Shockey-Gillett |  | 138 | JM
31.3 | TK | 4501 | Sidney-Eugene |  | 345 | MCH |  | 31 | [18 empty] | 1 | 1 | 1 | 1
35.19 | TN | 4525 | Sidney-Kansas |  | 345 | MCH | [10 empty] | 35 | [9 empty] | 1
31.4 | AA | 1524 | Sidney-Paxton East |  | 138 | MCH | [20 empty] | 1 | 1
24.25 | NI | 4567 | Sidney-Rising | ITC | 345 | MCH |  | 24 | [19 empty] | 1 | 1
14.64 | RA | 1312 | Sidney-SW Campus |  | 138 | MCH | [21 empty] | 1
0.5 | CL |  | Sioux-Roxford 1 & 2 - IL |  | 345 | TJM | [21 empty] | 1
87.43 | X |  | Sioux-South Quincy - 4 |  | 138 | TJM | [21 empty] | 6 | 3 | 1
5.58 | RH | 1334 | S. Bloomington-W. Washington |  | 138 | JWM | [23 empty] | 1
36.77 | SK | 1526 | South Belleville-Tilden |  | 138 | TJM | 37 | [8 empty] | 0 | 37 | [9 empty] | 4 |  | 2 | 1
15.8 | SO | 1546 | South Centralia-Mount Vernon West |  | 138 | JP | [20 empty] | 1
6.48 | CN |  | South Quincy-East Quincy - 4 |  | 138 | JWM | [10 empty] | 6 | [9 empty] | 1 | 1
2.34 | CO | 1476C | Sparta-Sub Tap |  | 138 | JP
8.6 | RS | 1426 | Stallings-East Collinsville |  | 138 | TJM | [9 empty] | 0 | 9 | [9 empty] | 2
8.54 | TW | 4581 | Stallings-Roxford |  | 345 | TJM | [20 empty] | 2 |  |  | 1
27.93 | WW | 1636 | Steeleville-Grand Tower |  | 138 | JP | 28 | [13 empty] | 1 | 1 |  |  |  |  | 1 |  | 1 | 1
34 | ZS | 4512 | Sugar Creek-Kansas | ITC | 345 | MCH | [21 empty] | 1
8.45 | R |  | Taylorville South-Taylorville Northeast |  | 138 | JM
12 | MG | 1353 | Tazewell-E Peoria |  | 138 | JWM | [20 empty] | 1 | 1
61.75 | MT | 1367 | Tazewell-E. Springfield |  | 138 | JWM | [19 empty] | 1
9.88 | MH | 1354 | Tazewell-Eastern |  | 138 | JWM | [23 empty] | 1
0.64 | NB | 4521 | Tazewell-Powerton (C.E.) |  | 345 | JWM
8.58 | CP | 1342C | Turris Coal-Sub Tap-1342A |  | 138 | JM
10 | ZU | 1302A | Valmeyer-Sub Tap |  | 138 | TJM | [22 empty] | 1 | 1
1 | CQ |  | Venice-Campbell - 1 (Partially Paralleled Circuits) |  | 138 | TJM
1 | BW |  | Venice-Campbell - 2 |  | 138 | TJM
3.37 | DG | 1359 | Venice-Madison Industrial |  | 138 | TJM | [9 empty] | 0 | 3 | [12 empty] | 1
5 | CR |  | Venice-Ridge - 4 |  | 138 | TJM
0.27 |  |  | Venice-Venice Peaker #3 & #4 |  | 138 | TJM
0.33 |  |  | Venice-Venice Peaker North |  | 138 | TJM
26.8 | RO | 1396 | Vermilion-N. Champaign |  | 138 | MCH | [20 empty] | 1 | 1
11.44 | SU | 1572 | Vermilion-Tilton Energy Center |  | 138 | MCH | [21 empty] | 1
12.8 | HA |  | Virden-Austin |  | 138 | JM | [9 empty] | 13
36.25 | TU | 4561 | W Frankfort East-Mt. Vernon West |  | 345 | JP |  |  | 36 | [13 empty] | 1 |  | 4 | 2 | 1 | 1
11.29 | AH |  | W. Frankfort East-Herrin East |  | 138 | JP | [23 empty] | 1
20.2 | M |  | W. Frankfort East-Muddy |  | 138 | JP | [20 empty] | 1 |  |  | 1
33.1 | BJ |  | W. Frankfort East-Norris City North |  | 345 | JP | [20 empty] | 1 | 1 |  | 1
10.21 | EE |  | W. Frankfort-Benton Northwest |  | 138 | JP | [20 empty] | 1 |  |  | 1
47.65 | A |  | W. Frankfort-Joppa |  | 230 | JP |  |  | 48 | [17 empty] | 2 | 2 | 5 | 3
5.25 | L |  | W. Frankfort-W. Frankfort East |  | 138 | JP | [6 empty] | 5 | [16 empty] | 1
1.28 | BP | 1356 | Wallace-E. Peoria |  | 138 | JWM
3.27 | MW | 1396 | Wallace-Keystone |  | 138 | JWM |  | 3
11.5 | MC | 1344 | Wallace-Spring Bay |  | 138 | JWM | [17 empty] | 1 |  |  | 1
3.72 | CS | 1322A | Waltonville Sub Tap |  | 138 | JP | [20 empty] | 1
14.55 | AQ |  | Watseka-Goodland |  | 138 | MCH | [21 empty] | 0
0.25 | CT | 1312A | Windsor Road Sub Tap |  | 138 | MCH | [21 empty] | 1
14.13 | RX | 1452 | Wood River-Madison Industrial |  | 138 | TJM | [9 empty] | 4 | 10 | [9 empty] | 1 | 1 | 1 | 1
25.46 | RV | 1436 | Wood River-North Staunton |  | 138 | TJM | [20 empty] | 1 |  | 1 | 1
4.07 | SH | 1506 | Wood River-Roxford |  | 138 | TJM | [22 empty] | 1
6.36 | CU | 1502 | Wood River-Roxford (NORTH LINE TO CONOCO) |  | 138 | TJM | [20 empty] | 1
17.84 | RY | 1456 | Wood River-Stallings |  | 138 | TJM | [20 empty] | 2 | 1 |  | 2
10.82 | CW | 1570 | Woodhall-Hallock |  | 138 | JWM | [20 empty] | 1 | 1
Follow up ground crew to be charged to aerial trimming, not tree crew work. | [5 empty] | Totals | 0 | 175.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 248 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 2 | 20 | 27 | 9 | 14 | 0 | 0 | 0
[29 empty] | 1Q | 20
[29 empty] | 2Q | 203.61
Radial Tap | [28 empty] | 3Q | 257
[29 empty] | 4Q | 16
496.61
1136.54 | [6 empty] | 0 | 175.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 248 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 2 | 20 | 27 | 9
[31 empty] | 0 | 0 | 0
Note on AB5: Morrison, Jim B: Non priority work identified on the 2022 patrol
Note on AB6: Morrison, Jim B: Work was performed in support of a line reroute
Note on AB7: Morrison, Jim B: Work was moved to early 2nd quarter based on crew availability
Note on Q10: Strauss, Anthony D: non priority work delayed to q3
Note on R10: Strauss, Anthony D: non priority work from q2
Note on AD10: Strauss, Anthony D: priority work found on 2023 patrol
Note on AC12: Part, Jesse: Non-priority work identified on 2022 patrol.
Note on AD12: Part, Jesse: 2/9/24 Non-priority work identified on 2023 patrol.
Note on AE12: Part, Jesse: 2/9/24 Non-priority work identified on 2023 patrol.
Note on AB15: Morrison, Jim B: Clearing was performed in support of a line reroute project
Note on AB18: Strauss, Anthony D: work completed in q4 2022
Note on AD18: Strauss, Anthony D: priority work found on 2023 patrol
Note on AE18: Strauss, Anthony D: priority work found on 2023 patrol
Note on Q21: Strauss, Anthony D: non priority work moved to q3
Note on R21: Strauss, Anthony D: non priority work from q2
Note on AC22: Strauss, Anthony D: non priority work pushed back till after 2023 repatrol
Note on AD22: Strauss, Anthony D: non priority work pushed back till after 2023 re patrol
Note on Q23: Strauss, Anthony D: non priority work moved to q3
Note on R23: Strauss, Anthony D: non priority work from q2
Note on Q24: Strauss, Anthony D: non priority work moved to q3
Note on R24: Strauss, Anthony D: non priority work from q2
Note on AB24: Strauss, Anthony D: Priority work found on 2023 patrol
Note on AC25: Strauss, Anthony D: priority work left over from q1
Note on AD25: Strauss, Anthony D: priority work found on 2023 patrol
Note on AE25: Strauss, Anthony D: priority work found on 2023 patrol
Note on AB27: Part, Jesse: Trim trees in support of a shoo-fly reroute for construction project.
Note on AD27: Part, Jesse: 2/9/24 Non-priority work identified on 2023 patrol.
Note on AC30: Henderson, Michelle: work identified on 2nd Q patrol
Note on AD31: Cox, Jeremy J: Helicopter Cleanup
Note on AC32: Mohr, Jeremy W: work identified on 2023 patrol
Note on AD32: Mohr, Jeremy W: work identified on 2023 patrol
Note on AE32: Mohr, Jeremy W: work identified on 2023 patrol
Note on AC33: Mohr, Jeremy W: work identifed on 2023 patrol
Note on AD33: Mohr, Jeremy W: work identified on 2023 patrol
Note on AE33: Mohr, Jeremy W: work identified on 2023 patrol
Note on Q35: Strauss, Anthony D: non priority work moved to q3
Note on R35: Strauss, Anthony D: non priority work from q2
Note on AE35: Strauss, Anthony D: priority work found on 2023 patrol
Note on AD36: Strauss, Anthony D: priority work found on 2023 patrol
Note on AB38: Strauss, Anthony D: priority work found on 2023 patrol
Note on Q40: Strauss, Anthony D: non priority work moved to q3
Note on R40: Strauss, Anthony D: non priority work from q2
Note on AB40: Strauss, Anthony D: non priority work completed due to availability of crews
Note on AE40: Strauss, Anthony D: Priority work found on 2023 patrol
Note on AB41: Strauss, Anthony D: work moved up due to availability of crews
Note on AC41: Strauss, Anthony D: work moved to q1 due to availability of crews
Note on AD42: Strauss, Anthony D: priority work found on 2023 patrol
Note on AB43: Strauss, Anthony D: work moved to q1 due to availability of crews
Note on AC43: Strauss, Anthony D: some work moved to q1 due to availability of crews
Note on AE43: Strauss, Anthony D: Priority work found on 2023 patrol
Note on AD45: Strauss, Anthony D: priority work found on 2023 patrol
Note on AD46: Strauss, Anthony D: priority work found on 2023 patrol
Note on AB47: Part, Jesse: Priority worked moved up to 1st quarter.
Note on AC47: Part, Jesse: Non-priority work identified on 2022 patrol.
Note on AD47: Part, Jesse: 2/9/24 Non-priority work identified on 2023 patrol.
Note on X48: Part, Jesse: Reclamation (Pending permitting) UPDATE: Will have to wait until 345kV project in 6-7 years to clear additional 25' on NBZ due to permitting.
Note on AA48: Part, Jesse: 2/9/24 Jaraffe trimming ISO SIRP construction project.
Note on AC48: Part, Jesse: Non-priority work identified on 2022 patrol.
Note on AD48: Part, Jesse: 2/9/24 Non-priority work identified on 2023 patrol.
Note on AE48: Part, Jesse: 2/9/24 Non-priority work identified on 2023 patrol.
Note on AB49: Henderson, Michelle: construction access clearing
Note on AC49: Henderson, Michelle: construction clearing
Note on AD49: Henderson, Michelle: construction clearing
Note on AE49: Henderson, Michelle: construction clearing
Note on AB52: Henderson, Michelle: reclamation
Note on AC52: Henderson, Michelle: work identified on 4thQ patrol
Note on AD52: Cox, Jeremy J: work identified on 2nd Q patrol
Note on AE52: Cox, Jeremy J: work identified on 2nd Q patrol
Note on AB56: Henderson, Michelle: work identified on 1st period ground patrol
Note on AC56: Henderson, Michelle: helicopter cleanup
Note on AD56: Cox, Jeremy J: work identified 2nd Q partol
Note on AE56: Cox, Jeremy J: work identified 2nd Q partol
Note on AB57: Henderson, Michelle: work identified on 1st period ground patrol
Note on Y58: Henderson, Michelle: construction clearing
Note on AA58: Cox, Jeremy J: construction clearing
Note on AB58: Henderson, Michelle: construction clearing
Note on AC59: Henderson, Michelle: helicopter cleanup
Note on AE59: Cox, Jeremy J: helicopter cleanup
Note on AB60: Morrison, Jim B: Priority work wa found on 2022 fourth quarter patrol
Note on X64: Strauss, Anthony D: veg rec work
Note on AB64: Strauss, Anthony D: Priority work found on 2023 patrol and construction
Note on AC64: Strauss, Anthony D: work completed due to proximity of crews
Note on AD64: Strauss, Anthony D: Priority work found on 2023 patrol
Note on AE64: Strauss, Anthony D: Construction and priority work found on 2023 patrol
Note on AB65: Strauss, Anthony D: work moved to q1 due to availability of crews
Note on AC65: Strauss, Anthony D: work moved to q1 due to availability of crews
Note on AB66: Part, Jesse: Priority worked moved up to 1st quarter.
Note on AB67: Part, Jesse: Priority worked moved up to 1st quarter.
Note on AC71: Mohr, Jeremy W: mow brush per customer request, completed additional mowing while in the area
Note on Q72: Strauss, Anthony D: non priority work moved to q3
Note on R72: Strauss, Anthony D: non priority work from q2
Note on AB72: Strauss, Anthony D: nonpriority work completed due to proximity of crews.
Note on AE72: Strauss, Anthony D: priority work found on 2023 patrol
Note on Q75: Strauss, Anthony D: non priority work moved to q3
Note on R75: Strauss, Anthony D: non priority work moved from q2
Note on AC75: Strauss, Anthony D: work from 2022 patrol
Note on AB77: Mohr, Jeremy W: work moved to 2nd QRT due to avilable resources
Note on AD77: Mohr, Jeremy W: construction clearing
Note on AE77: Mohr, Jeremy W: construction clearing
Note on X78: Morrison, Jim B: Reclamation
Note on AC80: Mohr, Jeremy W: moved brush per customer request
Note on AB82: Mohr, Jeremy W: priority tree was clear upon arrival
Note on AB83: Henderson, Michelle: non priority mow work
Note on AB86: Morrison, Jim B: Non priority work identified on the 2023 patrol
Note on AC88: Mohr, Jeremy W: clearing on fee owned property
Note on Q89: Strauss, Anthony D: non priority work moved to q3
Note on R89: Strauss, Anthony D: non priority work from q2
Note on Q90: Strauss, Anthony D: non priority work moved to q3
Note on R90: Strauss, Anthony D: non priority work from q2
Note on AB90: Strauss, Anthony D: work performed in q4 2022.
Note on AE93: Strauss, Anthony D: priority work found on 2023 patrol
Note on AC94: Henderson, Michelle: non-priority reclamation work postponed indefinitely due to upcoming LRTP construction on the affected properties
Note on V96: Part, Jesse: 2/9/24 Intren mowed ROW for construction access.
Note on AD96: Part, Jesse: 2/9/24 Non-priority work identified on 2023 patrol and construction access clearing.
Note on AE96: Part, Jesse: 2/9/24 Non-priority work identified on 2023 patrol and construction access clearing.
Note on AC97: Part, Jesse: Non-priority work identified on 2022 patrol.
Note on AD97: Part, Jesse: 2/9/24 Non-priority work identified on 2023 patrol.
Note on AE100: Mohr, Jeremy W: work identified on 2023 patrol
Note on X103: Mohr, Jeremy W: additional singed reclamation completed
Note on AE103: Mohr, Jeremy W: work identified on 2023 patrol
Note on AB107: Mohr, Jeremy W: construction access clearing needed
Note on AB108: Mohr, Jeremy W: construction access clearing needed
Note on AC108: Mohr, Jeremy W: contruction clearing request
Note on AD108: Mohr, Jeremy W: work identified in 2023
Note on AB111: Mohr, Jeremy W: work moved to April due to customer
Note on AE113: Cox, Jeremy J: non priority work
Note on X114: Mohr, Jeremy W: reclamation started in March
Note on Z114: Mohr, Jeremy W: Last of reclamation completed
Note on AC114: Mohr, Jeremy W: maintanance work completed near reclamation
Note on AE114: Mohr, Jeremy W: work identified on 2023 patrol
Note on AB116: Henderson, Michelle: work identified on 3rd period 2022 patrol
Note on AC116: Henderson, Michelle: work identified on 3rd Q patrol
Note on AE116: Cox, Jeremy J: work identified on 3rd Q patrol
Note on AB117: Henderson, Michelle: non priority work identified on 3rd period 2022 patrol
Note on AE119: Part, Jesse: 2/9/24 Non-priority work identified on 2023 patrol.
Note on AB130: Part, Jesse: Non-priority work identified on 2022 patrol.
Note on AD130: Part, Jesse: 2/9/24 Non-priority work identified on 2022 patrol.
Note on AE130: Part, Jesse: 2/9/24 Non-priority work identified on 2022 patrol.
Note on AB131: Part, Jesse: Priority work identified on 2022 patrol. Moved up to 1st quarter.
Note on AC131: Part, Jesse: Non-priority work identified on 2022 patrol.
Note on AD131: Part, Jesse: 2/9/24 Non-priority work identified on 2023 patrol.
Note on AE131: Part, Jesse: 2/9/24 Non-priority work identified on 2023 patrol.
Note on AB132: Part, Jesse: Priority work identified on 2022 patrol. Moved up to 1st Q. Access work in support of construction project.
Note on AC132: Part, Jesse: Non-priority work identified on 2022 patrol.
Note on AD132: Part, Jesse: 2/9/24 Non-priority work identified on 2023 patrol.
Note on AE133: Cox, Jeremy J: non priority work
Note on AA134: Cox, Jeremy J: construction clearing
Note on AB135: Henderson, Michelle: work identified on 3rd period 2022 patrol
Note on AE135: Cox, Jeremy J: non priority work
Note on AB136: Henderson, Michelle: work identified on 1st period ground patrol
Note on AC136: Henderson, Michelle: work identified on 1st Q 2023 patrol
Note on AB139: Morrison, Jim B: 1 mile was moved into early second quarter based on crew availability
Note on AB141: Morrison, Jim B: 1 mile of work was moved up to the 4th quarter of 2022, one mile was moved to early 2nd quarter of 2023 based on site accessibility
Note on AB144: Henderson, Michelle: work identified on 1st period ground patrol
Note on AE145: Cox, Jeremy J: work identified on 3rd Q patrol
Note on AE148: Strauss, Anthony D: priority work found on 2023 patrol
Note on X151: Mohr, Jeremy W: completed 3 QRT reclamation with priority work
Note on Z151: Mohr, Jeremy W: completed in 1st QRT with priority work
Note on Q154: Strauss, Anthony D: non priority work delayed to q3
Note on R154: Strauss, Anthony D: non priority work from q2
Note on AE157: Mohr, Jeremy W: utilized jarraff on crop locked backyard trimming
Note on X158: Part, Jesse: Continued reclamation. Crew was pulled off this project to work on a large scale clearing project for SIRP.
Note on Z158: Part, Jesse: 2/9/24 Continued reclamation
Note on AA158: Part, Jesse: 2/9/24 Continued reclamation
Note on AB158: Part, Jesse: Non-priority work identified on 2022 patrol.
Note on AB159: Part, Jesse: Work completed early due to crew availability.
Note on AC159: Part, Jesse: Moved to 1st quarter
Note on AB160: Mohr, Jeremy W: construction access cleared
Note on AB162: Henderson, Michelle: construction work
Note on AC162: Henderson, Michelle: construction work
Note on AE162: Cox, Jeremy J: work identified on 3rd Q patrol
Note on AB163: Henderson, Michelle: work identified on 2022 3rd period patrol
Note on AC163: Henderson, Michelle: work identified on 2022 3rd period patrol
Note on AE163: Cox, Jeremy J: work identified on 3rd Q patrol
Note on AD165: Mohr, Jeremy W: work identified on 2023 patrol
Note on X166: Mohr, Jeremy W: additional signed reclamation completed
Note on AB167: Mohr, Jeremy W: priority work was moved to April due to available equipment
Note on AE167: Strauss, Anthony D: construction and priority work found on 2023 patrol
Note on AB168: Mohr, Jeremy W: priority work was moved to April due to available equipment
Note on AB169: Mohr, Jeremy W: work completed due to available equipment
Note on AB171: Mohr, Jeremy W: work completed due to resources in the area
Note on AC176: Strauss, Anthony D: work completed due to availability of crews
Note on AB178: Mohr, Jeremy W: work completed due to optumal ground conditions
Note on AC179: Part, Jesse: Non-priority work identified on 2022 patrol.
Note on AD179: Part, Jesse: 2/9/24 Non-priority work identified on 2022 patrol.
Note on AB180: Morrison, Jim B: Work was completed in the 1st quarter of 2023 based on ROW accessibility
Note on AB181: Morrison, Jim B: Work was moved to early 2nd quarter based on crew availability
Note on AB182: Morrison, Jim B: Non priority work identified on the 2022 patrol
Note on AB183: Morrison, Jim B: Work was moved up to 1st quarter 2023 based on crew availability
Note on AE184: Part, Jesse: 2/9/24 Non-priority work identified on 2023 patrol.
Note on AD185: Cox, Jeremy J: reclamation
Note on AE185: Cox, Jeremy J: reclamation
Note on AD187: Mohr, Jeremy W: tall brush mitigated while water was down
Note on X191: Morrison, Jim B: Reclamation, One mile was moved into the second quarter based on crew availability
Note on AC195: Henderson, Michelle: work identified on 2nd Q patrol
Note on AB196: Part, Jesse: Non-priority work identified on 2022 patrol.
Note on X202: Morrison, Jim B: Non priority reclamation work
Note on AD204: Strauss, Anthony D: priority work found on 2023 patrol
Note on AE204: Strauss, Anthony D: Priority work found on 2023 patrol
Note on AB205: Mohr, Jeremy W: additional work carrying over to the 3rd QRT
Note on AD205: Mohr, Jeremy W: work from Q1
Note on AB207: Part, Jesse: Non-priority work identified on 2022 patrol.
Note on AC210: Henderson, Michelle: work identified on 1st Q patrol
Note on AB211: Mohr, Jeremy W: work completed due to crews prioximity to work
Note on AB214: Morrison, Jim B: Non priority found on the 2023 patrol
Note on T221: Morrison, Jim B: Work was completed in support of a rebuild project
Note on AB222: Henderson, Michelle: non priority work identified on 2022 patrol
Note on AC222: Henderson, Michelle: non priority work
Note on AE222: Cox, Jeremy J: non priority work
Note on AB223: Henderson, Michelle: work identified on 2021 ground patrol
Note on AC223: Henderson, Michelle: work identified on 2nd Q patrol
Note on AC224: Part, Jesse: Work completed ISO SIRP South construction project.
Note on AD224: Part, Jesse: 2/9/24 Work completed ISO SIRP construction project
Note on AE224: Part, Jesse: 2/9/24 Non-priority work identified on 2023 patrol and construction access clearing.
Note on AB225: Mohr, Jeremy W: work moved to April due to customer
Note on AB226: Strauss, Anthony D: priority work found on 2022 patrol
Note on AC226: Strauss, Anthony D: work found on 2022 patrol
Note on AB227: Strauss, Anthony D: work moved to q1 due to availability of crews
Note on AC227: Strauss, Anthony D: work moved to q1 due to availability of crews
Note on X228: Strauss, Anthony D: veg rec work
Note on AC228: Strauss, Anthony D: priority work completed from 2022 patrol
Note on AC229: Strauss, Anthony D: veg rec
Note on AD229: Strauss, Anthony D: ongoing veg rec
Note on AE229: Strauss, Anthony D: ongoing veg rec
Note on X230: Mohr, Jeremy W: reclamation started early
Note on Z230: Mohr, Jeremy W: Last of reclamation completed
Note on AC230: Mohr, Jeremy W: trees removed working with the City of Princeton
Note on X232: Morrison, Jim B: Non priority reclamation work was completed
Note on AB232: Morrison, Jim B: Priority work was found on the 4th quarter patrol, Work was also completed in support of a rebuild project
Note on AB233: Henderson, Michelle: non priority reclamation work postponed due customer issues
Note on D235: Henderson, Michelle: Runs entirely in a corridor with Sidney-Rising 345kv
Note on AB236: Henderson, Michelle: non priority reclamation work postponed due to crew availability
Note on AB239: Strauss, Anthony D: Priority work identified on 2022 patrol
Note on AE241: Strauss, Anthony D: priority work found on 2023 patrol
Note on R242: Strauss, Anthony D: non priority work pushed to q3
Note on AD242: Strauss, Anthony D: priority work found on 2023 patrol
Note on AD243: Mohr, Jeremy W: work identified on 2023 patrol
Note on AC244: Mohr, Jeremy W: work identified on 2023 patrol
Note on AD245: Cox, Jeremy J: work identified on 2nd Q patrol
Note on AB249: Mohr, Jeremy W: mowing completed while equipment was in the area
Note on AD252: Part, Jesse: 2/9/24 Worked completed for construction project reroute.
Note on AE252: Part, Jesse: 2/9/24 Work completed for construction project reroute and non-priority work identified on the 2022 patrol.
Note on AB253: Part, Jesse: This is access work for construction, but project was deferred until Fall 2023. Moving this work to 3rd quarter.
Note on AD253: Part, Jesse: 2/9/24 Construction clearing work moved to 2024 because of landowner negotiation.
Note on AB255: Henderson, Michelle: work identified on 4th period 2022 ground patrol
Note on AC255: Henderson, Michelle: work identified on 4th Q 2022 patrol
Note on AD255: Cox, Jeremy J: work identified on 2nd Q patrol
Note on AE255: Cox, Jeremy J: non priority work
Note on AB256: Henderson, Michelle: work identified on 1st period ground patrol
Note on AC257: Henderson, Michelle: work identified on 2nd Q patrol
Note on AC258: Henderson, Michelle: helicopter debris cleanup
Note on AD258: Henderson, Michelle: helicopter debris cleanup
Note on AC259: Henderson, Michelle: work identified on 2nd Q patrol
Note on AC260: Strauss, Anthony D: work completed due to availability of crew
Note on AD261: Strauss, Anthony D: priority work found on 2023 patrol
Note on AE261: Strauss, Anthony D: priority work found on 2023 patrol
Note on AE262: Mohr, Jeremy W: work identified on 2023 patrol
Note on Q263: Strauss, Anthony D: non priority work moved to q3
Note on R263: Strauss, Anthony D: non priority work from q2
Note on AD263: Strauss, Anthony D: priority work found on 2023 patrol
Note on AE263: Strauss, Anthony D: priority work found on 2023 patrol
Note on AC265: Mohr, Jeremy W: permitted removals
Note on Q267: Strauss, Anthony D: non priority work delayed to q3
Note on R267: Strauss, Anthony D: work from q2
Note on AB268: Strauss, Anthony D: non priority work completed in area with limited access due to flooding.
Note on AE268: Strauss, Anthony D: priority work found on 2023 patrol
Note on V269: Part, Jesse: 2/9/24 Mowing maintenance (Intren)
Note on W269: Part, Jesse: 2/9/24 Mowing maintenance (Intren)
Note on AD269: Part, Jesse: 2/9/24 Non-priority work identified on 2023 patrol.
Note on AE269: Part, Jesse: 2/9/24 Non-priority work identified on 2023 patrol.
Note on AC270: Henderson, Michelle: work identified on patrol 1st Q 2023
Note on AC272: Mohr, Jeremy W: hazard tree mitigation
Note on AA273: Mohr, Jeremy W: Towerline to Interstate
Note on AE274: Mohr, Jeremy W: work identified on 2023 patrol
Note on AD277: Strauss, Anthony D: priority work found on 2023 patrol
Note on AE277: Strauss, Anthony D: Construction
Note on Q280: Strauss, Anthony D: non priority work moved to q3
Note on R280: Strauss, Anthony D: non priority work from q2
Note on AE280: Strauss, Anthony D: priority work found on 2023 patrol
Note on B282: Paries, Dieter E: Ameren Property
Note on B283: Paries, Dieter E: Ameren Property
Note on AB284: Henderson, Michelle: construction clean up
Note on AC284: Henderson, Michelle: work identified on 2nd Q patrol
Note on AC285: Henderson, Michelle: work identified on 2nd Q patrol
Note on J287: Part, Jesse: Brought helicopter back to trim line on capital after clearing.
Note on X287: Part, Jesse: Continued Reclamation.
Note on Z287: Part, Jesse: 2/9/24 Continued reclamation
Note on AA287: Part, Jesse: 2/9/24 Continued reclamation
Note on AC287: Part, Jesse: Assisted Intren on Veg Rec.
Note on AE288: Part, Jesse: 2/9/24 Non-priority work identified on 2023 patrol.
Note on AE289: Part, Jesse: 2/9/24 Non-priority work identified on 2023 patrol.
Note on AB290: Part, Jesse: Non-priority work identified on 2022 patrol.
Note on AC290: Part, Jesse: Non-priority work identified on 2022 patrol.
Note on AE290: Part, Jesse: 2/9/24 Non-priority work identified on 2023 patrol.
Note on AB291: Part, Jesse: Non-priority work identified on 2022 patrol.
Note on AE291: Part, Jesse: 2/9/24 Non-priority work identified on 2023 patrol.
Note on J292: Part, Jesse: Brought helicopter back to trim line post construction.
Note on AC292: Part, Jesse: Non-priority work identified on 2022 patrol, and work ISO SIRP South construction project.
Note on AD292: Part, Jesse: 2/9/24 Non-priority work identified on 2022 patrol and construction clearing.
Note on AE292: Part, Jesse: 2/9/24 Construction clearing ISO SIRP
Note on AE293: Part, Jesse: 2/9/24 Non-priority work identified on 2023 patrol.
Note on AB296: Mohr, Jeremy W: reos sub statioin clearing
Note on AC298: Henderson, Michelle: non-priority reclamation work postponed indefinitely due to upcoming LRTP construction on the affected properties
Note on AC299: Henderson, Michelle: work identified on 2nd Q patrol
Note on Q300: Strauss, Anthony D: some non priortiy work finished in q3
Note on R300: Strauss, Anthony D: non priority work left from q2
Note on AB300: Strauss, Anthony D: priority work found on 2022 patrol
Note on AC300: Strauss, Anthony D: priority work found on 2022 patrol
Note on AD300: Strauss, Anthony D: priority work found on 2023 patrol
Note on AE300: Strauss, Anthony D: priority work found on 2023 patrol
Note on AB301: Strauss, Anthony D: non priority work completed due to proximity of crews
Note on AD301: Strauss, Anthony D: priority work found on 2023 patrol
Note on AE301: Strauss, Anthony D: priority work found on 2023 patrol
Note on AD302: Strauss, Anthony D: Construction
Note on AB303: Strauss, Anthony D: non priority work completed due to proximity of crews.
Note on AC304: Strauss, Anthony D: work from 2022 patrol
Note on AE304: Strauss, Anthony D: Priority work found on 2023 patrol
Note on AC305: Mohr, Jeremy W: mow work completed on no spray customer while mower was in the area

## IL
IL - 2023 - Scheduled vs. Completed Work
Quarter | Scheduled Miles | Completed Miles | Percentage Completed
1 | 397 | 20 | 5.038%
2 | 1023 | 203.61 | 19.9%
3 | 642 | 257 | 40.03%
4 | 0 | 16 | #DIV/0!
Totals | 2062 | 496.61 | 24.08%

## Carry Over
Watseka - Goodland | non priority reclamation work has been postponed indefinitely. LRTP new construction is upcoming along the same route, and both lines may be moved.
Gilman - Watseka | non priority reclamation work has been postponed indefinitely. LRTP new construction is upcoming along the same route, and both lines may be moved.