## Sheet1
Quarter 1 2024 Project Tracking Appendix 1
COMPLETE |  |  |  | Complete and in-service
CLOSED OUT |  |  |  | In-service and all required project close-out documentation supplied by TO. Per BP 7060, Section 13, upgrades reported as closed out this quarter will not be included in subsequent reports.
DELAY - MITIGATION |  |  |  | Behind schedule, interim mitigation provided or project may change but time permits the implementation of project; asterisk (*) indicates interim mitigation plan provided by SPP
IDENTIFIED |  |  |  | Upgrade identified and included in Board approved study results
IN SERVICE |  |  |  | Upgrade is in service, but not all project activities are complete
NTC - COMMITMENT WINDOW |  |  |  | NTC/NTC-C issued, still within the 90 day written commitment to construct window and no commitment received
NTC-C PROJECT ESTIMATE WINDOW |  |  |  | Within the NTC-C Project Estimate (CPE) window
ON SCHEDULE < 4 |  |  |  | On Schedule within 4-year horizon
ON SCHEDULE > 4 |  |  |  | On Schedule beyond 4-year horizon
REEVALUATION |  |  |  | NTC/NTC-C active; pending re-evaluation
RFP RESPONSE WINDOW |  |  |  | RFP Issued
SUSPENDED |  |  |  | NTC/GIA suspended
NTC_ID | PID | UID | ProjectOwner | State(s) | Project Name | Upgrade Name | Project Type | Project Owner Indicated In-Service Date | RTO Determined Need Date | Letter of Notification to Construct Issue Date | Source Study | Baseline Cost Estimate | Baseline Cost Estimate Year | Baseline Cost Estimate with Escalation | Current Cost Estimate | Final Cost | Project Status | From Bus Number | From Bus Name | To Bus Number | To Bus Name | Project Description/ Comments | Voltages (kV) | Number of New | Number of Rebuild/Reconductor | Number of Voltage Conversion
200220 | 30375 | 50442 | NPPD | NE | Multi - Gentleman - Cherry Co. - Holt Co. 345 kV | Cherry Co. - Gentleman 345 kV Ckt 1 | Regional Reliability | 2026-12-31 | 2018-01-01 | 2013-03-11 | 2012 ITP10 | 204236579 | 2020 | 225438968.5097 | 204236579 |  | Delay - Mitigation | 640500 | Cherry County 345 kV | 640183 | Gerald Gentleman Station | Build new 110-mile 345 kV line from Gerald Gentleman Station substation to new Cherry County substation. This upgrade is contingent upon approval from Western Area Power Administration ("WAPA") to tap the Grand Island - Fort Thompson 345 kV line. | 345 | 100.7
200220 | 30375 | 50444 | NPPD | NE | Multi - Gentleman - Cherry Co. - Holt Co. 345 kV | Cherry Co. Substation 345 kV | Regional Reliability | 2026-12-31 | 2018-01-01 | 2013-03-11 | 2012 ITP10 | 13692681 | 2020 | 15114157.7865 | 13692681 |  | Delay - Mitigation | 640500 | Cherry County 345 kV |  |  | Build new Cherry County 345 kV substation and install necessary terminal equipment. This upgrade is contingent upon approval from WAPA to tap the Grand Island - Fort Thompson 345 kV line. | 345
200220 | 30375 | 50445 | NPPD | NE | Multi - Gentleman - Cherry Co. - Holt Co. 345 kV | Cherry Co. - Holt Co. 345 kV Ckt 1 | Regional Reliability | 2026-12-31 | 2018-01-01 | 2013-03-11 | 2012 ITP10 | 232903698 | 2020 | 257082103.9811 | 232903698 |  | Delay - Mitigation | 640500 | Cherry County 345 kV | 640503 | Holt County 345 kV | Build new 117-mile 345 kV line from new Cherry County substation to new Holt County substation. This upgrade is contingent upon approval from WAPA to tap the Grand Island - Fort Thompson 345 kV line. | 345 | 124.3
210618 | 30375 | 50446 | NPPD | NE | Multi - Gentleman - Cherry Co. - Holt Co. 345 kV | Holt Co. Substation 345 kV | Regional Reliability | 2026-12-31 | 2018-01-01 | 2021-11-04 | 2012 ITP10 | 577000 | 2021 | 621365.8877 | 577000 |  | Delay - Mitigation | 640503 | Holt County 345 kV |  |  | Add line bay terminal equipment as necessary to connect, commission and operate the 345 kV line from Thedford to Holt County Substation. | 345
200245 | 30563 | 50702 | WFEC | OK | Device - Sandy Corner 138 kV | Sandy Corner 138 kV Cap Bank | Regional Reliability | 2017-06-01 | 2017-06-01 | 2014-02-19 | 2014 ITPNT | 504000 | 2014 | 542752.8725 | 504000 |  | Re-evaluation | 520204 | Sandy Corner 138 kV |  |  | Add 20 Mvar of capacitance at Sandy Corner 138 kV. | 138
200397 | 242 | 10308 | WFEC | OK | Line - Elmore - Paoli 69 kV Rebuild | Elmore - Paoli 69 kV Ckt 1 Rebuild | Regional Reliability | 2018-01-20 | 2009-06-01 | 2016-05-17 | 2016 ITPNT | 3240000 | 2016 | 3404025 | 4339358 | 4171494.22 | Closed Out | 520898 | ELMORE | 521022 | PAOLI | Rebuild 10.8-mile 69 kV line from Elmore to Paoli. | 69 |  | 10.8
200397 | 844 | 11113 | WFEC | OK | Line - Sara Road - Sunshine Canyon 69 kV Ckt 1 Rebuild | Sara Road - Sunshine Canyon 69 kV Ckt 1 Rebuild | Regional Reliability | 2023-12-31 | 2020-06-01 | 2016-05-17 | 2016 ITPNT | 4725000 | 2016 | 5616540.1688 | 4725000 | 643783.96 | Delay - Mitigation | 521005 | MUSTANG | 521058 | SUNSHINE CANYON | Rebuild 10-mile 69 kV line from Sara Road to Sunshine Canyon. | 69 |  | 10
200397 | 31002 | 51445 | WFEC | OK | Line - Lincoln - Meeker 138 kV Ckt 1 New Line | Lincoln - Meeker 138 kV Ckt 1 New Line (WFEC) | Regional Reliability | 2020-06-26 | 2017-06-01 | 2016-05-17 | 2016 ITPNT | 6000000 | 2016 | 6622877.34 | 7710000 |  | Closed Out | 515442 | Lincoln 138kv | 520994 | MEEKER | Construct new 8.5-mile 138 kV line from Lincoln to Meeker. | 138
200397 | 31065 | 51484 | WFEC | OK | Sub - Cleo Junction 138 kV Terminal Upgrades | Cleo Junction 138 kV Terminal Upgrades | Regional Reliability | 2025-07-31 | 2017-06-01 | 2016-05-17 | 2016 ITPNT | 4000000 | 2016 | 4873611.6 | 4500000 |  | Delay - Mitigation | 520855 | CLEO JCT |  |  | Install 3-breaker ring bus at Cleo Junction to allow load to be moved from 69 kV to 138 kV. | 138
200390 | 31025 | 51487 | GRDA | OK | Sub - Sallisaw 161 kV Terminal Upgrades | Sallisaw 161 kV Terminal Upgrades | Regional Reliability | 2017-12-31 | 2017-06-01 | 2016-05-17 | 2016 ITPNT | 2266000 | 2016 | 2322650 | 2266000 |  | Re-evaluation | 505550 | Sallisaw |  |  | Install ring bus at Sallisaw 161 kV substation. | 161
200397 | 31041 | 51526 | WFEC | OK | Multi - Driftwood 138/69 kV Substation and Transformer | Driftwood 138 kV Substation | Regional Reliability | 2023-07-31 | 2017-06-01 | 2016-05-17 | 2016 ITPNT | 550000 | 2016 | 653777.1625 | 600000 |  | Delay - Mitigation | 520203 |  |  |  | Tap the 138 kV line from Byron to Cherokee City to construct new Driftwood substation. Install any required 138 kV terminal upgrades required to install 138/69 kV transformer. | 138
200397 | 31041 | 51527 | WFEC | OK | Multi - Driftwood 138/69 kV Substation and Transformer | Driftwood 138/69 kV Transformer | Regional Reliability | 2023-07-31 | 2017-06-01 | 2016-05-17 | 2016 ITPNT | 3000000 | 2016 | 3566057.25 | 3600000 |  | Delay - Mitigation |  |  | 520938 | HAZELTON JCT | Install new 138/69 kV transformer at new Driftwood substation. Install new 69 kV terminal for 69 kV line from Hazelton Junction. | 138/69
200419 | 31042 | 51531 | WFEC | OK | Multi - DeGrasse - Knob Hill 138 kV New Line and DeGrasse 345/138 kV Transformer | DeGrasse 138 kV Substation (WFEC) | Regional Reliability | 2027-12-31 | 2017-06-01 | 2016-12-27 | 2016 ITPNT | 1400000 | 2017 | 1664160.05 | 5700000 |  | Delay - Mitigation | 520999 | MOORELAND |  |  | Tap the existing 138 kV line from Mooreland to Rose Valley and terminate both end points into the new DeGrasse substation. WFEC and Oklahoma Gas and Electric Company shall decide who shall build how much of these Network Upgrades and shall provide such information, along with specific cost estimates for each DTO's portion of the Network Upgrades, to SPP in its response to this NTC. | 138 | 2
200386 | 31057 | 51560 | AEP | OK | Line - Atoka - Atoka Pump - Pittsburg - Savanna - Army Ammo - McAlester City 69 kV Ckt 1 Rebuild | Atoka - Atoka Pump - Pittsburg 69 kV Ckt 1 Rebuild | Zonal Reliability | 2022-11-20 | 2017-06-01 | 2016-05-17 | 2016 ITPNT | 21668581.75 | 2016 | 25128911.6762 | 20759228 |  | Delay - Mitigation | 510882 | ATOKA 69KV | 510885 | PITTSBURG 69KV | Rebuild 27.1-mile 69 kV line from Atoka to Atoka Pump to Pittsburg. | 69
200433 | 31144 | 51764 | WFEC | OK | Sub - Tupelo - Tupelo Tap 138 kV Terminal Upgrades | Tupelo 138 kV Terminal Upgrades | Economic | 2023-12-31 | 2020-01-01 | 2017-02-21 | 2017 ITP10 | 100000 | 2017 | 115969.342 | 410000 |  | Delay - Mitigation | 505600 | Tupelo | 521071 | TUPELO TAP | Upgrade any necessary terminal equipment at Tupelo to increase the rating of the 138 kV line between Tupelo substation and Tupelo Tap substation. | 138
200455 | 41198 | 61852 | SPS | TX | Sub - Texas County - Hitchland 115 kV bus | Texas County 115 kV Terminal Upgrades #1 | Regional Reliability | 2024-04-01 | 2018-06-01 | 2017-05-12 | 2017 ITPNT | 98639 | 2017 | 117250.7737 | 0 |  | Delay - Mitigation | 523090 | Texas County Interchange 115 kV | 523093 | Hitchland Interchange 115 kV | Upgrade terminal equipment on the Texas County - Hitchland 115 kV Ckt 1 at Texas County. | 115
200455 | 41198 | 61853 | SPS | TX | Sub - Texas County - Hitchland 115 kV bus | Texas County 115 kV Terminal Upgrades #2 | Regional Reliability | 2024-04-01 | 2018-06-01 | 2017-05-12 | 2017 ITPNT | 108430 | 2017 | 128889.1959 | 0 |  | Delay - Mitigation | 523090 | Texas County Interchange 115 kV | 523093 | Hitchland Interchange 115 kV | Upgrade terminal equipment on the Texas County - Hitchland 115 kV Ckt 2 at Texas County. | 115
210536 | 41199 | 71960 | SPS | TX | Line - Etter - Moore - 115 kV | Etter - Moore 115 kV Rebuild | Regional Reliability | 2021-10-21 | 2018-06-01 | 2019-10-29 | 2017 ITPNT | 9037903 | 2017 | 9976153.83 | 1367428 |  | Closed Out | 523308 | Moore County Interchange East Bus 115 kV | 523256 | Etter Rural Sub 115 kV | Rebuild 10.83-mile 115 kV line from Etter to Moore. | 115 | 10.25
210496 | 51316 | 72095 | SPS | TX | Carlisle - Murphy 115kV Terminal Upgrades | Carlisle - Murphy 115 kV Terminal Upgrades | Regional Reliability | 2022-03-11 | 2022-06-01 | 2018-08-17 | 2018 ITPNT | 232952 | 2018 | 257135.4204 | 0 |  | Complete | 526160 | Carlisle Interchange 115 kV | 526192 | Murphy Sub 115 kV | Replace terminal equipment on the Carlisle to Murphy (circuit V40) line and address any line clearance concerns to meet or exceed the conductor rating. | 115
210496 | 61346 | 92151 | SPS | TX | XFR - McDowell 230/115 kV Ckt 1 | McDowell Creek 230/115kV Substation | Regional Reliability | 2024-11-22 | 2019-06-01 | 2018-08-17 | 2018 ITPNT | 13626695 | 2021 | 14674460.0271 | 14950257 |  | Delay - Mitigation |  |  |  |  | Tap Moore-Potter 230kV and tap Exell-Fain 115kV and tie into a new substation at McDowell Creek. | 230 | 0.2
210496 | 61346 | 92152 | SPS | TX | XFR - McDowell 230/115 kV Ckt 1 | McDowell Creek 230/115kV Transformer | Regional Reliability | 2024-11-22 | 2019-06-01 | 2018-08-17 | 2018 ITPNT | 6531679 | 2021 | 7033903.848 | 8774789 |  | Delay - Mitigation |  |  |  |  | Install a 230/115 kV transformer at the McDowell Creek substation | 230/115
210623 | 81500 | 112360 | AEP | OK | Sub - Riverside Station 138 kV | Riverside Station 138 kV Breakers | Regional Reliability | 2026-05-01 | 2021-06-01 | 2021-11-05 | 2019 ITP | 41100000 | 2020 | 45366709.779 | 46270466 |  | Delay - Mitigation | 509783 | RIVERSIDE STATION 138KV |  |  | Replace 27 breakers at Riverside Station 138 kV with 90 kA breakers and expand substation as necessary to accommodate physically larger breakers | 138 | 1.56
210544 | 81501 | 112361 | AEP | OK | Sub - Southwestern Station 138 kV | Southwestern Station 138 kV Breakers | Regional Reliability | 2025-01-08 | 2021-06-01 | 2019-11-18 | 2019 ITP | 4421345 | 2020 | 4880337.6021 | 4194065 |  | Delay - Mitigation | 511477 | SOUTHWESTERN STATION 138KV |  |  | Replace 8 breakers at Southwestern Station 138 kV with 63 kA breakers | 138
210538 | 81505 | 112366 | NPPD | NE | Sub - Canaday 115 kV | Canaday 115 kV Breakers | Regional Reliability | 2020-02-01 | 2021-06-01 | 2019-11-18 | 2019 ITP | 2600000 | 2020 | 2600000 | 2555908 | 2555908 | Complete | 640103 | Canaday |  |  | Replace 5 breakers at Canaday 115 kV with 40 kA breakers | 115
210538 | 81506 | 112367 | NPPD | NE | Sub - Hastings 115 kV | Hastings 115 kV Breakers | Regional Reliability | 2021-01-01 | 2021-06-01 | 2019-11-18 | 2019 ITP | 550000 | 2020 | 563750 | 434289 | 434289 | Complete | 640215 | Hastings |  |  | Replace 2 breakers at Hastings 115 kV with 40 kA breakers | 115
210538 | 81507 | 112368 | NPPD | NE | Sub - Moore 13.8 kV Breaker | Moore 13.8 kV Breaker | Regional Reliability | 2022-08-01 | 2021-06-01 | 2019-11-18 | 2019 ITP | 510000 | 2020 | 535818.75 | 648464 | 648464 | Complete | 640280 | Moore |  |  | Replace 1 breaker at Moore 13.8 kV with 40 kA breakers | 138
210545 | 81513 | 112377 | WFEC | OK | Sub - Anadarko 138 kV | Anadarko 138 kV Breakers | Regional Reliability | 2027-08-01 | 2021-06-01 | 2019-11-18 | 2019 ITP | 828359 | 2020 | 914353.3417 | 838500 |  | Delay - Mitigation | 520814 | ANADARKO |  |  | Replace 3 breakers at Anadarko 138 kV with 63 kA breakers | 138
210545 | 81514 | 112378 | WFEC | OK | Sub - Washita 69 kV | Washita 69 kV Breaker | Regional Reliability | 2023-12-31 | 2021-06-01 | 2019-11-18 | 2019 ITP | 52400 | 2020 | 56429.0685 | 52400 |  | Delay - Mitigation Window | 521088 | WASHITA |  |  | Replace 1 breaker at Washita 69 kV with 40 kA | 69
210545 | 81515 | 112379 | WFEC | OK | Sub - Mooreland 138/69 kV Breakers | Mooreland 138 kV Breakers #2 | Regional Reliability | 2022-12-29 | 2021-06-01 | 2019-11-18 | 2019 ITP | 822500 | 2020 | 864139.0625 | 4100000 |  | Delay - Mitigation | 520999 | MOORELAND |  |  | Replace 12 breakers at Mooreland 138 kV with 40 kA breakers
210545 | 81515 | 112380 | WFEC | OK | Sub - Mooreland 138/69 kV Breakers | Mooreland 69 kV Breakers #2 | Regional Reliability | 2024-12-31 | 2021-06-01 | 2019-11-18 | 2019 ITP | 128300 | 2020 | 141619.1938 | 204000 |  | Delay - Mitigation | 520995 | MOORELAND |  |  | Replace 2 breakers at Mooreland 69 kV with 40 kA breakers
210605 | 81516 | 112383 | EKC | KS | Multi - Marshall County - Smittyville - Baileyville - South Seneca 115 kV | Multi-Marshall County - Baileyville - South Seneca 115 kV | Regional Reliability | 2022-06-01 | 2021-04-01 | 2021-03-02 | 2019 ITP | 9204123 | 2020 | 9670081.7269 | 14189053 | 14189052 | Complete | 533338 | SMITTYVILLE N.M. COOP 115 KV (NEMAHA MARSHALL R.E. | 533338 | SMITTYVILLE N.M. COOP 115 KV (NEMAHA MARSHALL R.E. | Tear down 7.99 miles of 115 kV line from Baileyville to Smittyville, 2.17 miles of 115 kV line from Marshall County to Smittyville, and the Smittyville substation, rebuild 10.16 miles of 115 kV line from Baileyville to Marshall County and upgrade any necessary terminal equipment at Marshall County and/or Baileyville to increase the summer emergency rating to 239 MVA | 115 | 2.2
210544 | 81520 | 112389 | AEP | OK | Line - Tulsa SE - S Hudson 138kV Ckt 1 | Tulsa SE - S Hudson 138kV Ckt 1 Rebuild | Regional Reliability | 2022-06-23 | 2021-06-01 | 2019-11-18 | 2019 ITP | 6724236.77 | 2020 | 7064651.2565 | 6724237 | 6451699 | Complete | 509811 | TULSA SOUTHEAST 138KV | 509833 | SOUTH HUDSON | Rebuild 1.97 miles of 138 kV line from Tulsa SE to S Hudson and upgrade any necessary terminal equipment at Tulsa SE and/or S Hudson to increase the summer emergency rating to 286 MVA | 138/138 | 2
210544 | 81523 | 112393 | AEP | OK | Line - Tulsa SE - 21st Street Tap 138kV Ckt 1 | Tulsa SE - 21st Street Tap 138 kV Ckt 1 | Regional Reliability | 2021-11-17 | 2021-06-01 | 2019-11-18 | 2019 ITP | 1307802 | 2020 | 1340497.05 | 1868658 |  | Complete | 509811 | TULSA SOUTHEAST 138KV | 509828 | 21st STREET TAP | Reconductor 1.48 miles of 138 kV from Tulsa SE to 21st Street Tap and upgrade any necessary terminal equipment at Tulsa SE and/or 21st Street Tap to increase the summer emergency rating to 345 MVA | 138/138 |  | 1.5
210545 | 81525 | 112395 | WFEC | OK | Device- Gypsum 69 kV Capacitor Bank | Gypsum 69 kV Capacitor Bank | Regional Reliability | 2025-11-28 | 2021-06-01 | 2019-11-18 | 2019 ITP | 400000 | 2020 | 441525.156 | 400000 |  | Delay - Mitigation | 520929 | GYPSUM |  |  | Install a new 12 MVAR capacitor bank at Gypsum 69 kV substation. | 69/69
210540 | 81532 | 112402 | OGE | OK | Sub - Cleo Corner - Cleo Junction 69kV | Cleo Corner - Cleo Junction 69kV Ckt 1 Terminal Upgrades | Regional Reliability | 2022-06-01 | 2022-06-01 | 2019-11-18 | 2019 ITP | 16602 | 2020 | 17442.4762 | 16602 |  | Complete | 514777 | CLEO CORNER 69 | 520855 | CLEO JCT | Upgrade any necessary terminal equipment at Cleo Corner and/or Cleo Junction to increase the summer emergency rating to 48 MVA | 69
210538 | 81533 | 112403 | NPPD | NE | Sub - Firth 115kV | Firth Cap Bank 115kV Ckt 1 | Regional Reliability | 2024-06-01 | 2021-04-01 | 2019-11-18 | 2019 ITP | 608900 | 2020 | 672111.6687 | 608900 |  | Delay - Mitigation | 640171 | Firth |  |  | Install new 15 MVAR capacitor bank at Firth 115 kV substation. | 115
210538 | 81533 | 112404 | NPPD | NE | Sub - Firth 115kV | Firth 115 kV Substation Expansion | Regional Reliability | 2024-06-01 | 2021-04-01 | 2019-11-18 | 2019 ITP | 3600000 | 2020 | 3973726.404 | 3036560 |  | Delay - Mitigation | 640171 | Firth |  |  | Expand the existing Firth 115 kV substation to accommodate a new 15 MVAR capacitor bank. | 115
210545 | 81550 | 112435 | WFEC | OK | Line - East Kingfisher - Kingfisher 138kV | East Kingfisher - Kingfisher 138 kV Rebuild | Economic | 2027-05-31 | 2021-01-01 | 2019-11-18 | 2019 ITP | 1000000 | 2020 | 1103812.89 | 1000000 |  | Delay - Mitigation |  |  |  |  | Rebuild 2.03 miles of 138 kV line from Kingfisher to East Kingfisher and upgrade any necessary terminal equipment at East Kingfisher and/or Kingfisher to increase the summer emergency rating to 286 MVA | 138
210543 | 81557 | 112451 | SEPC | KS | Multi - Setab - Scott City - Pile - Arnold - Ransom 115 kV | Arnold - Ransom 115kV Terminal Upgrades | Economic | 2024-02-28 | 2025-01-01 | 2019-11-18 | 2019 ITP | 462000 | 2020 | 509961.5552 | 1075000 |  | On Schedule < 4 | 531409 | ARNOLD | 531414 | RANSOM | Upgrade any necessary terminal equipment at Arnold and/or Ransom to increase the summer emergency rating to 165 MVA | 115
210543 | 81557 | 112452 | SEPC | KS | Multi - Setab - Scott City - Pile - Arnold - Ransom 115 kV | Pile - Scott City 115kV Terminal Upgrades | Economic | 2023-10-25 | 2025-01-01 | 2019-11-18 | 2019 ITP | 1633500 | 2020 | 1759100.8278 | 130000 |  | Complete | 531432 | PILE | 531433 | SCOTT CITY | Upgrade any necessary terminal equipment at Pile and/or Scott City to increase the summer emergency rating to 229 MVA | 115
210543 | 81557 | 112453 | SEPC | KS | Multi - Setab - Scott City - Pile - Arnold - Ransom 115 kV | Scott City - Setab 115kV Terminal Upgrades | Economic | 2023-10-11 | 2025-01-01 | 2019-11-18 | 2019 ITP | 1556500 | 2020 | 1676180.25 | 144495 |  | Complete | 531433 | SCOTT CITY | 531464 | SETAB | Upgrade any necessary terminal equipment at Scott City and/or Setab to increase the summer emergency rating to 230 MVA | 115
210593 | 81561 | 112458 | TSOK | OK | Multi - Sooner - Wekiwa 345 kV and Sand Springs - Sheffield 138 kV | Sooner - Wekiwa 345 kV New Line | Economic | 2026-01-01 | 2026-01-01 | 2021-02-10 | 2019 ITP | 97111851 | 2020 | 107193312.9056 | 104642958 |  | On Schedule < 4 | 509755 | WEKIWA 345KV | 514803 | SOONER 345 | Build a new 345kV line from Sooner to Wekiwa with a summer emergency rating of 1792 MVA | 345
210544 | 81561 | 112460 | AEP | OK | Multi - Sooner - Wekiwa 345 kV and Sand Springs - Sheffield 138 kV | Sand Springs - Sheffield Steel 138 kV Terminal Upgrades | Economic | 2026-02-26 | 2026-01-01 | 2019-11-18 | 2019 ITP | 733520 | 2020 | 809668.8311 | 1242638 |  | Delay - Mitigation Window | 509812 | SHEFFIELD | 509815 | Sand Springs 138 kV | Upgrade any necessary terminal equipment at Sand Springs and/or Sheffield Steel to increase the summer rating to 278 MVA | 138
210544 | 81571 | 112488 | AEP | OK | XFR - Pryor Junction 138/115 | Pryor Junction 138/115 kV Transformer | Regional Reliability | 2022-06-01 | 2021-06-01 | 2019-11-18 | 2019 ITP | 9155167 | 2020 | 9618647.3294 | 9155167 |  | Complete | 510407 | PRYOR JUNCTION 115KV | 510371 | Pryor Jct Tertiary # 1 | : Replace the existing 115/69 kV transformer with a new 138/115 kV transformer and upgrade any necessary terminal equipment at Pryor Junction to increase the summer emergency rating to 167 MVA | 138/115
210544 | 81561 | 112502 | AEP | OK | Multi - Sooner - Wekiwa 345 kV and Sand Springs - Sheffield 138 kV | Sooner - Wekiwa 345 kV Terminal Upgrades (AEP) | Economic | 2025-05-01 | 2026-01-01 | 2019-11-18 | 2019 ITP | 3165684 | 2019 | 3581680.8679 | 5329277 |  | On Schedule < 4 |  |  |  |  | Install terminal equipment at Wekiwa to support a 345 kV line from Sooner to Wekiwa rated at summer emergency of 1792 MVA | 345 | 0.06
210540 | 81561 | 112504 | OGE | OK | Multi - Sooner - Wekiwa 345 kV and Sand Springs - Sheffield 138 kV | Sooner - Wekiwa 345kV Terminal Upgrades (OGE) | Economic | 2025-10-01 | 2026-01-01 | 2019-11-18 | 2019 ITP | 4139615 | 2020 | 4569360.3966 | 3909824 |  | On Schedule < 4 |  |  |  |  | Install terminal equipment to support a 345kV line from Wekiwa to Sooner rated at summer emergency of 1792 MVA | 345
210592 | 81547 | 112509 | EKC | KS | Line - Wolf Creek - Blackberry 345 kV | Wolf Creek 345kV Terminal Equipment | Economic | 2025-01-01 | 2026-01-01 | 2021-01-21 | 2019 ITP | 11618029 | 2021 | 12511346.453 | 23518225 |  | On Schedule < 4 |  |  |  |  | Install terminal equipment at Wolf Creek to support 345kV line from Wolf Creek to Blackberry rated at 1792 MVA | 345
210626 | 81547 | 122598 | NEET | KS/MO | Line - Wolf Creek - Blackberry 345 kV | Blackberry - Wolf Creek 345 kV | Economic | 2025-01-01 | 2026-01-01 | 2021-12-03 | 2019 ITP | 85168938 | 2021 | 91717630.4476 | 87298154 |  | On Schedule < 4 |  |  |  |  | Build a new 345kV line from Wolf Creek to Blackberry with a summer emergency rating of 1792 MVA | 345
210586 | 81553 | 112443 | WFEC | OK | Line - Russett - South Brown 138 kV | Russett - South Brown 138 kV Ckt 1 Rebuild | Economic | 2027-12-01 | 2022-01-01 | 2020-11-17 | 2020 ITP | 10267390.81 | 2021 | 11056856.8552 | 10267390.81 |  | Delay - Mitigation | 505602 | Brown | 521044 | RUSSETT | Rebuild 18.62 miles of 138 kV line from Russett to South Brown and upgrade terminal equipment at South Brown as needed to achieve a summer emergency rating of 234 MVA | 138
210578 | 81675 | 122717 | GRDA | OK/ | Sub - GRDA1 345/161 kV Ckt 1 and Ckt 2 | GRDA1 345 kV Terminal Upgrades Transformer Ckt 1 | Economic | 2023-01-31 | 2022-01-01 | 2020-11-17 | 2020 ITP | 374400 | 2021 | 393354 | 374400 |  | Complete | 512650 | GRDA1 345 |  |  | Upgrade terminal equipment at GRDA1 345 kV Ckt 1 to achieve a summer emergency rating of 558 MVA | 345/345
210578 | 81675 | 122718 | GRDA | OK | Sub - GRDA1 345/161 kV Ckt 1 and Ckt 2 | GRDA1 161 kV Terminal Upgrades Transformer Ckt 1 | Economic | 2023-01-31 | 2022-01-01 | 2020-11-17 | 2020 ITP | 453000 | 2021 | 475933.125 | 453000 |  | Complete | 512650 | GRDA1 345 | 512650 | GRDA1 345 | Upgrade terminal equipment at GRDA1 161 kV Ckt 1 to achieve a summer emergency rating of 558 MVA | 345/161
210586 | 81679 | 122722 | WFEC | OK | Multi - Dover Switch - O'Keene and Aspen - Mooreland - Pic 138 kV | Dover Switch - O'Keene 138 kV Ckt 1 Terminal Upgrades | Economic | 2025-12-31 | 2022-01-01 | 2020-11-17 | 2020 ITP | 910000 | 2021 | 979970.4642 | 910000 |  | Delay - Mitigation | 520882 | DOVER SW | 521016 | OKEENE | Upgrade any necessary terminal equipment, increase clearances, and replace conductor to achieve a summer emergency rating of 136 MVA
210574 | 81682 | 122725 | SPS | TX | Line - Allen - Quaker 115kV | Allen - Quaker 115 kV Ckt 1 Rebuild | Regional Reliability |  | 2022-06-01 | 2020-11-17 | 2020 ITP | 2961075 | 2021 | 3188753.8926 | 2961075 |  | Re-evaluation | 526213 | Allen Sub 115 kV | 526243 | South Plains REC-Quaker 115 kV | Rebuild 3.6 miles 115 kV line from Allen to Quaker and upgrade any necessary terminal equipment to achieve a summer emergency rating of 300 MVA |  |  | 3.5
210574 | 81684 | 122727 | SPS | TX | Line - Allen - Lubbock South 115kV | Allen - Lubbock South 115 kV Ckt 1 Rebuild | Regional Reliability |  | 2022-06-01 | 2020-11-17 | 2020 ITP | 7350796 | 2021 | 7916003.2619 | 7350796 |  | Re-evaluation | 526213 | Allen Sub 115 kV | 526268 | Lubbock South Interchange 115 kV | Rebuild 5.98 miles of 115 kV line from Allen to Lubbock and upgrade any necessary terminal equipment to achieve a summer emergency rating of 300 MVA. |  |  | 6
210575 | 81687 | 122730 | AEP | LA | Line - South Shreveport - Wallace Lake 138 kV #2 | South Shreveport - Wallace Lake 138 kV Ckt 1 Rebuild #2 | Regional Reliability | 2025-03-20 | 2024-06-01 | 2020-11-17 | 2020 ITP | 23622577 | 2021 | 25438931.5915 | 20597910 |  | Delay - Mitigation | 507755 | SOUTH SHREVEPORT 138KV | 507765 | WALLACE LAKE 138KV | Rebuild 11.18 miles of 138 kV line from South Shreveport to Wallace Lake and upgrade any necessary terminal equipment to achieve a summer emergency to 347 MVA |  | 11.2
210581 | 81768 | 122745 | BEPC | ND | Multi - Watford City 230/115 kV | Watford City 230/115 kV Transformer Ckt 1 (KV1A) | Regional Reliability | 2024-06-30 | 2022-06-01 | 2020-11-17 | 2020 ITP | 3389739 | 2021 | 3650378.1333 | 3910285 |  | Delay - Mitigation |  |  |  |  | Replace the 230/115 kV transformer Ckt 1 at Watford City to achieve a summer emergency rating of 208 MVA | 230/115
210581 | 81768 | 122746 | BEPC | ND | Multi - Watford City 230/115 kV | Watford City 230/115 kV Transformer Ckt 2 (KV2A | Regional Reliability | 2024-06-30 | 2022-06-01 | 2020-11-17 | 2020 ITP | 173041 | 2021 | 186346.2298 | 173041 |  | Delay - Mitigation |  |  |  |  | Upgrade any necessary terminal equipment at Watford City for the 230/115 kV transformer Ckt 2 to achieve a summer emergency rating of 208 MVA | 230/115
210627 | 81717 | 122796 | AEP | OK | Multi - Border - Woodward 345 kV Tap | Chisholm Substation 345 kV Terminal Upgrades | Economic | 2024-05-24 | 2022-01-01 | 2021-11-05 | 2020 ITP | 6275764 | 2023 | 6432658.1 | 6275764 |  | Delay - Mitigation | 511553 | Elk City 345 kV |  |  | Install any necessary terminal equipment to support a new line 345 kV line from Border - Woodward 345 kV substation with a summer emergency rating of 1792 MVA |  | 0.2
210578 | 81675 | 122801 | GRDA | OK | Sub - GRDA1 345/161 kV Ckt 1 and Ckt 2 | GRDA1 345 kV Terminal Upgrades Transformer Ckt 2 | Economic | 2022-06-30 | 2022-01-01 | 2020-11-17 | 2020 ITP | 312000 | 2021 | 319800 | 312000 |  | Complete | 512650 | GRDA1 345 |  |  | Upgrade terminal equipment at GRDA1 345 kV Ckt 2 to achieve a summer emergency rating of 558 MVA
210578 | 81675 | 122802 | GRDA | OK | Sub - GRDA1 345/161 kV Ckt 1 and Ckt 2 | GRDA1 161 kV Terminal Upgrades Transformer Ckt 2 | Economic | 2022-06-30 | 2022-01-01 | 2020-11-17 | 2020 ITP | 453000 | 2021 | 464325 | 453000 |  | Complete | 512656 | GRDA1 161 |  |  | Upgrade terminal equipment at GRDA1 161 kV Ckt 2 to achieve a summer emergency rating of 558 MVA | 161/0
210583 | 81720 | 122804 | EM | KS | Sub - Northeast 161 kV | Northeast 161 kV Breakers | Regional Reliability | 2025-12-01 | 2022-06-01 | 2020-11-17 | 2020 ITP | 887479 | 2021 | 955717.8105 | 914927 |  | Delay - Mitigation |  |  |  |  | Replace three breakers at the Northeast 161 kV station with 63 kA breakers
210583 | 81722 | 122806 | EM | KS | Sub - Leeds 161 kV #2 | Leeds 161 kV Breaker | Regional Reliability | 2022-06-01 | 2022-06-01 | 2020-11-17 | 2020 ITP | 300000 | 2021 | 307500 | 260000 |  | In Service | 542997 | LEEDS 161 KV |  |  | Replace 1 breaker at the Leeds 161 kV station with a 40 kA breaker
210589 | 81733 | 122818 | OGE | OK// | Line - Cushing Tap - Shell Cushing Tap - Pipeline | Cushing - Shell Pipeline Cushing Tap 69 kV Ckt 1 Rebuild | Regional Reliability | 2024-10-01 | 2023-06-01 | 2020-11-17 | 2020 ITP | 4281150 | 2021 | 4610330.2778 | 6366645 |  | Delay - Mitigation Window | 515032 | CUSHING 69 | 515022 | PIPELINE 69 | Rebuild 4.71 miles of 69 kV line from Cushing to Shell Pipeline Cushing Tap and upgrade any necessary terminal equipment to achieve a summer emergency rating of 72 MVA
210589 | 81733 | 122819 | OGE | OK/ | Line - Cushing Tap - Shell Cushing Tap - Pipeline | Pipeline - Shell Pipeline Cushing Tap 69 kV Ckt 1 Rebuild | Regional Reliability | 2024-10-01 | 2023-06-01 | 2020-11-17 | 2020 ITP | 1081649 | 2021 | 1164817.6622 | 1081649 |  | Delay - Mitigation Window | 515022 | PIPELINE 69 |  |  | Rebuild 1.19 miles of 69 kV line from Pipeline to Shell Pipeline Cushing Tap and upgrade any necessary terminal equipment to achieve a summer emergency rating of 72 MVA
210628 | 81717 | 122823 | OGE | OK | Multi - Border - Woodward 345 kV Tap | Border - Woodward Tap 345 kV Substation | Economic | 2025-03-31 | 2022-01-01 | 2021-11-05 | 2020 ITP | 23239179 | 2023 | 23820158.475 | 23239179 |  | Delay - Mitigation |  |  |  |  | Tap the existing Border to Woodward 345 kV line 19 miles from the Border station and build a new 345 kV substation or switching station
210616 | 81741 | 122848 | OGE | OK | Multi - Minco - Pleasant Valley - Draper 345 kV | Minco 345 kV Terminal Equipment | Economic | 2025-01-01 | 2025-01-01 | 2021-06-04 | 2020 ITP | 1843729 | 2021 | 1985494.4659 | 5170350 |  | On Schedule < 4 | 514801 | Minco 345 kv |  |  | Install terminal equipment at Minco substation 345 kV to support a new 345 kV line from Minco with a summer emergency rating of 1792 MVA | 345
210616 | 81741 | 122849 | OGE | OK | Multi - Minco - Pleasant Valley - Draper 345 kV | Pleasant Valley 345/138 kV Substation (345 kV) | Economic | 2025-01-01 | 2025-01-01 | 2021-06-04 | 2020 ITP | 30707951 | 2021 | 33069104.3913 | 32342389 |  | On Schedule < 4 |  |  |  |  | Expand the existing Pleasant Valley 138 kV substation to 345 kV with new terminals to accommodate new line from Minco to Pleasant Valley to Draper and terminals to accommodate cut in of existing Cimarron to Draper 345 kV line. Tie into existing Cimarron to Draper 345 kV line. This description is specific to the 345 kV components. | 345
210616 | 81741 | 122850 | OGE | OK | Multi - Minco - Pleasant Valley - Draper 345 kV | Pleasant Valley 345/138 kV Transformer Ckt 1 | Economic | 2025-01-01 | 2025-01-01 | 2021-06-04 | 2020 ITP | 5003830 | 2021 | 5388577.5911 | 4536741 |  | On Schedule < 4 |  |  | 514929 | PLEASANT VALLEY 138 | Install a new 345/138 kV transformer to achieve a summer emergency rating of 478 MVA | 345/138
210616 | 81741 | 122851 | OGE | OK | Multi - Minco - Pleasant Valley - Draper 345 kV | Pleasant Valley 345/138 kV Transformer Ckt 2 | Economic | 2025-01-01 | 2025-01-01 | 2021-06-04 | 2020 ITP | 4885649 | 2021 | 5261309.5807 | 4536741 |  | On Schedule < 4 |  |  | 514929 | PLEASANT VALLEY 138 | Install a new 345/138 kV transformer to achieve a summer emergency rating of 478 MVA | 345/138
210616 | 81741 | 122858 | OGE | OK | Multi - Minco - Pleasant Valley - Draper 345 kV | Cimarron - Draper 345 kV Terminal Upgrades #2 | Economic | 2025-01-01 | 2025-01-01 | 2021-06-04 | 2020 ITP | 2541200 | 2021 | 2736594.4435 | 647852 |  | On Schedule < 4 | 514901 | CIMARRON 345 | 514934 | DRAPER LAKE 345 | Upgrade any necessary terminal equipment on the Cimarron to Draper 345 kV line to achieve a summer emergency rating of 1540 MVA
210586 | 81751 | 122864 | WFEC | OK | Sub - Anadarko 138 kV #2 | Anadarko 138 kV Breakers #2 | Regional Reliability | 2027-05-31 | 2022-06-01 | 2020-11-17 | 2020 ITP | 850000 | 2021 | 915357.027 | 850000 |  | Delay - Mitigation Window | 520814 | ANADARKO |  |  | Replace 4 breakers at the Anadarko 138 kV station with a 63 kA breakers
210586 | 81679 | 122865 | WFEC | OK | Multi - Dover Switch - O'Keene and Aspen - Mooreland - Pic 138 kV | Mooreland - Aspen 138 kV Terminal Upgrades | Economic | 2023-02-23 | 2022-01-01 | 2020-11-17 | 2020 ITP | 202500 | 2021 | 212751.5625 | 202500 |  | Complete | 520999 | MOORELAND |  |  | Upgrade any necessary terminal equipment at Mooreland 138 kV for the Aspen to Mooreland 138 kV line to achieve a summer emergency rating of 187 MVA rating
210586 | 81679 | 122866 | WFEC | OK | Multi - Dover Switch - O'Keene and Aspen - Mooreland - Pic 138 kV | Mooreland - Pic 138 kV Terminal Upgrades | Economic | 2023-02-23 | 2022-01-01 | 2020-11-17 | 2020 ITP | 405000 | 2021 | 425503.125 | 405000 |  | Complete | 520999 | MOORELAND |  |  | Upgrade any necessary terminal equipment at Mooreland 138 kV for the Mooreland to Pic 138 kV line to achieve a summer emergency rating of 187 MVA rating
210574 | 81755 | 122869 | SPS | TX// | Sub - Bushland - Deaf Smith 230 kV | Bushland - Deaf Smith 230 kV Terminal Upgrades | Regional Reliability | 2022-12-15 | 2022-04-01 | 2020-11-17 | 2020 ITP | 998956 | 2021 | 1023929.9 | 367342 |  | Complete | 524267 | Bushland Interchange 230 kV (POI: Wildorado Wind, 160MW) | 524623 | Deaf Smith County Interchange 230 kV | Increase clearances and upgrade any necessary terminal equipment at Bushland and/or Deaf Smith 230 kV to achieve a summer emergency rating of 546 MVA. |  | 33
210574 | 81757 | 122871 | SPS | TX/ | Sub - Deaf Smith #6 - Friona 115 kV | Deaf Smith #6 - Friona 115 kV Rebuild | Regional Reliability | 2025-12-15 | 2022-04-01 | 2020-11-17 | 2020 ITP | 11609949 | 2021 | 12502645.1768 | 13836016 |  | Delay - Mitigation | 524629 | Deaf Smith REC-#6 115 kV | 524655 | Friona Sub 115 kV | Rebuild 18.9 miles of 115 kV line from Deaf Smith #6 to Friona and upgrade any necessary terminal equipment at Deaf Smith #6 and/or Friona to achieve a summer emergency rating of 120 MVA |  | 17.4
210574 | 81758 | 122872 | SPS | TX | Line - Carlisle - Murphy 115 kV #2 | Carlisle - Murphy 115 kV Ckt 1 Rebuild | Regional Reliability | 2022-06-01 | 2022-06-01 | 2020-11-17 | 2020 ITP | 4160581 | 2021 | 4264595.525 | 4160581 |  | Re-evaluation | 526160 | Carlisle Interchange 115 kV | 526192 | Murphy Sub 115 kV | Rebuild 4.0 miles of 115 kV line from Carlisle to Murphy and upgrade any necessary terminal equipment to achieve a summer emergency rating of 240 MVA |  |  | 4
210574 | 81760 | 122876 | SPS | TX | Line - Deaf Smith #6 - Hereford 115 kV | Deaf Smith #6 - Hereford 115 kV Ckt 1 Rebuild | Regional Reliability | 2025-12-15 | 2022-04-01 | 2020-11-17 | 2020 ITP | 6956586 | 2021 | 7491482.2106 | 6583793 |  | Delay - Mitigation | 524629 | Deaf Smith REC-#6 115 kV | 524606 | Hereford Interchange 115 kV | Rebuild 2.33 miles of 115 kV line from Deaf Smith #6 to Hereford and upgrade any necessary terminal equipment to achieve a summer emergency rating of 239 MVA |  | 7.3
210574 | 81763 | 122883 | SPS | TX | Sub - Lubbock South - Wolfforth 230 kV | Lubbock South - Wolfforth 230 kV Ckt 1 Terminal Upgrades #2 | Regional Reliability | 2022-06-01 | 2022-06-01 | 2020-11-17 | 2020 ITP | 944000 | 2021 | 967600 | 1037244 |  | Complete | 526269 | Lubbock South Interchange 230 kV | 526525 | Wolfforth Interchange 230 kV | Increase clearances and upgrade any necessary terminal equipment at Lubbock South and/or Wolfforth to achieve a summer emergency rating of 550 MVA |  | 14.6
210584 | 81497 | 132893 | NWE | SD | Multi - Aberdeen Junction - Richmond 115 kV | Aberdeen Junction 115 kV Terminal Upgrades | Regional Reliability | 2021-12-31 | 2022-12-01 | 2020-11-17 | 2020 ITP | 1182000 | 2021 | 1182000 | 1182000 | 989393 | Complete |  |  |  |  | Install any necessary terminal equipment to support a new 115 kV line from Richmond to achieve a summer emergency rating of 139 MVA
210670 | 81741 | 133085 | NEET | OK | Multi - Minco - Pleasant Valley - Draper 345 kV | Minco - Pleasant Valley 345 kV Ckt 1 | Economic | 2024-07-01 | 2025-01-01 | 2022-04-28 | 2020 ITP | 38537430 | 2022 | 40488387.3937 | 38537430 |  | On Schedule < 4 |  |  |  |  | Build 34.8 miles of 345 kV line from Minco to Pleasant Valley 345 kV to achieve a 1792 MVA summer emergency rating.
210670 | 81741 | 133106 | NEET | OK | Multi - Minco - Pleasant Valley - Draper 345 kV | Draper - Pleasant Valley 345 kV Ckt 2 | Economic | 2024-07-01 | 2025-01-01 | 2022-04-28 | 2020 ITP | 16516041 | 2022 | 17352165.5756 | 16516041 |  | On Schedule < 4 |  |  |  |  | Build a second 13.2-mile 345 kV line from Draper 345 kV substation to Pleasant Valley 345 kV substation with a summer emergency rating of 1792 MVA
210576 | 91875 | 143156 | AEP | OK | Device - Grady 138 kV | Grady 138 kV Capacitor Bank | Zonal Reliability | 2022-12-13 | 2022-12-01 | 2020-11-17 | 2020 ITP | 1184404 | 2021 | 1214014.1 | 1910669 | 1460414 | Complete |  |  |  |  | Install a new 23 MVAR capacitor bank at Grady 138 kV
210579 | 91876 | 143157 | WAPA | ND/ | Device - Bismarck 12.47 kV | Bismarck 12.47 kV Reactors | Regional Reliability | 2023-11-30 | 2022-04-01 | 2020-11-23 | 2020 ITP | 2143217 | 2021 | 2251717.3606 | 4309263 |  | Complete |  |  |  |  | Install 2x35 MVAR reactors at Bismarck to control voltage on the 230 kV transmission system
210585 | 91878 | 143159 | MRES | MN | Device - Moorehead 230 kV | Moorehead 230 kV Reactor | Regional Reliability | 2024-12-31 | 2022-04-01 | 2020-11-17 | 2020 ITP | 4358300 | 2022 | 4578938.9375 | 6499045.72 |  | Delay - Mitigation |  |  |  |  | Install 2x40 MVAR reactors at Moorehead to control voltage on the 115 kV and 230 kV transmission systems
210574 | 91884 | 143167 | SPS | TX | Line - Cargill - Friona 115 kV | Cargill - Friona 115 kV Ckt 1 Rebuild | Regional Reliability | 2025-12-15 | 2022-04-01 | 2020-11-17 | 2020 ITP | 1675731 | 2021 | 1804578.9955 | 1301898 |  | Delay - Mitigation |  |  |  |  | Rebuild 1.15 miles of existing 115 kV line from Cargill to Friona and upgrade any necessary terminal equipment to achieve a summer emergency rating of 240 MVA
210616 | 81741 | 143176 | OGE | OK | Multi - Minco - Pleasant Valley - Draper 345 kV | Draper 345 kV Terminal Equipment | Economic | 2025-01-01 | 2025-01-01 | 2021-06-04 | 2020 ITP | 6484533 | 2021 | 6983132.7628 | 7099303 |  | On Schedule < 4 |  |  |  |  | Install a new line terminal at Draper 345 kV to accommodate new 345 kV line from Pleasant Valley.
210584 | 81497 | 143181 | NWE | SD | Multi - Aberdeen Junction - Richmond 115 kV | Aberdeen Jct - Richmond 115 kV Ckt 1 (NWE) | Regional Reliability | 2021-12-31 | 2022-12-01 | 2020-11-17 | 2020 ITP | 3277500 | 2021 | 3277500 | 3277500 |  | Delay - Mitigation Window |  |  |  |  | Build a new 13.5 mile 115 kV line from Aberdeen Junction to Richmond to achieve a summer emergency rating of 139 MVA |  | 14.4
210627 | 81717 | 143182 | AEP | OK// | Multi - Border - Woodward 345 kV Tap | Chisholm - Woodward - Border 345 kV Ckt 1 (AEP) | Economic | 2024-05-24 | 2022-01-01 | 2021-11-05 | 2020 ITP | 9059992 | 2023 | 9286491.8 | 9059992 |  | Delay - Mitigation |  |  |  |  | Build 0.84-miles of new 345 kV line from a new tap on the Woodward to Border 345 kV line to Chisholm with a summer emergency rating of 1792 MVA. Oklahoma Gas and Electric Co. and American Electric Power shall decide who shall build how much of these Network Upgrades and shall provide such information, along with specific cost estimates for each DTO's portion of the Network Upgrades, to SPP in its response to this NTC | 345 | 1
210616 | 81741 | 143257 | OGE | OK/ | Multi - Minco - Pleasant Valley - Draper 345 kV | Pleasant Valley 345/138 kV Substation (138 kV) | Economic | 2025-01-01 | 2025-01-01 | 2021-06-04 | 2020 ITP | 10112621 | 2021 | 10890186.6985 | 28449977 |  | On Schedule < 4 |  |  |  |  | Expand the existing Pleasant Valley 138 kV substation to 345 kV with new terminals to accommodate new line from Minco to Pleasant Valley to Draper. This description is specific to the 138 kV components.
210642 | 81529 | 112399 | SPS | TX | Sub - Lubbock South - Jones 230 kV Ckt 1 & 2 Terminal Upgrades | Lubbock South - Jones 230 kV Ckt 1 Terminal Upgrades | Regional Reliability | 2023-10-13 | 2023-06-01 | 2022-03-11 | 2021 ITP | 231742 | 2022 | 237535.55 | 200833 |  | Delay - Mitigation | 526269 | Lubbock South Interchange 230 kV | 526337 | Jones Station Bus#1 230 kV | Increase clearances and upgrade any necessary terminal equipment at Jones and/or Lubbock South 230 kV station | 230
210642 | 81529 | 112401 | SPS | TX | Sub - Lubbock South - Jones 230 kV Ckt 1 & 2 Terminal Upgrades | Lubbock South - Jones 230kV Ckt 2 Terminal Upgrades | Regional Reliability |  | 2023-06-01 | 2022-03-11 | 2021 ITP | 397668 | 2022 | 417799.9425 | 0 |  | In Service | 526269 | Lubbock South Interchange 230 kV | 526337 | Jones Station Bus#1 230 kV | Increase clearances and upgrade any necessary terminal equipment at Jones and/or Lubbock South 230 kV station | 230
210648 | 81691 | 122734 | WAPA | SD | Line - Oahe - Sully Buttes - Whitlock - Glenham 230 kV | Oahe 230 kV Terminal Upgrades (WAPA) | Economic | 2025-01-01 | 2025-01-01 | 2022-03-11 | 2021 ITP | 561800 | 2022 | 590241.125 | 561800 |  | On Schedule < 4 |  |  |  |  | Upgrade terminal equipment at Oahe 230 kV for the Oahe to Sully Buttes 230 kV line. Re-conductor three spans of line between Oahe 230 kV substation and Sully Buttes 230 kV substation..
210639 | 81691 | 122735 | EREC | SD | Line - Oahe - Sully Buttes - Whitlock - Glenham 230 kV | Sully Buttes 230 kV Terminal Upgrades | Economic |  | 2025-01-01 | 2022-03-11 | 2021 ITP | 587000 | 2022 | 616716.875 | 627400 |  | In Service |  |  |  |  | Upgrade terminal equipment at Sully Buttes for Oahe - Sully Buttes - Whitlock 230 kV line
210645 | 81694 | 122739 | NPPD | NE | XFR - Columbus 230/115 | Columbus East 230/115 kV transformer | Economic | 2025-06-01 | 2023-01-01 | 2022-03-09 | 2021 ITP | 5080000 | 2022 | 5337175 | 9278651 |  | Delay - Mitigation | 640127 | Columbus East | 640126 | Columbus East | Replace the 230/115 kV transformer and any necessary terminal equipment at Columbus East. | 230/115
210645 | 81769 | 122741 | NPPD | NE | Line - Scottsbluff - Victory Hill 115 kV Ckt 2 | Scottsbluff - Victory Hill 115kV Ckt 2 | Economic | 2025-06-01 | 2023-01-01 | 2022-03-09 | 2021 ITP | 7760000 | 2022 | 8152850 | 13952932 |  | Delay - Mitigation | 640338 | Scottsbluff | 640397 | Victory Hill | Build second 9 mile 115 kV line from Scottsbluff to Victory Hill.
210656 | 81741 | 122863 | OGE | OK | Multi - Minco - Pleasant Valley - Draper 345 kV | Midwest 138 kV Ckt 1 Terminal Upgrades | Economic | 2022-02-11 | 2025-01-01 | 2022-03-11 | 2021 ITP | 65000 | 2021 | 66625 | 81162.56 | 81162.56 | Complete | 514946 | MIDWEST TAP 138 |  |  | Upgrade any necessary terminal equipment at Midwest 138 kV on the Midwest to Franklin 138 kV line to achieve a summer emergency rating of 308 MVA
210655 | 92112 | 143587 | EM | KS | Sub - Platte City 161 kV | Platte City 161 kV Terminal Upgrade | Regional Reliability | 2022-12-19 | 2023-06-01 | 2022-03-09 | 2021 ITP | 55271.78 | 2022 | 55271.78 | 71643 | 71643 | Complete |  |  |  |  | Upgrade the switch at Platte City 161 kV for the Platte City - Weston 161 kV line. | 161
220720 | 92113 | 143588 | BEPC | ND | Line - Kummer Ridge - Round Up 345 kV | Kummer Ridge - Round Up 345 kV | Regional Reliability | 2025-04-01 | 2023-01-01 | 2023-03-16 | 2021 ITP | 78293357 | 2022 | 82256958.1981 | 81266669 |  | Delay - Mitigation |  |  |  |  | Build 33.2 mile new 345 kV line from Kummer Ridge to Round Up | 345
220720 | 92113 | 143589 | BEPC | ND | Line - Kummer Ridge - Round Up 345 kV | Kummer Ridge 345 kV Terminal Upgrades | Regional Reliability | 2025-04-01 | 2023-01-01 | 2023-03-16 | 2021 ITP | 342000 | 2022 | 359313.75 | 342000 |  | Delay - Mitigation |  |  |  |  | Install terminal equipment at Kummer Ridge substation 345 kV to support a new 345 kV line from Round Up | 345
220720 | 92113 | 143590 | BEPC | ND | Line - Kummer Ridge - Round Up 345 kV | Round Up 345 kV Terminal Upgrades | Regional Reliability | 2025-04-01 | 2023-01-01 | 2023-03-16 | 2021 ITP | 342000 | 2022 | 359313.75 | 342000 |  | Delay - Mitigation |  |  |  |  | Install terminal equipment at Round Up substation 345 kV to support a new 345 kV line from Kummer Ridge | 345
210633 | 92114 | 143591 | AEP | OK | Line- Catoosa - Blue Circle 69 kV | Blue Circle - Catoosa 69 kV Ckt 1 Rebuild | Regional Reliability | 2025-03-26 | 2023-06-01 | 2022-03-09 | 2021 ITP | 9020000 | 2022 | 9476637.5 | 9020000 |  | Delay - Mitigation |  |  |  |  | Rebuild 3.5 miles of 69 kV line from Catoosa to Blue Circle and upgrade any necessary terminal equipment at Catoosa and/or Blue Circle | 69
210645 | 81769 | 143599 | NPPD | NE | Line - Scottsbluff - Victory Hill 115 kV Ckt 2 | Scottsbluff 115 kV Ckt 2 Terminal Upgrades | Economic | 2025-06-01 | 2023-01-01 | 2022-03-09 | 2021 ITP | 1194000 | 2022 | 1254446.25 | 1194000 |  | Delay - Mitigation |  |  |  |  | Install terminal equipment at Scottsbluff 115 kV to support a second 115 kV line from Victory Hill. | 115
210645 | 81769 | 143600 | NPPD | NE | Line - Scottsbluff - Victory Hill 115 kV Ckt 2 | Victory Hill 115 kV Ckt 2 Terminal Upgrades | Economic | 2025-06-01 | 2023-01-01 | 2022-03-09 | 2021 ITP | 1129000 | 2022 | 1186155.625 | 1129000 |  | Delay - Mitigation |  |  |  |  | Install terminal equipment at Victory Hill 115 kV to support a second 115 kV line from Scottsbluff with a summer emergency rating of 264 MVA | 115
210648 | 81691 | 143613 | WAPA | SD | Line - Oahe - Sully Buttes - Whitlock - Glenham 230 kV | Sully Buttes - Whitlock 230 kV Line Clearance Increase | Economic | 2025-01-01 | 2025-01-01 | 2022-03-11 | 2021 ITP | 1744800 | 2022 | 1833130.5 | 562397 |  | On Schedule < 4 |  |  |  |  | Increase ground clearance of the Sully Buttes to Whitlock 230 kV line. | 230
210648 | 81691 | 143614 | WAPA | SD | Line - Oahe - Sully Buttes - Whitlock - Glenham 230 kV | Whitlock - Glenham 230 kV Clearance Increase | Economic | 2025-01-01 | 2025-01-01 | 2022-03-11 | 2021 ITP | 5845900 | 2022 | 6141848.6875 | 2734578 |  | On Schedule < 4 |  |  |  |  | Increase ground clearance of the Whitlock - Glenham 230 kV. | 230
210680 | 92123 | 143660 | OPPD | NE | Line - S3454 - S3740 345 kV | S3454 - S3740 345 kV New Line | Regional Reliability | 2026-12-31 | 2024-06-01 | 2022-07-19 | 2021 ITP | 64071687 | 2022 | 67315316.1544 | 64071687 |  | Delay - Mitigation Window |  |  |  |  | Build an approximately 29 mile 345 kV line from S3454 to S3740 Ckt 1. | 345
210680 | 92123 | 143661 | OPPD | NE/ | Line - S3454 - S3740 345 kV | S3454 345 kV Terminal Upgrades | Regional Reliability | 2026-12-31 | 2024-06-01 | 2022-07-19 | 2021 ITP | 2070042 | 2022 | 2174837.8763 | 2070042 |  | Delay - Mitigation Window |  |  |  |  | Install terminal equipment at S3454 substation 345 kV to support a new 345 kV line from S3454 to S3740. | 345
210680 | 92123 | 143662 | OPPD | NE/ | Line - S3454 - S3740 345 kV | S3740 345 kV Terminal Upgrades | Regional Reliability | 2026-12-31 | 2024-06-01 | 2022-07-19 | 2021 ITP | 1786830 | 2022 | 1877288.2688 | 1786830 |  | Delay - Mitigation Window |  |  |  |  | Install terminal equipment at S3740 substation 345 kV to support a new 345 kV line from S3454 to S3740. | 345
210637 | 92140 | 143663 | EKC | KS/ | Sub - Jarbalo Junction 115 kV Breaker Upgrade | Jarbalo Junction 115 kV Breaker | Regional Reliability | 2023-02-10 | 2023-06-01 | 2022-03-09 | 2021 ITP | 236539 | 2022 | 242452.475 | 195694 | 195694 | Complete |  |  |  |  | Replace breaker 115-483 at the Jarbalo Junction substation | 115
210647 | 92144 | 143664 | EM | KS | Sub - Shawnee Mission 161 kV Breaker | Shawnee Mission 161 kV | Regional Reliability | 2023-09-30 | 2023-06-01 | 2022-03-09 | 2021 ITP | 255075 | 2022 | 261451.875 | 864676 |  | Delay - Mitigation Window |  |  |  |  | Upgrade the R3-7 breaker at the Shawnee Mission 161 kV substation | 161
210647 | 92144 | 143665 | EM | KS | Sub - Shawnee Mission 161 kV Breaker | Shawnee Mission 161 kV Breaker | Regional Reliability |  | 2023-06-01 | 2022-03-09 | 2021 ITP | 255075 | 2022 | 267988.1719 | 0 |  | In Service |  |  |  |  | Upgrade the R7-12 breaker at the Shawnee Mission 161 kV substation | 161
210647 | 92141 | 143666 | EM | KS | Sub - Craig 161 kV Breaker | Craig 161 kV Breaker #2 | Regional Reliability | 2023-05-01 | 2023-06-01 | 2022-03-09 | 2021 ITP | 319002 | 2022 | 326977.05 | 267642.71 |  | Complete | 542978 | CRAIG 161 KV |  |  | Upgrade the R5-33 breaker at the Craig 161 kV substation | 161
210640 | 92142 | 143667 | MRES | MN | Sub - Moorhead 230 kV Substation Reconfiguration | Moorhead 230 kV Substation Reconfiguration | Regional Reliability | 2024-12-31 | 2023-06-01 | 2022-03-11 | 2021 ITP | 9989000 | 2022 | 10494693.125 | 15232591.82 |  | Delay - Mitigation |  |  |  |  | Reconfigure the Moorhead 230 kV substation with a ring bus, expandable to breaker-and-a-half. | 230
210675 | 92168 | 143714 | BEPC | ND | Multi - Tande - Finstad - Leland Olds 345 kV | Finstad - Tande 345 kV New Line | Regional Reliability | 2026-11-30 | 2023-01-01 | 2022-07-12 | 2021 ITP | 67411405 | 2022 | 70824107.3781 | 67411405 |  | Delay - Mitigation |  |  |  |  | Build a 48 mile 345 kV line from Finstad to Tande.
210656 | 92184 | 143786 | OGE | OK | Sub - Cleo Corner 69 kV & Cleo Junction 69 kV | Cleo Corner 69 kV Terminal Upgrades | Economic | 2023-03-01 | 2023-01-01 | 2022-03-11 | 2021 ITP | 168228 | 2022 | 172433.7 | 168228 |  | In Service |  |  |  |  | Upgrade any necessary terminal equipment at the Cleo Corner 69 kV substation | 69
210656 | 92190 | 143806 | OGE | OK/ | Multi - Rocky Point - OG&E Marietta - WFEC Marietta 138 kV Rebuild | Marietta Tap (OKGE) – Marietta Switchyard (WFEC) 138 kV Ckt 1 New Line (OGE) | Regional Reliability | 2024-12-16 | 2023-06-01 | 2022-03-11 | 2021 ITP | 1575000 | 2022 | 1654734.375 | 892961 |  | Delay - Mitigation |  |  |  |  | Build new 2.1 mile 138 kV line from Marietta Tap (OKGE) – Marietta Switchyard (WFEC) | 138
210656 | 92190 | 143815 | OGE | OK/ | Multi - Rocky Point - OG&E Marietta - WFEC Marietta 138 kV Rebuild | Marietta 2 138 kV Voltage Conversion | Regional Reliability | 2024-12-16 | 2023-06-01 | 2022-03-11 | 2021 ITP | 5000000 | 2022 | 5253125 | 3340351 |  | Delay - Mitigation |  |  |  |  | Convert the Marietta 2 substation from 69 kV to 138 kV and install terminal equipment to support a new 138 kV line from Marietta 4 | 69
210656 | 92190 | 143816 | OGE | OK | Multi - Rocky Point - OG&E Marietta - WFEC Marietta 138 kV Rebuild | Rocky Point - Marietta 2 138 kV Ckt 1 Rebuild | Regional Reliability | 2024-12-16 | 2023-06-01 | 2022-03-11 | 2021 ITP | 8806000 | 2022 | 9251803.75 | 29559659 |  | Delay - Mitigation |  |  |  |  | Rebuild the existing 69 kV line from Rocky Point to Marietta 2 as a 138 kV line | 69
210656 | 92190 | 143817 | OGE | OK | Multi - Rocky Point - OG&E Marietta - WFEC Marietta 138 kV Rebuild | Rocky Point 69 kV Replace Relays | Regional Reliability | 2024-12-16 | 2023-06-01 | 2022-03-11 | 2021 ITP | 250000 | 2022 | 262656.25 | 230807 |  | Delay - Mitigation Window |  |  |  |  | Replace the existing relays at Rocky Point | 69
210641 | 92213 | 143980 | NIPCO | IA// | Multi - Sioux City - Hinton 69 kV | Hinton 69 kV Terminal Equipment | Regional Reliability | 2023-10-31 | 2023-06-01 | 2022-03-11 | 2021 ITP | 223750 | 2022 | 229343.75 | 233750 |  | Delay - Mitigation |  |  |  |  | Upgrade the terminal equipment at Hinton (K412) substation.
210644 | 92238 | 144142 | TSGT | NE | Line - Ogallala Tri State - Ogallala NPPD 115 kV | Ogallala (Tri State) - Ogallala (NPPD) 115 kV (TSGT) | Economic | 2023-12-13 | 2023-01-01 | 2022-03-11 | 2021 ITP | 380321 | 2022 | 389829.025 | 380321 |  | Delay - Mitigation |  |  |  |  | Upgrade the 115 kV tie from Ogallala Tri State to Ogallala NPPD.
210645 | 92238 | 144143 | NPPD | NE | Line - Ogallala Tri State - Ogallala NPPD 115 kV | Ogallala (Tri State) - Ogallala (NPPD) 115 kV (NPPD) | Economic | 2023-12-31 | 2023-01-01 | 2022-03-09 | 2021 ITP | 281000 | 2022 | 288025 | 326708 |  | Delay - Mitigation |  |  |  |  | Upgrade the 115 kV tie from Ogallala Tri State to Ogallala NPPD.
210663 | 92178 | 144148 | MWE | ND | Multi - E Newtown 115 kV | E Newtown 115 kV New Statcom | Regional Reliability | 2024-07-01 | 2023-01-01 | 2022-07-12 | 2021 ITP | 22213115 | 2022 | 23337653.9469 | 19500000 |  | Delay - Mitigation |  |  |  |  | Install a 150 MVAR statcom and supporting equipment at E Newtown to control voltage on the 115 kV transmission system
210663 | 92211 | 144163 | MWE | ND | Multi - NE Williston - Folvag 115 kV - Judson - East Fork - Tande 345 kV | Folvag 115 kV Terminal Equipment | Regional Reliability | 2024-07-01 | 2023-01-01 | 2022-07-12 | 2021 ITP | 613746 | 2022 | 644816.8912 | 613746 |  | Delay - Mitigation |  |  |  |  | Install terminal equipment at Folvag 115 kV sub to accommodate new 115 kV line from NE Williston 115 kV sub.
210675 | 92211 | 144171 | BEPC | ND/ | Multi - NE Williston - Folvag 115 kV - Judson - East Fork - Tande 345 kV | East Fork 345/115 kV Substation | Regional Reliability | 2024-11-30 | 2023-01-01 | 2022-07-12 | 2021 ITP | 17766381 | 2022 | 18665804.0381 | 17866380 |  | Delay - Mitigation |  |  |  |  | Bisect the Judson to Tande 345 kV line approximately 18 miles from Judson and build a new 345 kV Substation.
210657 | 92190 | 144173 | WFEC | OK | Multi - Rocky Point - OG&E Marietta - WFEC Marietta 138 kV Rebuild | Marietta Switchyard 138 kV Ckt 1 Terminal Equipment | Regional Reliability | 2023-06-01 | 2023-06-01 | 2022-03-11 | 2021 ITP | 736000 | 2022 | 754400 | 736000 |  | Delay - Mitigation Window |  |  |  |  | Install terminal equipment at WFEC Marietta Switch to support a new 138 kV line from OG&E Marietta.
210663 | 92211 | 144177 | MWE | ND | Multi - NE Williston - Folvag 115 kV - Judson - East Fork - Tande 345 kV | NE Williston - Folvag 115 kV New Line | Regional Reliability | 2024-07-01 | 2023-01-01 | 2022-07-12 | 2021 ITP | 6490000 | 2022 | 6818556.25 | 8700000 |  | Delay - Mitigation |  |  |  |  | Build a new 4.5 mile 115 kV line from NE Williston to Folvag.
210663 | 92211 | 144178 | MWE | ND | Multi - NE Williston - Folvag 115 kV - Judson - East Fork - Tande 345 kV | NE Williston 115 kV Terminal Equipment | Regional Reliability | 2024-07-01 | 2023-01-01 | 2022-07-12 | 2021 ITP | 596597 | 2022 | 626799.7231 | 596597 |  | Delay - Mitigation |  |  |  |  | Install terminal equipment at NE Williston 115 kV sub to accommodate new 115 kV line from Folvag 115 kV sub.
210675 | 92211 | 144198 | BEPC | ND | Multi - NE Williston - Folvag 115 kV - Judson - East Fork - Tande 345 kV | East Fork 345/115 kV Transformer | Regional Reliability | 2024-11-30 | 2023-01-01 | 2022-07-12 | 2021 ITP | 5904650 | 2022 | 6203572.9062 | 6136273 |  | Delay - Mitigation |  |  |  |  | Install a 345/115 kV Transformer at the new East Fork 345/115 kV Substation.
210663 | 92211 | 144199 | MWE | ND/ | Multi - NE Williston - Folvag 115 kV - Judson - East Fork - Tande 345 kV | East Fork 115 kV Terminal Equipment | Regional Reliability | 2024-12-01 | 2023-01-01 | 2022-07-12 | 2021 ITP | 2511246 | 2022 | 2638377.8287 | 4092000 |  | On Schedule < 4 |  |  |  |  | Install 115 kV terminal equipment at MWEC’s East Fork 115 kV substation to accommodate a 115 kV tie line from the East Fork 345/115 kV substation. Construct a 115 kV tie line from the East Fork 115 kV substation to the proposed BEPC East Fork 345/115 kV substation.
210663 | 92178 | 144202 | MWE | ND | Multi - E Newtown 115 kV | E Newtown 115 kV Substation | Regional Reliability | 2024-07-01 | 2023-01-01 | 2022-07-12 | 2021 ITP | 1087789 | 2022 | 1142858.3181 | 1500000 |  | Delay - Mitigation |  |  |  |  | Expand existing 115 kV E Newtown substation to accommodate the statcom interconnection.
210663 | 92168 | 144226 | MWE | ND/ | Multi - Tande - Finstad - Leland Olds 345 kV | Finstad - Vanhook 115 kV New Line | Regional Reliability | 2025-12-01 | 2023-01-01 | 2022-07-12 | 2021 ITP | 4702500 | 2022 | 4940564.0625 | 4702500 |  | Delay - Mitigation |  |  |  |  | Build a 5-mile 115 kV line from Finstad to Vanhook.
210675 | 92168 | 144227 | BEPC | ND | Multi - Tande - Finstad - Leland Olds 345 kV | Finstad 115 kV Substation | Regional Reliability | 2026-11-30 | 2023-01-01 | 2022-07-12 | 2021 ITP | 4675697 | 2022 | 4912404.1606 | 4675697 |  | Delay - Mitigation |  |  |  |  | Build a new 115 kV Substation with terminal equipment to support a line from Vanhook 115 kV substation.
210675 | 92168 | 144230 | BEPC | ND/ | Multi - Tande - Finstad - Leland Olds 345 kV | Finstad 345 kV New Substation | Regional Reliability | 2026-11-30 | 2023-01-01 | 2022-07-12 | 2021 ITP | 18822018 | 2022 | 19774882.6612 | 18932308 |  | Delay - Mitigation |  |  |  |  | Build a new 345 kV Substation including 345 kV terminals for lines from Leland Olds 345 kV substation, Tande 345 kV substation and high side terminal equipment for Finstad 345/115 kV Ckt 1 transformer and Finstad 345/115 kV Ckt 2 transformer
210675 | 92168 | 144231 | BEPC | ND | Multi - Tande - Finstad - Leland Olds 345 kV | Finstad Switched Shunt | Regional Reliability | 2026-11-30 | 2023-01-01 | 2022-07-12 | 2021 ITP | 385021 | 2022 | 404512.6881 | 385021 |  | Delay - Mitigation |  |  |  |  | Install a switched shunt at Finstad.
210675 | 92168 | 144233 | BEPC | ND/ | Multi - Tande - Finstad - Leland Olds 345 kV | Finstad 345/115 kV Ckt 1 Transformer | Regional Reliability | 2026-11-30 | 2023-01-01 | 2022-07-12 | 2021 ITP | 5315254 | 2022 | 5584338.7337 | 5799981 |  | Delay - Mitigation |  |  |  |  | Install a 345/115 kV Ckt 1 Transformer at Finstad 345 | 345/115
210675 | 92168 | 144235 | BEPC | ND | Multi - Tande - Finstad - Leland Olds 345 kV | Finstad 345/115 kV Ckt 2 Transformer | Regional Reliability | 2026-11-30 | 2023-01-01 | 2022-07-12 | 2021 ITP | 5315254 | 2022 | 5584338.7337 | 5799981 |  | Delay - Mitigation |  |  |  |  | Install a 345/115 kV Ckt 2 transformer at Finstad 115 and upgrade any necessary 115 kV terminal equipment. | 345/115
210675 | 92168 | 144236 | BEPC | ND | Multi - Tande - Finstad - Leland Olds 345 kV | Leland Olds - Finstad - 345 kV New Line | Regional Reliability | 2026-11-30 | 2023-01-01 | 2022-07-12 | 2021 ITP | 200761539 | 2022 | 210925091.9119 | 215340373 |  | Delay - Mitigation |  |  |  |  | Build a 123 mile 345 kV line from Leland Olds to Finstad.
210675 | 92168 | 144237 | BEPC | ND/ | Multi - Tande - Finstad - Leland Olds 345 kV | Leland Olds 345 kV Substation | Regional Reliability | 2026-11-30 | 2023-01-01 | 2022-07-12 | 2021 ITP | 9277339 | 2022 | 9747004.2869 | 9338360 |  | Delay - Mitigation |  |  |  |  | Build a new 345 kV Substation with terminal equipment to support a new line from Finstad 345 kV substation.
210675 | 92168 | 144238 | BEPC | ND/ | Multi - Tande - Finstad - Leland Olds 345 kV | Tande 345 kV Terminal Equipment | Regional Reliability | 2026-11-30 | 2023-01-01 | 2022-07-12 | 2021 ITP | 5085047 | 2022 | 5342477.5044 | 5085047 |  | Delay - Mitigation |  |  |  |  | Install new terminal equipment at Tande to support a new 345 kV line from Finstad. Install a series compensation device at Finstad or Tande.
210663 | 92168 | 144239 | MWE | ND | Multi - Tande - Finstad - Leland Olds 345 kV | Vanhook 115 kV Terminal Equipment | Regional Reliability | 2025-12-01 | 2023-01-01 | 2022-07-12 | 2021 ITP | 3811190 | 2022 | 4004131.4937 | 3811190 |  | Delay - Mitigation |  |  |  |  | Install new 115 kV terminal equipment at Vanhook to support a new 115 kV line from Finstad.
210681 | 92421 | 156407 | SPS | NM | Multi - Crossroads - Hobbs - Roadrunner 345 kV dbl ckt | Crossroads 345 kV ckts 1 & 2 Terminal Equipment | Economic | 2025-05-15 | 2023-01-01 | 2022-09-12 | 2021 ITP | 16799460 | 2022 | 17649932.6625 | 15537358 |  | Delay - Mitigation |  |  |  |  | Install any necessary terminal equipment at Crossroads 345 kV to support a new double-circuit line to Hobbs 345 kV | 345
210681 | 92421 | 156408 | SPS | NM | Multi - Crossroads - Hobbs - Roadrunner 345 kV dbl ckt | Hobbs 345 kV ckts 1 & 2 Terminal Equipment #1 | Economic | 2025-05-15 | 2023-01-01 | 2022-09-12 | 2021 ITP | 14586640 | 2022 | 15325088.65 | 18672807 |  | Delay - Mitigation |  |  |  |  | Install any necessary terminal equipment at Hobbs 345 kV to support a new double-circuit line from Crossroads 345 kV | 345
210681 | 92421 | 156409 | SPS | NM | Multi - Crossroads - Hobbs - Roadrunner 345 kV dbl ckt | Hobbs 345 kV ckts 1 & 2 Terminal Equipment #2 | Economic | 2025-05-15 | 2023-01-01 | 2022-09-12 | 2021 ITP | 27053744 | 2022 | 28423339.79 | 12930976 |  | Delay - Mitigation |  |  |  |  | Install any necessary terminal equipment at Hobbs 345 kV to support a new double-circuit line from Roadrunner 345 kV | 345
210681 | 92421 | 156410 | SPS | NM | Multi - Crossroads - Hobbs - Roadrunner 345 kV dbl ckt | Roadrunner 345 kV ckts 1 & 2 Terminal Equipment | Economic | 2025-05-15 | 2023-01-01 | 2022-09-12 | 2021 ITP | 15831264 | 2022 | 16632721.74 | 14507008 |  | Delay - Mitigation |  |  |  |  | Install any necessary terminal equipment at Roadrunner 345 kV to support a new double-circuit line from Hobbs 345 kV | 345
220726 | 92421 | 156411 | NEET | NM | Multi - Crossroads - Hobbs - Roadrunner 345 kV dbl ckt | Crossroads - Hobbs 345 kV ckts 1 & 2 | Economic | 2026-05-15 | 2023-01-01 | 2023-10-03 | 2021 ITP |  |  | 0 | 196135073 |  | On Schedule < 4 |  |  |  |  | Build a new 90.5 mile 345 kV double-circuit line from Crossroads 345 kV substation to Hobbs 345 kV substation with a summer rating of at least 2640 MVA.. | 345 | 97
220726 | 92421 | 156412 | NEET | NM | Multi - Crossroads - Hobbs - Roadrunner 345 kV dbl ckt | Hobbs - Phantom 345 kV ckts 1 & 2 | Economic | 2026-05-15 | 2023-01-01 | 2023-10-03 | 2021 ITP |  |  | 0 | 95479502 |  | On Schedule < 4 |  |  |  |  | Build a new 44.5 mile 345 kV double-circuit line from Hobbs 345 kV substation to Roadrunner 345 kV substation with a summer rating of at least 2640 MVA | 345 | 46
210715 | 92394 | 156282 | WAPA | ND | Sub - Fargo 230 kV Terminal Upgrade | Fargo 230 kV Terminal Upgrade | Regional Reliability | 2025-12-31 | 2024-06-01 | 2022-12-09 | 2022 ITP | 3119998 | 2023 | 3197997.95 | 3277470 |  | Delay - Mitigation | 652435 | FARGO |  |  | Upgrade terminal conductor at Fargo 230 kV substation to support the line to Sheyenne | 230
210714 | 92382 | 156288 | SPS | NM | Device - Lea Road 115 kV Capacitor Bank | Lea Road 115 kV Capacitor Bank | Regional Reliability | 2026-12-15 | 2028-06-01 | 2022-12-09 | 2022 ITP | 5426756 | 2023 | 5562424.9 | 5200000 |  | On Schedule < 4 |  |  |  |  | Install 28.8 MVAR capacitor bank at Lea Road 115 kV substation | 115
210710 | 92381 | 156289 | EM | KS | Device - Craig 345 kV Relay | Craig 345 kV Relay | Regional Reliability |  | 2024-06-01 | 2022-12-09 | 2022 ITP | 200000 | 2022 | 210125 | 559232 |  | In Service |  |  |  |  | Install a redundant relay at the Craig 345 kV substation | 345
210708 | 92393 | 156293 | AEP | AR | Multi - Siloam Springs-Siloam Springs City 161 kV Terminal Upgrades | Siloam Springs 161 kV Terminal Upgrade | Regional Reliability | 2024-10-11 | 2024-06-01 | 2022-12-09 | 2022 ITP | 698030 | 2023 | 715480.75 | 698030 |  | Delay - Mitigation |  |  |  |  | Upgrade terminal equipment at Siloam Springs 161 kV substation | 161
210711 | 92393 | 156294 | GRDA | AR | Multi - Siloam Springs-Siloam Springs City 161 kV Terminal Upgrades | Siloam Springs City 161 kV Terminal Upgrade | Regional Reliability | 2024-06-01 | 2024-06-01 | 2022-12-09 | 2022 ITP | 324000 | 2023 | 332100 | 324000 |  | On Schedule < 4 |  |  |  |  | Upgrade terminal equipment at Siloam Springs City 161 kV substation | 161
210708 | 92386 | 156299 | AEP | OK | Line - 36th & Lewis - 52nd & Delaware Tap 138 kV Rebuild | 36th & Lewis - 52nd & Delaware Tap 138 kV Ckt 1 Rebuild | Regional Reliability | 2029-05-31 | 2027-06-01 | 2022-12-09 | 2022 ITP | 951250 | 2023 | 975031.25 | 4951250 |  | Delay - Mitigation |  |  |  |  | Rebuild 138 kV line from 36th & Lewis to 52nd & Delaware Tap | 138
210708 | 92386 | 156300 | AEP | OK | Line - 36th & Lewis - 52nd & Delaware Tap 138 kV Rebuild | 36th & Lewis 138 kV Ckt 1 Terminal Upgrade | Regional Reliability | 2029-05-31 | 2027-06-01 | 2022-12-09 | 2022 ITP | 540691 | 2023 | 554208.275 | 540691 |  | Delay - Mitigation | 509800 | 36th & LEWIS |  |  | Replace wave traps at 36th & Lewis 138 kV substation | 138
210712 | 92389 | 156320 | NIPCO | IA | Line - Eagle - J1 Center 69 kV Rebuild | Eagle - J1 Center 69 kV Ckt 1 rebuild | Regional Reliability | 2024-07-01 | 2024-06-01 | 2022-12-09 | 2022 ITP | 1644058 | 2023 | 1685159.45 | 1644058 |  | On Schedule < 4 |  |  |  |  | Rebuild 3.5 mile line from Eagle 69 kV substation to J1 Center 69 kV switching station | 69
210709 | 92403 | 156359 | EDE | MO | Device - Dadeville 161 kV Breaker | Dadeville 161 kV Breaker | Regional Reliability | 2020-12-04 | 2024-06-01 | 2022-12-09 | 2022 ITP |  |  | 0 | 135184 |  | In Service |  |  |  |  | Upgrade breaker 16103 at Dadeville 161 kV substation | 161
210709 | 92404 | 156360 | EDE | MO | Device - Joplin 69 kV Breaker | Joplin 69 kV Breaker | Regional Reliability | 2019-12-31 | 2024-06-01 | 2022-12-09 | 2022 ITP | 145818 | 2023 | 145818 | 0 |  | In Service |  |  |  |  | Upgrade breaker 3411 at Joplin 69 kV substation to 40 kA | 69
210709 | 92405 | 156361 | EDE | MO// | Device - Ozark Dam 161 kV Breaker | Ozark Dam 161 kV Breaker | Regional Reliability | 2024-01-31 | 2024-06-01 | 2022-12-09 | 2022 ITP | 985341 | 2023 | 1009974.525 | 985341 |  | On Schedule < 4 |  |  |  |  | Upgrade breaker 16103 at Ozark Dam 161 kV substation to 40 kA | 161
210713 | 92411 | 156372 | OGE | OK | Device - West Oak 138 kV Breakers | West Oak 138 kV Breaker #1 | Regional Reliability | 2024-06-01 | 2014-06-01 | 2022-12-09 | 2022 ITP | 166722 |  | 0 | 166722 |  | Delay - Mitigation | 514866 | WESTOAKS 138 |  |  | Upgrade breaker 4349 at West Oak 138 kV substation | 138
210713 | 92411 | 156373 | OGE | OK | Device - West Oak 138 kV Breakers | West Oak 138 kV Breaker #2 | Regional Reliability | 2024-06-01 | 2024-06-01 | 2022-12-09 | 2022 ITP | 166722 | 2023 | 170890.05 | 166722 |  | On Schedule < 4 | 514866 | WESTOAKS 138 |  |  | Upgrade breaker 4350 at West Oak 138 kV substation | 138
210714 | 92412 | 156374 | SPS | TX | Device - Lubbock South 115 kV Breaker | Lubbock South 115 kV Breaker | Regional Reliability | 2024-06-01 | 2024-06-01 | 2022-12-09 | 2022 ITP | 467987 | 2022 | 491678.8419 | 467987 |  | On Schedule < 4 | 526268 | Lubbock South Interchange 115 kV |  |  | Upgrade breaker 6940 at Lubbock South 115 kV substation | 115
210713 | 92413 | 156375 | OGE | OK | Device - Cherry Creek 138 kV Breaker | Cherry Creek 138 kV Breaker | Regional Reliability | 2024-06-01 | 2024-06-01 | 2022-12-09 | 2022 ITP | 157787 | 2023 | 161731.675 | 157787 |  | On Schedule < 4 | 514957 | CHERRY CREEK 138 |  |  | Upgrade breaker 3848 at Cherry Creek 138 kV substation | 138
210713 | 92414 | 156376 | OGE | OK | Device - Indian Hill 138 kV Breaker | Indian Hill 138 kV Breaker | Regional Reliability | 2024-06-01 | 2024-06-01 | 2022-12-09 | 2022 ITP | 157506 | 2023 | 161443.65 | 157506 |  | On Schedule < 4 | 515380 | Indian Hills 138kv |  |  | Upgrade breaker 4852 at Indian Hill 138 kV substation | 138
210713 | 92415 | 156377 | OGE | OK | Device - Turner 138 kV Breaker | Turner 138 kV Breaker | Regional Reliability | 2024-06-01 | 2024-06-01 | 2022-12-09 | 2022 ITP | 153163 | 2023 | 156992.075 | 153163 |  | On Schedule < 4 | 514992 | TURNER #4 138 |  |  | Upgrade breaker 4873 at Turner 138 kV substation | 138
220754 | 81701 | 122754 | WFEC | OK | Line - Anadarko - Gracemont 138 kV double Ckt 2 & 3 | Anadarko - Gracemont 138 kV Ckt3 (WFEC) | Economic |  | 2023-11-14 | 2023-12-15 | 2023 ITP |  |  | 0 | 19500000 |  | NTC-C Project Estimate Window | 520814 | ANADARKO | 515802 | Gracemont 138 kV | Build new 15 mile 138 kV Ckt 3 line from Anadarko 138 kV substation to Gracemont 138 kV substation as a double circuit to achieve a summer emergency rating of 478 MVA.
220754 | 81701 | 122756 | WFEC | OK/ | Line - Anadarko - Gracemont 138 kV double Ckt 2 & 3 | Anadarko138 kV Substation | Economic |  | 2023-11-14 | 2023-12-15 | 2023 ITP |  |  | 0 | 20000000 |  | NTC-C Project Estimate Window | 520814 | ANADARKO |  |  | Build a new substation at Anadarko 138 kV to support a second and third Ckt 138 kV line from Anadarko to Gracemont to achieve a summer emergency rating of 478 MVA
220739 | 81700 | 122761 | OGE | OK | Line - Cimarron - Czech Hall 138 kV Ckt 1 | Czech Hall 138 kV Terminal Upgrade | Economic |  | 2025-01-01 | 2023-12-15 | 2023 ITP |  |  | 0 | 69476 |  | NTC - Commitment Window | 514898 | CIMARRON 138 | 514894 | CZECH HALL 138 | Upgrade the switch at Czech Hall 138 kV on the Cimarron to Czech Hall line to achieve a 388/444/478/478 (SN/SE/WN/WE) MVA rating.
220741 | 92400 | 156301 | GRDA | OK/ | Line - Kerr 161 kV - Maid 161 kV Ckt 1 & Ckt 2 Rebuild | Kerr - Maid 161 kV Ckt 1 Rebuild #2 | Regional Reliability | 2026-12-31 | 2024-04-01 | 2023-11-15 | 2023 ITP |  |  | 0 | 4923250 |  | NTC - Commitment Window | 512635 | KERR 161 | 512648 | MAID 161 | Rebuild 5.5 miles of 161 kV Ckt 1 line from Kerr 161 kV substation to Maid 161 kV substation and upgrade any necessary terminal equipment to achieve a summer emergency rating of 557 MVA. | 161
220741 | 92400 | 156302 | GRDA | OK | Line - Kerr 161 kV - Maid 161 kV Ckt 1 & Ckt 2 Rebuild | Kerr 161 kV Terminal Equipment | Regional Reliability | 2026-12-31 | 2024-04-01 | 2023-11-15 | 2023 ITP |  |  | 0 | 730200 |  | NTC - Commitment Window | 512635 | KERR 161 |  |  | Install any necessary terminal equipment at Kerr 161 kV substation to support the line from Kerr 161 kV substation to Maid 161 kV substation with a summer emergency rating of 557 MVA. | 161
220741 | 92400 | 156303 | GRDA | OK | Line - Kerr 161 kV - Maid 161 kV Ckt 1 & Ckt 2 Rebuild | Maid 161 kV Terminal Equipment | Regional Reliability |  | 2024-04-01 | 2023-11-15 | 2023 ITP |  |  | 0 | 1107600 |  | NTC - Commitment Window | 512648 | MAID 161 |  |  | Install any necessary terminal equipment at Maid 161 kV substation to support the line from Maid 161 kV substation to Kerr 161 kV substation with a summer emergency rating of 557 MVA | 161
220741 | 92400 | 156304 | GRDA | OK/ | Line - Kerr 161 kV - Maid 161 kV Ckt 1 & Ckt 2 Rebuild | Kerr - Maid 161 kV Ckt 2 Rebuild | Regional Reliability | 2026-12-31 | 2024-04-01 | 2023-11-15 | 2023 ITP |  |  | 0 | 4923250 |  | NTC - Commitment Window | 512635 | KERR 161 | 512648 | MAID 161 | Rebuild 5.5 miles of 161 kV Ckt 2 line from Kerr 161 kV to Maid 161 kV and upgrade any necessary terminal equipment to achieve a summer emergency rating of 557 MVA. | 161
220741 | 92400 | 156305 | GRDA | OK/ | Line - Kerr 161 kV - Maid 161 kV Ckt 1 & Ckt 2 Rebuild | Kerr 161 kV Terminal Equipment Ckt 2 | Regional Reliability |  | 2024-04-01 | 2023-11-15 | 2023 ITP |  |  | 0 | 730200 |  | NTC - Commitment Window | 512635 | KERR 161 |  |  | Install any necessary terminal equipment at Kerr 161 kV substation to support the line from Kerr 161 kV substation to Maid 161 kV substation with a summer emergency rating of 557 MVA. | 161
220741 | 92400 | 156306 | GRDA | OK | Line - Kerr 161 kV - Maid 161 kV Ckt 1 & Ckt 2 Rebuild | Maid 161 kV Terminal Upgrade Ckt 2 | Regional Reliability |  | 2024-04-01 | 2023-11-15 | 2023 ITP |  |  | 0 | 1107600 |  | NTC - Commitment Window | 512648 | MAID 161 |  |  | Install any necessary terminal equipment at Maid 161 kV substation to support the line from Maid 161 kV substation to Kerr 161 kV substation with a summer emergency rating of 557 MVA. | 161
220751 | 92940 | 157186 | SEPC | KS | Device - Ellsworth Tap - Great Bend 115 kV Ckt 1 Structure Upgrade | Ellsworth Tap - Great Bend 115 kV Ckt 1 Structure Upgrade | Economic |  | 2028-01-01 | 2023-11-19 | 2023 ITP |  |  | 0 | 750000 |  | NTC - Commitment Window | 539642 | Ellsworth Tap | 539678 | Mullergren 115 KV | Upgrade 25 structures of the 30.2 mile 115 kV line from Ellsworth Tap substation to Great Bend substation | 115
220746 | 92947 | 157202 | EM | KS | Sub - Craig 161 kV - Lenexa South 161 kV Ckt 2 Terminal Upgrades | Craig 161 kV Ckt 2 Terminal Upgrade | Economic |  | 2025-01-01 | 2023-12-15 | 2023 ITP |  |  | 0 | 1329162 |  | NTC - Commitment Window | 542978 | CRAIG 161 KV |  |  | Upgrade any necessary terminal equipment at Craig 161 kV substation on the Lenexa South to Craig 161 kV line to achieve a summer emergency rating of 557 MVA. | 161
220746 | 92947 | 157203 | EM | KS | Sub - Craig 161 kV - Lenexa South 161 kV Ckt 2 Terminal Upgrades | Lenexa South 161 kV Ckt 2 Terminal Upgrade | Economic |  | 2025-01-01 | 2023-12-15 | 2023 ITP |  |  | 0 | 1329161 |  | NTC - Commitment Window | 543038 | LENEXA SOUTH 161 KV |  |  | Upgrade any necessary terminal equipment at Lenexa South 161 kV substation on the Craig to Lenexa South 161 kV line to achieve a summer emergency rating of 557 MVA. | 161
220739 | 92955 | 157241 | OGE | OK | XFR - Seminole 345/138 kV Ckt3 | Seminole 345/138 kV Transformer Ckt 3 (138 kV) | Regional Reliability |  | 2024-06-01 | 2023-12-15 | 2023 ITP |  |  | 0 | 3415129 |  | NTC - Commitment Window | 515045 | SEMINOLE 345 |  |  | Install a new 345/138 kV transformer at Seminole 138 kV substation to achieve a summer emergency rating of 448 MVA. | 345/138
220739 | 92955 | 157242 | OGE | OK | XFR - Seminole 345/138 kV Ckt3 | Seminole 345/138 kV Transformer Ckt 3 (345 kV) | Regional Reliability |  | 2024-06-01 | 2023-12-15 | 2023 ITP |  |  | 0 | 4891214 |  | NTC - Commitment Window | 515044 | SEMINOLE 138 |  |  | Install a new 345/138 kV transformer at Seminole 345 kV substation to achieve a summer emergency rating of 675 MVA. | 345/138
220739 | 92966 | 157254 | OGE | OK | Device - Lightning Creek 138 kV Breaker | Lightning Creek 138 kV Breaker #1 | Regional Reliability |  | 2024-06-01 | 2023-12-15 | 2023 ITP |  |  | 0 | 1418348 |  | NTC - Commitment Window | 514923 | LIGHTNING CREEK 138 |  |  | Upgrade 2 breakers at Lightning Creek 138 kV substation with a 50 kA breaker. | 138
220746 | 92969 | 157255 | EM | OK | Device - Blue Valley 161 kV Breaker | Blue Valley 161 kV Breaker #1 | Regional Reliability |  | 2024-06-01 | 2023-12-15 | 2023 ITP |  |  | 0 | 310000 |  | NTC - Commitment Window | 543000 | BLUE VALLEY 161 KV |  |  | Upgrade breaker R8-14 at the Blue Valley 161 kV substation with 63 kA breakers. | 161
220746 | 92970 | 157256 | EM | KS | Device - Craig 161 kV Breaker | Craig 161 kV Breaker #1 | Regional Reliability |  | 2024-06-01 | 2023-12-15 | 2023 ITP |  |  | 0 | 609491 |  | NTC - Commitment Window | 542978 | CRAIG 161 KV |  |  | Upgrade breaker R1-11 at Craig 161 kV substation with 63 kA breakers. | 161
220746 | 92970 | 157257 | EM | KS | Device - Craig 161 kV Breaker | Craig 161 kV Breaker #3 | Regional Reliability |  | 2024-06-01 | 2023-12-15 | 2023 ITP |  |  | 0 | 609490 |  | NTC - Commitment Window | 542978 | CRAIG 161 KV |  |  | Upgrade breaker R3-6 at Craig 161 kV substation with 63 kA breakers | 161
220746 | 92970 | 157258 | EM | KS | Device - Craig 161 kV Breaker | Craig 161 kV Breaker #4 | Regional Reliability |  | 2024-06-01 | 2023-12-15 | 2023 ITP |  |  | 0 | 609491 |  | NTC - Commitment Window | 542978 | CRAIG 161 KV |  |  | Upgrade breaker R5-11 at Craig 161 kV substation with 63 kA breakers. | 161
220746 | 92970 | 157259 | EM | KS | Device - Craig 161 kV Breaker | Craig 161 kV Breaker #5 | Regional Reliability |  | 2024-06-01 | 2023-12-15 | 2023 ITP |  |  | 0 | 609491 |  | NTC - Commitment Window | 542978 | CRAIG 161 KV |  |  | Upgrade breaker R6-33 at Craig 161 kV substation with 63 kA breakers. | 161
220737 | 92974 | 157263 | AEP | OK | Line - Flournoy 138 kV- Oak Pan-Harr 138 kV - Longwood 138 kV | Longwood - Oak Pan-Harr 138 kV Ckt 1 Rebuild | Regional Reliability |  | 2028-06-01 | 2023-12-15 | 2023 ITP |  |  | 0 | 4070000 |  | NTC - Commitment Window | 508808 | LONGWOOD 138KV | 508816 | OAK PAN-HARR REC | Rebuild 1.8 miles of 138 kV line from Longwood 138 kV to Oak Pan-Harr 138 kV substation and upgrade any necessary terminal equipment to achieve a summer emergency rating of 324 MVA. | 138
220737 | 92974 | 157264 | AEP | OK | Line - Flournoy 138 kV- Oak Pan-Harr 138 kV - Longwood 138 kV | Longwood 138 kV Terminal Upgrade | Regional Reliability |  | 2028-06-01 | 2023-12-15 | 2023 ITP |  |  | 0 | 150000 |  | NTC - Commitment Window | 508808 | LONGWOOD 138KV |  |  | Upgrade any necessary terminal equipment at Longwood 138 kV substation on the Longwood to Oak Pan-Harr 138 kV line to achieve a summer emergency rating of 324 MVA. | 138
220737 | 92974 | 157266 | AEP | OK | Line - Flournoy 138 kV- Oak Pan-Harr 138 kV - Longwood 138 kV | Flournoy - Oak Pan-Harr 138 kV Ckt 1 Rebuild | Regional Reliability |  | 2028-06-01 | 2023-12-15 | 2023 ITP |  |  | 0 | 15260000 |  | NTC - Commitment Window | 507727 | FLOURNOY 138KV | 508816 | OAK PAN-HARR REC | Rebuild 10.4 miles of 138 kV line from Flournoy 138 kV substation to Oak Pan-Harr 138 kV substation and upgrade any necessary terminal equipment to achieve a summer emergency rating of 287 MVA. | 138
220737 | 92976 | 157268 | AEP | AR | XFR - Turk 138/115 kV | Turk 138/115 kV Transformer Ckt 1 (138 kV) | Regional Reliability |  | 2024-06-01 | 2023-12-15 | 2023 ITP |  |  | 0 | 5250000 |  | NTC - Commitment Window | 507454 | Turk 138 |  |  | Replace current 138/115 transformer Ckt 1 at Turk 138 kV substation to achieve a summer emergency rating of 250 MVA. | 138/115
220739 | 92980 | 157274 | OGE | OK | Sub - Newman Grace Tap - Woodward Nitrogen 69 kV Terminal Upgrade | Woodward Nitrogen 69 kV Terminal Upgrade | Regional Reliability |  | 2024-06-01 | 2023-12-15 | 2023 ITP |  |  | 0 | 815000 |  | NTC - Commitment Window | 514779 | WOODWARD NITROGEN 69 |  |  | Upgrade any necessary terminal equipment at Woodward Nitrogen 69 kV substation on the Woodward Nitrogen to Newman Grace Tap 69 kV line to achieve a summer emergency rating of 71 MVA. | 69
220748 | 93107 | 157280 | WAPA | OK | Device Dawson County-Fort Peck 230 kV 40 MVAR Line Reactor | Dawson County-Fort Peck 230 kV Line Reactor | Regional Reliability |  | 2024-06-01 | 2023-12-15 | 2023 ITP |  |  | 0 | 4007750 |  | NTC - Commitment Window | 652405 | FT PECK |  |  | Install 40 MVAR reactor on the Dawson County-Fort Peck 230 kV Line | 230
220747 | 92987 | 157375 | BEPC | ND | Device - Broadland 345 kV Reactor | Broadland 345 kV Reactor | Regional Reliability |  | 2024-04-01 | 2023-12-15 | 2023 ITP |  |  | 0 | 5445170 |  | NTC - Commitment Window |  |  |  |  | Install 2nd 75 MVAR reactor at Broadland 345 kV substation | 345
220750 | 92989 | 157377 | SPS | TX | Sub - Moore Co 115 kV Terminal Upgrade | Moore Co 115 kV Terminal Upgrade | Regional Reliability |  | 2027-06-01 | 2023-12-15 | 2023 ITP |  |  | 0 | 210000 |  | NTC - Commitment Window | 523304 | Moore County Interchange West Bus 115 kV |  |  | Upgrade any necessary terminal equipment at Moore Co 115 kV substation to achieve a summer emergency rating of 175 MVA. | 115
220758 | 92992 | 157382 | WFEC | OK | Sub - Anadarko 138 kV - Southwestern 138 kV | Anadarko 138 kV Terminal Upgrade Ckt 1 | Economic |  | 2025-01-01 | 2023-12-15 | 2023 ITP |  |  | 0 | 1000000 |  | NTC - Commitment Window | 520814 | ANADARKO |  |  | Upgrade terminal equipment at Anadarko 138 kV substation for the line to Southwestern 138 kV substation | 138
220743 | 92993 | 157383 | NPPD | NE | XFR - Fremont 115/69 kV & Sub 976 Terminal Upgrade | Sub 976 115/69 kV Transformer Ckt 2 (69 kV) | Economic |  | 2025-01-01 | 2023-12-15 | 2023 ITP |  |  | 0 | 5600000 |  | NTC - Commitment Window | 640173 | Fremont |  |  | Install new 115/69 transformer at Fremont 115 kV substation | 115/69
220743 | 92993 | 157384 | NPPD | NE | XFR - Fremont 115/69 kV & Sub 976 Terminal Upgrade | Fremont 115/69 kV Transformer Ckt 2 (115 kV) | Economic |  | 2025-01-01 | 2023-12-15 | 2023 ITP |  |  | 0 | 300000 |  | NTC - Commitment Window | 647976 | Sub 976 |  |  | Install 115 kV terminal equipment to support 115/69 transformer at Fremont 115 kV substation | 115/69
220745 | 92994 | 157385 | LES | NE | Multi - Sub 1214 - 70th & Bluff 161 kV Rebuild | Sub 1214 - 70th & Bluff 161 kV Ckt 1 Rebuild (LES) | Economic |  | 2027-01-01 | 2023-12-15 | 2023 ITP |  |  | 0 | 1200000 |  | NTC - Commitment Window | 646214 | Sub 1214 | 650169 | 70th & Bluff | Rebuild 17.7 miles of 161 kV Ckt 1 line from Sub 1214 161 kV substation to 70th & Bluff161 kV substation with a summer emergency rating of 215 MVA. | 161
220744 | 92994 | 157386 | OPPD | NE | Multi - Sub 1214 - 70th & Bluff 161 kV Rebuild | Sub 1214 161 kV Terminal Upgrade | Economic |  | 2027-01-01 | 2023-12-15 | 2023 ITP |  |  | 0 | 114179 |  | NTC - Commitment Window |  |  |  |  | Upgrade any necessary terminal equipment at Sub 1214 161 kV substation on the 70th & Bluff to Sub 1214 161 kV line to achieve a summer emergency rating of 215 MVA. | 161
220745 | 92994 | 157387 | LES | NE | Multi - Sub 1214 - 70th & Bluff 161 kV Rebuild | 70th & Bluff 161 kV Terminal Upgrade | Economic |  | 2027-01-01 | 2023-12-15 | 2023 ITP |  |  | 0 | 2700000 |  | NTC - Commitment Window | 650169 | 70th & Bluff |  |  | Upgrade any necessary terminal equipment at 70th & Bluff 161 kV substation on the Sub 1214 to 70th & Bluff 161 kV line to achieve a summer emergency rating of 215 MVA. | 161
220739 | 92996 | 157390 | OGE | OK | Multi - Southgate - Westmoore Tap - Pennsylvania 138 kV | Southgate - Westmoore Tap 138 kV Extend Line | Regional Reliability |  | 2027-06-01 | 2023-12-15 | 2023 ITP |  |  | 0 | 6470000 |  | NTC - Commitment Window | 514887 | WESTMOORE 138 | 514928 | SOUTHGATE 138 | Extend Southgate - Westmoore Tap 138 kV 0.76 miles to Westmoore 138 kV substation, including structures suited for double circuit configuration. | 138
220739 | 92996 | 157392 | OGE | OK | Multi - Southgate - Westmoore Tap - Pennsylvania 138 kV | Westmoore 138 kV Terminal Upgrade #2 | Regional Reliability |  | 2027-06-01 | 2023-12-15 | 2023 ITP |  |  | 0 | 4790000 |  | NTC - Commitment Window | 514887 | WESTMOORE 138 |  |  | Install any necessary terminal equipment at Westmoore 138 kV substation to support a new line from Westmoore substation to Southgate 138 kV substation with a summer emergency rating of 308 MVA. | 138
220739 | 92996 | 157393 | OGE | OK | Multi - Southgate - Westmoore Tap - Pennsylvania 138 kV | Pennsylvania 138 kV Terminal Upgrade | Regional Reliability |  | 2027-06-01 | 2023-12-15 | 2023 ITP |  |  | 0 | 200000 |  | NTC - Commitment Window | 514925 | PENNSYLVANIA 138 |  |  | Install a 2000 Amp switch at the Pennsylvania 138 kV substation. | 138
220738 | 81701 | 157395 | OGE | OK | Line - Anadarko - Gracemont 138 kV double Ckt 2 & 3 | Gracemont 138 kV Ck 2 Terminal Upgrade | Economic |  | 2023-11-14 | 2023-12-15 | 2023 ITP |  |  | 0 | 2171478 |  | NTC-C Project Estimate Window | 515802 | Gracemont 138 kV |  |  | Install any necessary terminal equipment at Gracemont 138 kV substation to support a second line from Gracemont to Anadarko 138 kV substation with a summer emergency rating of 286 MVA. | 138
220754 | 81701 | 157396 | WFEC | OK | Line - Anadarko - Gracemont 138 kV double Ckt 2 & 3 | Anadarko 138 kV Ckt 3 Terminal Upgrade | Economic |  | 2023-11-14 | 2023-12-15 | 2023 ITP |  |  | 0 | 2500000 |  | NTC-C Project Estimate Window | 520814 | ANADARKO |  |  | Install any necessary terminal equipment at Anadarko 138 kV substation to support a third line from Anadarko to Gracemont 138 kV substation with a summer emergency rating of 478 MVA. | 138
220745 | 92994 | 157397 | LES | NE | Multi - Sub 1214 - 70th & Bluff 161 kV Rebuild | 70th & Bluff 161/115 kV Transformer Ckt 1 (115 kV) | Economic |  | 2027-01-01 | 2023-12-15 | 2023 ITP |  |  | 0 | 4900000 |  | NTC - Commitment Window | 650169 | 70th & Bluff |  |  | Upgrade 161/115 transformer Ckt 1 at 70th & Bluff 115 kV substation to achieve a summer emergency rating of 215 MVA. | 161/115
220749 | 92999 | 157403 | EKC | KS | Sub - Blackberry - Neosho 345 kV Terminal Equipment | Neosho 345 kV Terminal Upgrade | Economic |  | 2025-01-01 | 2023-12-15 | 2023 ITP |  |  | 0 | 3415129 |  | NTC - Commitment Window | 532793 | NEOSHO 345 KV |  |  | Install any necessary terminal equipment at Neosho 345 kV substation on the Neosho to Blackberry 345 kV line to achieve a summer emergency rating of 870 MVA. | 345
220749 | 93000 | 157405 | EKC | KS | Sub - Butler 138 kV - Midian 138 kV Terminal Upgrade | Butler 138 kV Terminal Upgrade | Economic |  | 2025-01-01 | 2023-12-15 | 2023 ITP |  |  | 0 | 1329161 |  | NTC - Commitment Window | 532987 | BUTLER 138 KV |  |  | Upgrade any necessary terminal equipment at Butler 138 kV substation on the Butler to Midian 138 kV line to achieve a summer emergency rating of 286 MVA. | 138
220749 | 93000 | 157406 | EKC | KS | Sub - Butler 138 kV - Midian 138 kV Terminal Upgrade | Midian 138 kV Ckt 1 Terminal Upgrade | Economic |  | 2025-01-01 | 2023-12-15 | 2023 ITP |  |  | 0 | 1329161 |  | NTC - Commitment Window | 532990 | MIDIAN 138 KV |  |  | Upgrade any necessary terminal equipment at Midian 138 kV substation on the Midian to Butler 138 kV line to achieve a summer emergency rating of 286 MVA. | 138
220737 | 93019 | 157475 | AEP | OK | Line - Pine & Peoria Tap 138 kV - 46Th Street Tap 138 kV-Tulsa North 138 kV Rebuild | Pine & Peoria Tap - 46Th Street Tap 138 kV Ckt 1 Rebuild | Economic |  | 2025-01-01 | 2023-12-15 | 2023 ITP |  |  | 0 | 1481809 |  | NTC - Commitment Window | 509863 | PINE & PEORIA TAP | 509900 |  | Rebuild 0.5 miles of 138 kV Ckt 1 line from Pine & Peoria Tap 138 kV substation to 46Th Street Tap 138 kV substation and upgrade any necessary terminal equipment to achieve a summer emergency rating of 347 MVA. | 138
220737 | 93019 | 157517 | AEP | OK | Line - Pine & Peoria Tap 138 kV - 46Th Street Tap 138 kV-Tulsa North 138 kV Rebuild | Tulsa North - 46Th Street Tap 138 kV Ckt 1 Rebuild | Economic |  | 2025-01-01 | 2023-12-15 | 2023 ITP |  |  | 0 | 14714997 |  | NTC - Commitment Window | 509817 | TULSA NORTH | 509900 |  | Rebuild 5.2 miles of 138 kV Ckt 1 line from Tulsa North 138 kV substation to 46th Street Tap138 kV substation and upgrade any necessary terminal equipment to achieve a summer emergency rating of 347 MVA. | 138
220737 | 93019 | 157518 | AEP | OK | Line - Pine & Peoria Tap 138 kV - 46Th Street Tap 138 kV-Tulsa North 138 kV Rebuild | Tulsa North 138 kV Terminal Upgrade | Economic |  | 2025-01-01 | 2023-12-15 | 2023 ITP |  |  | 0 | 150000 |  | NTC - Commitment Window | 509817 | TULSA NORTH |  |  | Upgrade any necessary terminal equipment at Tulsa North 138 kV substation on the 46th Street Tap to Tulsa North 138 kV line to achieve a summer emergency rating of 347 MVA. | 138
220736 | 93038 | 157526 | AEP | OK | Line - Osage - Webb City Tap - Shidler 138 kV Rebuild | Shidler - Webb City Tap 138 kV Ckt 1 Rebuild | Economic |  | 2023-11-14 | 2023-12-15 | 2023 ITP |  |  | 0 | 4718963 |  | NTC-C Project Estimate Window | 510376 | WEBB CITY TAP | 510403 | SHIDLER | Rebuild 2.2 miles of 138 kV line from Shidler 138 kV substation to Webb City Tap 138 kV and upgrade any necessary terminal equipment to achieve a summer emergency rating of 561 MVA. | 138
220736 | 93038 | 157527 | AEP | OK | Line - Osage - Webb City Tap - Shidler 138 kV Rebuild | Webb City Tap 138 kV Terminal Upgrade | Economic |  | 2023-11-14 | 2023-12-15 | 2023 ITP |  |  | 0 | 902559 |  | NTC-C Project Estimate Window | 510376 | WEBB CITY TAP |  |  | Upgrade any necessary terminal equipment at Webb City Tap 138 kV substation on the Shidler to Webb City 138 kV line to achieve a summer emergency rating of 561 MVA. | 138
220736 | 93038 | 157528 | AEP | OK | Line - Osage - Webb City Tap - Shidler 138 kV Rebuild | Shidler 138 kV Terminal Upgrade | Economic |  | 2023-11-14 | 2023-12-15 | 2023 ITP |  |  | 0 | 150000 |  | NTC-C Project Estimate Window | 510403 | SHIDLER |  |  | Upgrade any necessary terminal equipment at Shidler 138 kV substation on the Webb City Tap to Shidler 138 kV line to achieve a summer emergency rating of 561 MVA. | 138
220736 | 93038 | 157529 | AEP | OK | Line - Osage - Webb City Tap - Shidler 138 kV Rebuild | Webb City Tap - Osage 138 kV Ckt 1 Rebuild (AEP) | Economic |  | 2023-11-14 | 2023-12-15 | 2023 ITP |  |  | 0 | 4765631 |  | NTC-C Project Estimate Window | 510376 | WEBB CITY TAP | 514743 | OSAGE 138 | Rebuild 22.2 miles of 138 kV line from Webb City Tap 138 kV substation to Osage 138 kV substation and upgrade any necessary terminal equipment to achieve a summer emergency rating of 561 MVA. | 138
220738 | 93038 | 157530 | OGE | OK | Line - Osage - Webb City Tap - Shidler 138 kV Rebuild | Osage 138 kV Terminal Upgrade | Economic |  | 2023-11-14 | 2023-12-15 | 2023 ITP |  |  | 0 | 4500000 |  | NTC-C Project Estimate Window | 514743 | OSAGE 138 |  |  | Upgrade any necessary terminal equipment at Osage 138 kV substation on the Osage to Webb City Tap 138 kV line to achieve a summer emergency rating of 561 MVA. | 138
220736 | 93038 | 157534 | AEP | OK | Line - Osage - Webb City Tap - Shidler 138 kV Rebuild | Webb City Tap 138 kV Terminal Upgrade #2 | Economic |  | 2023-11-14 | 2023-12-15 | 2023 ITP |  |  | 0 | 902559 |  | NTC-C Project Estimate Window | 510376 | WEBB CITY TAP |  |  | Upgrade any necessary terminal equipment at Webb City Tap 138 kV substation on the Webb City Tap to Osage 138 kV line to achieve a summer emergency rating of 561 MVA. | 138
220753 | 93063 | 157551 | WAPA | SD | XFR - Fort Thompson 345/230 kV | Fort Thompson 345/230 kV Transformer Ckt 1 (345 kV) | Economic |  | 2023-11-14 | 2023-12-15 | 2023 ITP |  |  | 0 | 12963375 |  | NTC-C Project Estimate Window | 652506 | FT THOMPSON |  |  | Replace any 345 kV terminal equipment to support 345/230 transformer Ckt 1 at Fort Thompson 345 kV substation. | 345/230
220753 | 93063 | 157552 | WAPA | SD | XFR - Fort Thompson 345/230 kV | Fort Thompson 345/230 kV Transformer Ckt 2 (230 kV) | Economic |  | 2023-11-14 | 2023-12-15 | 2023 ITP |  |  | 0 | 4891214 |  | NTC-C Project Estimate Window | 652507 | FT THOMPSON |  |  | Replace any 230 kV terminal equipment to support 345/230 transformer Ckt 2 at Fort Thompson 230 kV substation. | 345/230
220753 | 93063 | 157553 | WAPA | SD | XFR - Fort Thompson 345/230 kV | Fort Thompson 345/230 kV Transformer Ckt 2 (345 kV) | Economic |  | 2023-11-14 | 2023-12-15 | 2023 ITP |  |  | 0 | 12963375 |  | NTC-C Project Estimate Window | 652506 | FT THOMPSON |  |  | Replace any 345 kV terminal equipment to support 345/230 transformer Ckt 2 at Fort Thompson 345 kV substation. | 345/230
220753 | 93063 | 157554 | WAPA | SD | XFR - Fort Thompson 345/230 kV | Fort Thompson 345/230 kV Transformer Ckt 1 (230 kV) | Economic |  | 2023-11-14 | 2023-12-15 | 2023 ITP |  |  | 0 | 2728949 |  | NTC-C Project Estimate Window | 652507 | FT THOMPSON |  |  | Replace any 230 kV terminal equipment to support 345/230 transformer Ckt 1 at Fort Thompson 230 kV substation. | 345/230
220743 | 93042 | 157594 | NPPD | NE | Multi- Gerald Gentleman Station - Ogallala 230 kV Terminal Upgrades | Gerald Gentleman Station - Ogallala 230 kV Line & Terminal Upgrades | Economic |  | 2023-11-14 | 2023-12-15 | 2023 ITP |  |  | 0 | 1600000 |  | NTC - Commitment Window |  |  |  |  | Upgrade any necessary terminal equipment at Gerald Gentleman Station 230 kV substation on the Gerald Gentleman Station to Ogallala 230 kV line to achieve a summer emergency rating of 435 MVA. | 230
220743 | 93042 | 157595 | NPPD | NE | Multi- Gerald Gentleman Station - Ogallala 230 kV Terminal Upgrades | Ogallala 230 kV Terminal Upgrade | Economic |  | 2023-11-14 | 2023-12-15 | 2023 ITP |  |  | 0 | 100000 |  | NTC - Commitment Window |  |  |  |  | Upgrade any necessary terminal equipment at Ogallala 230 kV substation on the Ogallala to Gerald Gentleman Station 230 kV line to achieve a summer emergency rating of 435 MVA. | 230
220749 | 93053 | 157620 | EKC | KS | XFR - Franklin 161/69 kV Ckt 2 | Franklin 161/69 kV Transformer Ckt 2 (69 kV) | Economic |  | 2025-01-01 | 2023-12-15 | 2023 ITP |  |  | 0 | 1661885 |  | NTC - Commitment Window |  |  |  |  | Install new 161/69 transformer Ckt 2 at Franklin 69 kV substation. | 161/69
220749 | 93053 | 157621 | EKC | KS | XFR - Franklin 161/69 kV Ckt 2 | Franklin 161/69 kV Transformer Ckt 2 (161 kV) | Economic |  | 2025-01-01 | 2023-12-15 | 2023 ITP |  |  | 0 | 1661884 |  | NTC - Commitment Window |  |  |  |  | Install new 161/69 transformer Ckt 2 at Franklin 161 kV substation. | 161/69
220739 | 93062 | 157644 | OGE | OK | Line - Fitzgerald Creek - Kinze 138 kV | Fitzgerald Creek - Kinze 138 kV Line Tap | Economic |  | 2025-01-01 | 2023-12-15 | 2023 ITP |  |  | 0 | 10016640 |  | NTC - Commitment Window | 514830 | FITZGERALD CREEK 138 | 515008 | KINZE 138 | Tap and extend the existing Fitzgerald Creek - Kinze 138 kV line by 2 miles to terminate at Valley 138 kV substation | 138
220739 | 93062 | 157650 | OGE | OK | Line - Fitzgerald Creek - Kinze 138 kV | Valley 138 kV Terminal Equipment | Economic |  | 2025-01-01 | 2023-12-15 | 2023 ITP |  |  | 0 | 483360 |  | NTC - Commitment Window | 300143 | Valley |  |  | Install any necessary terminal equipment at Valley 138 kV substation to support the new tap from Fitzgerald Creek - Kinze 138 kV line tap to Valley substation with a summer emergency rating of 222 MVA. | 138
220742 | 93101 | 157721 | NWE | SD | Line - Huron 'B' Tap 115 kV - Huron 115 kV - Huron West Park 115 kV Rebuild | Huron West Park 115 kV Terminal Upgrade | Economic |  | 2025-01-01 | 2023-12-15 | 2023 ITP |  |  | 0 | 393298 |  | NTC - Commitment Window | 660003 | HURON WEST PARK |  |  | Upgrade any necessary terminal equipment at Huron West Park 115 kV substation on the Huron West Park to Huron 'B' Tap 115 kV line to achieve a summer emergency rating of 239 MVA. | 115
220742 | 93101 | 157724 | NWE | SD | Line - Huron 'B' Tap 115 kV - Huron 115 kV - Huron West Park 115 kV Rebuild | Huron B Tap 115 kV Terminal Upgrade | Economic |  | 2025-01-01 | 2023-12-15 | 2023 ITP |  |  | 0 | 393298 |  | NTC - Commitment Window | 660009 | WEST PARK B TAP |  |  | Upgrade any necessary terminal equipment at Huron B Tap 115 kV substation on the Huron B Tap to Huron 115 kV line to achieve a summer emergency rating of 239 MVA. | 115
220755 | 93103 | 157736 | MGS | ND | Device - Devaul 2 115 kV Switched Shunt | Devaul 115 kV Reactor | Regional Reliability |  | 2024-04-01 | 2023-12-15 | 2023 ITP |  |  | 0 | 1671705 |  | NTC - Commitment Window | 655747 |  |  |  | Install 15 MVAR reactor at Devaul 115 kV substation | 115
220738 | 81701 | 157879 | OGE | OK | Line - Anadarko - Gracemont 138 kV double Ckt 2 & 3 | Anadarko - Gracemont 138 kV Ckt 3 New Line (OGE) | Economic |  | 2023-11-14 | 2023-12-15 | 2023 ITP |  |  | 0 | 22081965 |  | NTC-C Project Estimate Window | 515802 | Gracemont 138 kV | 520814 | ANADARKO | Build new 15 mile 138 kV Ckt 3 line from Anadarko 138 kV substation to Gracemont 138 kV substation as a double circuit to achieve a summer emergency rating of 478 MVA. | 138
220738 | 93038 | 157880 | OGE | OK | Line - Osage - Webb City Tap - Shidler 138 kV Rebuild | Webb City Tap - Osage 138 kV Ckt 1 Rebuild (OGE) | Economic |  | 2023-11-14 | 2023-12-15 | 2023 ITP |  |  | 0 | 28250000 | 25000000 | NTC-C Project Estimate Window | 510376 | WEBB CITY TAP | 514743 | OSAGE 138 | Rebuild 20 miles of 138 kV line from Webb City Tap 138 kV substation to Osage 138 kV substation and upgrade any necessary terminal equipment to achieve a summer emergency rating of 561 MV | 138
220742 | 93101 | 157891 | NWE | SD | Line - Huron 'B' Tap 115 kV - Huron 115 kV - Huron West Park 115 kV Rebuild | Huron - Huron West Park 115 kV Ckt 1 Rebuild (NWE) | Economic |  | 2025-01-01 | 2023-12-15 | 2023 ITP |  |  | 0 | 11554745 |  | NTC - Commitment Window | 652515 | HURON | 660003 | HURON WEST PARK | Rebuild 10.4 mile Ckt 1 line from Huron 115 kV substation to Huron West Park 115 kV substation | 115
220742 | 93101 | 157892 | NWE | SD | Line - Huron 'B' Tap 115 kV - Huron 115 kV - Huron West Park 115 kV Rebuild | Huron - Huron 'B' Tap 115 kV Ckt 1 Rebuild (NWE) | Economic |  | 2025-01-01 | 2023-12-15 | 2023 ITP |  |  | 0 | 207080 |  | NTC - Commitment Window | 652515 | HURON | 660009 | WEST PARK B TAP | Rebuild 0.2 mile Ckt 1 line from Huron 115 kV substation to Huron 'B' Tap 115 kV substation | 115
220738 | 81701 | 157897 | OGE | OK | Line - Anadarko - Gracemont 138 kV double Ckt 2 & 3 | Anadarko - Gracemont 138kV Ckt 2 New Line (OGE) | Economic |  | 2023-11-14 | 2023-12-15 | 2023 ITP |  |  | 0 | 22081965 |  | NTC-C Project Estimate Window |  |  |  |  | Build new 15-mile 138 kV Ckt 2 line from Anadarko 138 kV substation to Gracemont 138 kV substation as a double circuit to achieve a summer emergency rating of 478 MVA. | 345 | 15
220754 | 81701 | 157899 | WFEC | OK | Line - Anadarko - Gracemont 138 kV double Ckt 2 & 3 | Anadarko - Gracemont 138kV Ckt 2 New Line (WFEC) | Economic |  | 2023-11-14 | 2023-12-15 | 2023 ITP |  |  | 0 | 19500000 |  | NTC-C Project Estimate Window |  |  |  |  | Build new 15-mile 138 kV Ckt 2 line from Anadarko 138 kV substation to Gracemont 138 kV substation as a double circuit to achieve a summer emergency rating of 478 MVA. | 345 | 15
220748 | 93171 | 157946 | WAPA | NE | Line - Gavins Point 115 kV - Yankton Junction 115 kV Rebuild | Gavins Point - Yankton Junction 115 kV Ckt 1 Rebuild (WAPA) | Economic |  | 2025-01-01 | 2023-12-15 | 2023 ITP |  |  | 0 | 4000000 |  | NTC - Commitment Window | 652511 | GAVINS POINT | 660006 | YANKON JCT | Rebuild 4 miles of 115 kV Ckt 1 line from Gavins Point 115 kV substation to Yankton Junction 115 kV substation and upgrade any necessary terminal equipment to achieve a summer emergency rating of 239 MVA. | 115
220748 | 93171 | 157948 | WAPA | NE | Line - Gavins Point 115 kV - Yankton Junction 115 kV Rebuild | Gavins Point 115 kV Terminal Upgrade | Economic |  | 2025-01-01 | 2023-12-15 | 2023 ITP |  |  | 0 | 264000 |  | NTC - Commitment Window | 652511 | GAVINS POINT |  |  | Upgrade any necessary terminal equipment at Gavin Point 115 kV substation on the Gavins Point to Yankton Junction 115 kV line to achieve a summer emergency rating of 239 MVA. | 115
220742 | 93171 | 157949 | NWE | SD | Line - Gavins Point 115 kV - Yankton Junction 115 kV Rebuild | Yankton Junction 115 kV Ckt 1 Terminal Upgrade | Economic |  | 2025-01-01 | 2023-12-15 | 2023 ITP |  |  | 0 | 393298 |  | NTC - Commitment Window | 660006 | YANKON JCT |  |  | Upgrade any necessary terminal equipment at Yankton Junction 115 kV substation on the Yankton Junction to Gavins Point 115 kV line to achieve a summer emergency rating of 239 MVA. | 115
220747 | 94080 | 158019 | BEPC | ND | Device - Groton 345 kV Reactor | Groton 345 kV Reactor | Regional Reliability |  | 2024-04-01 | 2023-12-15 | 2023 ITP |  |  | 0 | 5162152 |  | NTC - Commitment Window |  |  |  |  | Install 2nd 68 MVAR reactor at Groton 345 kV substation | 345
220746 | 92970 | 158045 | EM | KS | Device - Craig 161 kV Breaker | Craig 161 kV Breaker #6 | Regional Reliability |  | 2024-06-01 | 2023-12-15 | 2023 ITP |  |  | 0 | 609492 |  | NTC - Commitment Window | 542978 | CRAIG 161 KV |  |  | Upgrade breaker R1-2 at Craig 161 kV substation with 63 kA breakers. | 161
220744 | 92993 | 158445 | OPPD | NE | XFR - Fremont 115/69 kV & Sub 976 Terminal Upgrade | Sub 976 69 kV Terminal Equipment | Economic |  | 2025-01-01 | 2023-12-15 | 2023 ITP |  |  | 0 | 165695 |  | NTC - Commitment Window |  |  |  |  | Install 69 kV terminal equipment at Sub 976 to support a new 115/69 kV transformer | 69
220749 | 93900 | 158452 | EKC | KS | Sub - Benton 345 kV - Wichita 345 kV Terminal Upgrades | Benton 345 kV Terminal Upgrade | Economic |  | 2023-11-14 | 2023-12-15 | 2023 ITP |  |  | 0 | 3415129 |  | NTC - Commitment Window |  |  |  |  | Upgrade any necessary terminal equipment at Benton 345 kV substation on the Benton to Wichita 345 kV line to achieve a summer emergency rating of 1119 MVA. | 345
220749 | 93900 | 158453 | EKC | KS | Sub - Benton 345 kV - Wichita 345 kV Terminal Upgrades | Wichita 345 kV Terminal Upgrade | Economic |  | 2023-11-14 | 2023-12-15 | 2023 ITP |  |  | 0 | 3415129 |  | NTC - Commitment Window |  |  |  |  | Upgrade any necessary terminal equipment at Wichita 345 kV substation on the Wichita to Benton 345 kV line to achieve a summer emergency rating of 1119 MVA. | 345
220738 | 94010 | 158573 | OGE | OK | Line - Matthewson 345 kV - Redbud 345 kV | Redbud 345 kV Terminal Upgrade | Economic |  | 2025-01-01 | 2023-12-15 | 2023 ITP |  |  | 0 | 3415129 |  | NTC-C Project Estimate Window | 514908 | ARCADIA 345 |  |  | Install any necessary terminal equipment at Redbud 345 kV substation to support a new line from Redbud 345 kV substation to Matthewson 345 kV substation with a summer emergency rating of 1792 MVA. | 345
220738 | 94010 | 158574 | OGE | OK | Line - Matthewson 345 kV - Redbud 345 kV | Matthewson 345 kV Terminal Equipment #2 | Economic |  | 2025-01-01 | 2023-12-15 | 2023 ITP |  |  | 0 | 3415129 |  | NTC-C Project Estimate Window | 515497 | MATHEWSON 345 |  |  | Install any necessary terminal equipment at Matthewson 345 kV substation to support a new line from Matthewson 345 kV substation to Redbud 345 kV substation with a summer emergency rating of 1792 MVA. | 345
220761 | 94067 | 158629 | SPS | TX | XFR-Potter County 345/230 kV Ckt1 & Ckt2 | Potter County 345/230 kV Transformer Ckt 2 (345 kV) | Economic |  | 2023-11-14 | 2023-12-15 | 2023 ITP |  |  | 0 | 7500000 |  | NTC-C Project Estimate Window | 523961 | Potter County Interchange 345 kV | 523959 | Potter County Interchange 230 kV | Install new 345/230 transformer at Potter County 345 kV substation CKt2 | 345
220761 | 94067 | 158630 | SPS | TX | XFR-Potter County 345/230 kV Ckt1 & Ckt2 | Potter County 345/230 kV Transformer Ckt 1 (230 kV) | Economic |  | 2023-11-14 | 2023-12-15 | 2023 ITP |  |  | 0 | 7500000 |  | NTC-C Project Estimate Window | 523961 | Potter County Interchange 345 kV | 523959 | Potter County Interchange 230 kV | Expand and replace 230 kV terminal equipment at Potter County substation to support the replacement of the 345/230 kV transformer ckt 1 and the new 345/230 kV transformer ckt 2 | 230
220761 | 94067 | 158631 | SPS | TX | XFR-Potter County 345/230 kV Ckt1 & Ckt2 | Potter County 345/230 kV Transformer Ckt 1 | Economic |  | 2023-11-14 | 2023-12-15 | 2023 ITP |  |  | 0 | 7500000 |  | NTC-C Project Estimate Window | 523961 | Potter County Interchange 345 kV | 523959 | Potter County Interchange 230 kV | Replace existing 345/230 kV transformer at Potter County substation ckt 1 | 230
220761 | 94067 | 158632 | SPS | TX | XFR-Potter County 345/230 kV Ckt1 & Ckt2 | Potter County 345 kV Substation Expansion | Economic |  | 2023-11-14 | 2023-12-15 | 2023 ITP |  |  | 0 | 7500000 |  | NTC-C Project Estimate Window | 523961 | Potter County Interchange 345 kV | 523959 | Potter County Interchange 230 kV | Expand and replace 345 kV terminal equipment at Potter County substation to support the replacement of the 345/230 kV transformer ckt 1 and the new 345/230 kV transformer ckt 2 | 345
220738 | 81701 | 158637 | OGE | OK | Line - Anadarko - Gracemont 138 kV double Ckt 2 & 3 | Gracemont 138 kV Ckt 3 Terminal Equipment | Economic |  | 2023-11-14 | 2023-12-15 | 2023 ITP |  |  | 0 | 2171478 |  | NTC-C Project Estimate Window | 515802 | Gracemont 138 kV |  |  | Install any necessary terminal equipment at Gracemont 138 kV substation to support a third 138 kV line from Anadarko to Gracemont to achieve a summer emergency rating of 478 MVA | 138/138 | 15
220754 | 81701 | 158638 | WFEC | OK | Line - Anadarko - Gracemont 138 kV double Ckt 2 & 3 | Anadarko 138 kV Ckt 3 Terminal Equipment | Economic |  | 2023-11-14 | 2023-12-15 | 2023 ITP |  |  | 0 | 2500000 |  | NTC-C Project Estimate Window | 520814 | ANADARKO |  |  | Install any necessary terminal equipment at Anadarko 138 kV to support a third 138 kV line from Anadarko to Gracemont to achieve a summer emergency rating of 478 MVA | 138/138 | 15
220749 | 94153 | 158653 | EKC | KS | XFR - 87th St. 345/115 kV. Ckt 2 | 87th St. Terminal Equipment Ckt 2 | Economic |  | 2025-01-01 | 2023-12-15 | 2023 ITP |  |  | 0 | 5100000 |  | NTC - Commitment Window |  |  |  |  | Install 345 kV terminal equipment at 87th street ckt 2 | 345/115
220749 | 94153 | 158654 | EKC | KS | XFR - 87th St. 345/115 kV. Ckt 2 | 87th St. 345/115 kV Transformer | Economic |  | 2025-01-01 | 2023-12-15 | 2023 ITP |  |  | 0 | 5100000 |  | NTC - Commitment Window |  |  |  |  | Install new 345/115 kV Transformer on ckt 2 at 87th St. | 345/115
210562 | 81628 | 122602 | WAPA | ND// | Sub - Jamestown 230 kV Redundant Bus Tie | Jamestown 230 kV Redundant Bus Tie | Generation Interconnection | 2024-12-31 |  | 2020-06-10 | DISIS-2016-001 | 1510000 | 2020 | 1666757.4639 | 1510000 |  | On Schedule < 4 |  |  |  |  | Add a redundant bus to Jamestown 230 kV substation to mitigate for a fault and breaker fail of CB 9182.
210611 | 81474 | 112307 | AEP | OK/ | Sub - Oklaunion 345 kV Capacitive Reactive Power Support | Oklaunion 345 kV Capacitive Reactive Power Support | Generation Interconnection | 2025-02-12 | 2023-05-15 | 2021-05-17 | DISIS-2016-002 | 9453182 | 2021 | 10180043.025 | 25800000 |  | Delay - Mitigation |  |  |  |  | Install +200Mvar Capacitor Bank(s) at the Oklaunion 345kV substation.
210609 | 81591 | 122537 | OGE | OK | Device - Border 345kV Capacitive Reactive Support | Border 345kV Capacitive Reactive Support | Generation Interconnection | 2025-04-20 | 2023-04-20 | 2021-05-17 | DISIS-2016-002 | 3996000 | 2021 | 4303254.9175 | 3996000 |  | Delay - Mitigation |  |  |  |  | Install + 275 MVAR Capacitor Bank(s) at Border 345 kV.
210564 | 81489 | 122600 | OGE | OK | Sub - Gracemont - Lawton East Side 345 kV | Gracemont - Lawton East Side 345 kV Substation GEN-2016-091 (NU) (OKGE) | Generation Interconnection | 2021-12-31 | 2020-09-22 | 2020-08-11 | DISIS-2016-002 | 10000 | 2020 | 10250 | 10000 |  | In Service |  |  |  |  | Relay settings upgrades
210630 | 81490 | 122601 | OGE | OK | Multi - Gracemont - Lawton East Side 345 kV | Gracemont - Lawton East Side 345 kV Terminal Equipment | Generation Interconnection | 2023-12-31 | 2023-12-31 | 2022-01-31 | DISIS-2016-002 |  |  | 0 | 10000 |  | On Schedule < 4 |  |  |  |  | Change relay settings to accommodate the construction of the GEN-2016-095 wind farm.
210565 | 81481 | 122622 | EKC | KS | Multi - West Gardner 345 kV, Swissvale 345 kV | Swissvale 345 kV Substation Upgrades | Generation Interconnection | 2025-12-31 |  | 2020-08-28 | DISIS-2016-002 | 139825 | 2020 | 154340.6373 | 136893 |  | On Schedule < 4 |  |  |  |  | Replace one control panel and review and/or apply new relay settings at the Swissvale substation.
210606 | 81636 | 122637 | EKC | KS | Spring Creek to Sooner 345kV GEN-2016-119 Interconnection Costs | Spring Creek345 kV (GEN-2016-119) | Generation Interconnection |  | 2025-03-15 | 2021-03-04 | DISIS-2016-002 | 16624 | 2021 | 17902.2297 | 16624.73 |  | On Schedule < 4 |  |  |  |  | Review and/or apply relay protection settings at the Spring Creek substation.
210631 | 81657 | 122667 | OGE | OK | Multi - Riverside 345 kV Substation | Redbud 345kV | Generation Interconnection | 2025-12-31 | 2025-12-31 | 2022-01-31 | DISIS-2016-002 |  |  | 0 | 15000 |  | On Schedule < 4 |  |  |  |  | Change relay settings to accommodate the Interconnection of the States Edge 1 Wind Farm.
210612 | 81660 | 122674 | OGE | OK | Viola 345kV GEN-2016-153 Interconnection Costs | Renfrow 345 kV Relay Setting Adjustment | Generation Interconnection | 2023-10-01 | 2023-10-01 | 2021-06-08 | DISIS-2016-002 | 15000 | 2021 | 15759.375 | 15000 |  | On Schedule < 4 |  |  |  |  | At the existing Renfrow 345 kV substation, update relay settings to accommodate new protection settings.
210677 | 81802 | 143117 | OGE | KS | Multi - Buffalo Flats - Degrasse - Thistle 345 kV Sub | Degrasse345 kV Substation | Generation Interconnection | 2024-06-01 | 2024-07-12 | 2022-06-22 | DISIS-2017-001 |  |  | 0 | 30000 |  | On Schedule < 4 |  |  |  |  | Update relay settings at Degrasse 345 kV Substation.
210676 | 81802 | 143118 | EKC | KS | Multi - Buffalo Flats - Degrasse - Thistle 345 kV Sub | Buffalo Flats 345 kV | Generation Interconnection |  | 2024-07-12 | 2022-06-22 | DISIS-2017-001 |  |  | 0 | 13299 |  | In Service |  |  |  |  | Review relay settings and apply adjusted settings at Buffalo Flats 345 kV substation.
210704 | 81854 | 143125 | OGE | KS/ | Sub - Renfrow 345 kV | Renfrow 345 kV Substation | Generation Interconnection | 2024-05-08 | 2024-10-31 | 2022-10-16 | DISIS-2017-001 |  |  | 0 | 20000 |  | On Schedule < 4 |  |  |  |  | Update relay settings and records at Renfrow 345 kV Substation for the Renfrow to Viola 345 kV line for interconnection of GEN-2017-086 at Viola 345 kV.
210643 | 81773 | 143127 | OGE | OK | Sub - Chisholm - Gracemont 345 kV | Gracemont 345 kV | Generation Interconnection | 2022-09-01 | 2022-09-01 | 2022-02-25 | DISIS-2017-001 | 15000 | 2022 | 15000 | 15000 |  | On Schedule < 4 |  |  |  |  | At the existing Gracmont 345 kV substation, update relay settings to accommodate new protection settings.
210717 | 81790 | 143151 | EKC | OK | Elm Creek-Summit 345 kV | Summit 345 kV GEN-2017-004 Interconnection (Non-Shared Network Upgrade (NU)) (EKC) | Generation Interconnection | 2025-07-18 | 2025-07-18 | 2022-12-13 | DISIS-2017-001 |  |  | 0 | 24937 |  | On Schedule < 4 |  |  |  |  | Review relay settings and apply adjusted settings at Summit 345kV substation.
200477 | 51254 | 71963 | NPPD | NE | Multi - Sheldon - Monolith 115 kV | Monolith 345 kV Substation | Regional Reliability | 2024-10-01 | 2020-12-01 | 2018-02-21 | DPA-2016-December-703 | 20279796 | 2022 | 21306460.6725 | 24319368 |  | Delay - Mitigation |  |  |  |  | Tap the existing 345 kV line from Moore to Cooper to construct the new Monolith substation approximately 1 mile from Moore. Install any necessary 345 kV terminal equipment. | 345 | 0.2
200477 | 51254 | 71964 | NPPD | NE | Multi - Sheldon - Monolith 115 kV | Monolith 345/115 kV Transformer #1 | Regional Reliability | 2024-10-01 | 2020-12-01 | 2018-02-21 | DPA-2016-December-703 | 5468352 | 2022 | 5745187.32 | 5468352 |  | Delay - Mitigation Window |  |  |  |  | Add a new 345/115 kV ckt 1 transformer at Monolith substation. | 345/115
200477 | 51254 | 71965 | NPPD | NE | Multi - Sheldon - Monolith 115 kV | Monolith 345/115 kV Transformer #2 | Regional Reliability | 2024-10-01 | 2020-12-01 | 2018-02-21 | DPA-2016-December-703 | 5179657 | 2018 | 6006814.1408 | 5468352 |  | Delay - Mitigation Window |  |  |  |  | Add a new 345/115 kV ckt 2 transformer at Monolith substation. | 345/115
210682 | 51254 | 71966 | NPPD | NE | Multi - Sheldon - Monolith 115 kV | Monolith 115 kV Substation Upgrades | Regional Reliability | 2023-06-01 | 2020-12-01 | 2022-08-12 | DPA-2016-December-703 | 13329402 | 2022 | 13662637.05 | 18617823 |  | Delay - Mitigation |  |  |  |  | Re-terminate Firth - Sheldon 115 kV line at Monolith 115 kV sub rather than Sheldon 115 kV sub. Install any necessary 115 kV terminal equipment. | 115 | 2.6
210682 | 51254 | 71967 | NPPD | NE | Multi - Sheldon - Monolith 115 kV | Sheldon - Monolith 115 kV Ckt 1 New Line | Regional Reliability | 2024-10-01 | 2020-12-01 | 2022-08-12 | DPA-2016-December-703 | 1605462 | 2022 | 1686738.5137 | 1173160 |  | Delay - Mitigation |  |  |  |  | Re-terminate LES SW 7th & Bennet - Sheldon 115 kV line at Monolith 115 kV sub rather than Sheldon 115 kV sub. Construct new 115 kV line interconnections into Monolith substation. | 115 | 1
200477 | 51254 | 71968 | NPPD | NE | Multi - Sheldon - Monolith 115 kV | Sheldon 115 kV Terminal Upgrades | Regional Reliability | 2024-10-01 | 2020-12-01 | 2018-02-21 | DPA-2016-December-703 | 5656017 | 2022 | 5942352.8606 | 5428037 |  | Delay - Mitigation |  |  |  |  | Upgrade all terminal equipment in northern half of Sheldon 115 kV substation to achieve Sheldon - Monolith 115 kV line rating of no less than 400/400 MVA | 115
200482 | 51280 | 72011 | WFEC | OK | Device - Dover SW 69 kV Cap Bank | Dover SW 69 kV Cap Bank | Regional Reliability | 2022-06-30 | 2019-06-01 | 2018-02-27 | DPA-2017-August-767-774-776 | 500000 | 2018 | 551906.445 | 813590 |  | Complete | 520881 | DOVER SW |  |  | Add new 14.4 MVAR capacitor bank at Dover SW 69 kV. | 69
200482 | 51281 | 72012 | WFEC | OK | Device - Cherokee SW 69 kV Cap Bank | Cherokee SW 69 kV Cap Bank | Regional Reliability | 2027-11-30 | 2018-06-01 | 2018-02-27 | DPA-2017-August-767-774-776 | 1000000 | 2018 | 1159693.42 | 1000000 |  | Delay - Mitigation | 520851 | CHEROKEE SW |  |  | Add new 28.8 MVAR capacitor bank at Cherokee SW 69 kV. | 69
210483 | 51282 | 72013 | WFEC | OK | Multi - Park Community - Sunshine 138 kV | Park Community 138 kV Substation | Regional Reliability | 2020-06-25 | 2018-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 2000000 | 2018 | 2101250 | 2000000 |  | Complete |  |  |  |  | New Park Community 138 kV substation with 3-terminal flat bus. | 138
210483 | 51282 | 72014 | WFEC | OK | Multi - Park Community - Sunshine 138 kV | Omega - Park Community 138 kV Ckt 1 New Line | Regional Reliability | 2019-09-16 | 2018-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 4700000 | 2018 | 4817500 | 4700000 |  | Closed Out | 520964 | KINGFISHER |  |  | Construct new 9.4 mile 138 kV line from Omega - Park Community. Complete necessary terminal upgrades at Omega. | 138 | 9.4
210483 | 51282 | 72015 | WFEC | OK | Multi - Park Community - Sunshine 138 kV | Omega - Watonga SW 138 kV Ckt 1 Voltage Conversion | Regional Reliability | 2023-05-31 | 2019-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 7950000 | 2018 | 8994695.2695 | 12428000 |  | Complete | 520964 | KINGFISHER | 521090 | WATONGA SW | Convert 7.9 mile 69 kV line from Omega - Watonga SW to 138 kV. Complete necessary terminal upgrades at Watonga SW. | 138 |  | 7.9 | 7.9
210669 | 51282 | 72016 | WFEC | OK | Multi - Park Community - Sunshine 138 kV | Okeene - Watonga SW 138 kV Ckt 1 Voltage Conversion | Regional Reliability | 2022-08-09 | 2019-06-01 | 2022-04-28 | DPA-2017-August-767-774-776 | 8600000 | 2018 | 9492790.854 | 7520000 |  | Complete | 521016 | OKEENE | 521090 | WATONGA SW | Convert 17.2 mile 69 kV line from Okeene - Watonga SW to 138 kV. Complete necessary terminal upgrades at Okeene. | 138 |  | 13.5 | 13.5
210483 | 51282 | 72018 | WFEC | OK | Multi - Park Community - Sunshine 138 kV | Calumet - Watonga SW 138 kV Ckt 1 Voltage Conversion | Regional Reliability | 2024-11-29 | 2019-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 8400000 | 2018 | 9741424.728 | 8400000 |  | Delay - Mitigation | 520839 | CALUMET | 521090 | WATONGA SW | Convert 16.8 mile 69 kV line from Calumet - Watonga SW to 138 kV. | 138 |  | 16.8 | 16.8
210483 | 51282 | 72019 | WFEC | OK | Multi - Park Community - Sunshine 138 kV | Calumet - Concho 138 kV Ckt 1 Voltage Conversion | Regional Reliability | 2024-11-30 | 2020-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 1250000 | 2018 | 1449616.775 | 2150000 |  | Delay - Mitigation | 520839 | CALUMET | 520865 | CONCHO | Convert 9.0 mile 69 kV line from Calumet - Concho to 138 kV. Complete necessary terminal upgrades at Concho. | 138 |  |  | 9
210483 | 51282 | 72020 | WFEC | OK | Multi - Park Community - Sunshine 138 kV | Calumet - Cana 138 kV Ckt 1 Voltage Conversion | Regional Reliability | 2025-04-30 | 2020-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 4550000 | 2018 | 5276605.061 | 4550000 |  | Delay - Mitigation | 520839 | CALUMET | 520502 |  | Convert 9.1 mile 69 kV line from Calumet - Cana to 138 kV. Complete necessary terminal upgrades at Cana. | 138 |  | 9.1 | 9.1
210483 | 51282 | 72021 | WFEC | OK | Multi - Park Community - Sunshine 138 kV | Calumet 138 kV Substation | Regional Reliability | 2024-11-30 | 2019-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 4000000 | 2018 | 4638773.68 | 4000000 |  | Delay - Mitigation | 520839 | CALUMET |  |  | New Calumet 138 kV substation with 4-terminal ring bus. | 138
210483 | 51282 | 72022 | WFEC | OK | Multi - Park Community - Sunshine 138 kV | Cana - El Reno Jct 138 kV Ckt 1 Voltage Conversion | Regional Reliability | 2025-06-30 | 2019-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 5650000 | 2018 | 6552267.823 | 5650000 |  | Delay - Mitigation | 520502 |  | 520899 | EL RENO | Convert 3.3 mile 69 kV line from Cana - El Reno Jct to 138 kV. Complete necessary terminal upgrades at El Reno Jct. | 138 |  | 3.3 | 3.3
210483 | 51282 | 72023 | WFEC | OK | Multi - Park Community - Sunshine 138 kV | El Reno - El Reno Jct 138 kV Ckt 1 Voltage Conversion | Regional Reliability | 2026-06-01 | 2019-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 4000000 | 2018 | 4638773.68 | 3500000 |  | Delay - Mitigation | 520892 | EL RENO SW | 520899 | EL RENO | Convert 6.5 mile 69 kV line from El Reno - El Reno Jct to 138 kV. Complete necessary terminal upgrades at El Reno. | 138
210483 | 51282 | 72024 | WFEC | OK | Multi - Park Community - Sunshine 138 kV | El Reno - Mustang 138 kV Ckt 1 Voltage Conversion | Regional Reliability | 2024-04-30 | 2019-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 4000000 | 2018 | 4638773.68 | 12155000 |  | Delay - Mitigation | 520892 | EL RENO SW | 520412 |  | Convert 21.3 mile 69 kV line from El Reno - Mustang to 138 kV. Complete necessary terminal upgrades at Mustang. | 138 |  | 21.3 | 21.3
210483 | 51282 | 72025 | WFEC | OK | Multi - Park Community - Sunshine 138 kV | Mustang - Sara Road 138 kV Ckt 1 Voltage Conversion | Regional Reliability | 2023-04-30 | 2019-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 10650000 | 2018 | 12049497.4365 | 1172000 |  | Delay - Mitigation | 520412 |  | 521005 | MUSTANG | Convert 2.1 mile 69 kV line from Mustang - Sara Road to 138 kV. Complete necessary terminal upgrades at Sara Road. | 138 |  | 2.1 | 2.1
210483 | 51282 | 72026 | WFEC | OK | Multi - Park Community - Sunshine 138 kV | Sara Road - Sunshine 138 kV Ckt 1 Voltage Conversion | Regional Reliability | 2024-05-30 | 2019-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 1050000 | 2018 | 1217678.091 | 10380000 |  | Delay - Mitigation | 521005 | MUSTANG | 521059 | SUNSHINE CANYON | Convert 10.0 mile 69 kV line from Sara Road - Sunshine to 138 kV. | 138 |  | 10 | 10
210483 | 51282 | 72027 | WFEC | OK | Multi - Park Community - Sunshine 138 kV | Cogar - El Reno Jct 138 kV Ckt 1 Voltage Conversion | Regional Reliability | 2025-11-30 | 2020-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 5000000 | 2018 | 5798467.1 | 5300000 |  | Delay - Mitigation | 520859 | COGAR | 520899 | EL RENO | Convert 10.6 mile 69 kV line from Cogar - El Reno Jct to 138 kV. | 138 |  | 10.6 | 10.6
210483 | 51282 | 72029 | WFEC | OK | Multi - Park Community - Sunshine 138 kV | Kingfisher SW - Park Community 138 kV Ckt 1 New Line | Regional Reliability | 2023-05-31 | 2018-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 4500000 | 2018 | 5091336.945 | 6141513 | 5762250.69 | Complete |  |  |  |  | Construct new 9.0 mile 138 kV line from Kingfisher SW - Park Community. | 138 | 9
210483 | 51282 | 72030 | WFEC | OK | Multi - Park Community - Sunshine 138 kV | Kingfisher SW 138 kV Substation | Regional Reliability | 2023-05-31 | 2018-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 4000000 | 2018 | 4525632.84 | 4975000 |  | Delay - Mitigation |  |  |  |  | Tap the East Kingfisher - Reeding 138 kV line and construct new Kingfisher SW 138 kV substation with 4-terminal ring bus. | 138
210483 | 51282 | 72031 | WFEC | OK | Multi - Park Community - Sunshine 138 kV | Concho - Kingfisher SW 138 kV Ckt 1 New Line | Regional Reliability | 2023-11-30 | 2019-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 4250000 | 2018 | 4808484.8925 | 4250000 |  | Delay - Mitigation | 520865 | CONCHO |  |  | Construct new 8.5 mile 138 kV line from Concho - Kingfisher SW. | 138 | 8.5
210489 | 51327 | 82111 | WFEC | OK | Line - Cogar - OU SW 138 kV | Cogar - Cleveland Jct 138 kV Ckt 1 Voltage Conversion | Regional Reliability | 2025-07-01 | 2018-12-31 | 2018-07-09 | DPA-2017-December-815 | 10000000 | 2018 | 11596934.2 | 10000000 |  | Delay - Mitigation | 520859 | COGAR | 520509 |  | Convert 12.0 mile 69 kV line from Cogar - Cleveland Junction to 138 kV. | 138
210489 | 51327 | 82112 | WFEC | OK | Line - Cogar - OU SW 138 kV | Cleveland Jct - Amber Tap 138 kV Ckt 1 Voltage Conversion | Regional Reliability | 2027-04-30 | 2018-12-31 | 2018-07-09 | DPA-2017-December-815 | 6900000 | 2018 | 8001884.598 | 6900000 |  | Delay - Mitigation | 520509 |  |  |  | Convert 13.8 mile 69 kV line from Cleveland Jct - Amber Tap to 138 kV. | 138
210489 | 51327 | 82113 | WFEC | OK | Line - Cogar - OU SW 138 kV | Amber Tap - Blanchard 138 kV Ckt 1 Voltage Conversion | Regional Reliability | 2021-12-30 | 2018-12-31 | 2018-07-09 | DPA-2017-December-815 | 7600000 | 2018 | 8184368.712 | 7019000 |  | Complete |  |  | 520828 | BLANCHARD | Convert 15.2 mile 69 kV line from Amber Tap - Blanchard to 138 kV. | 138
210489 | 51327 | 82114 | WFEC | OK | Line - Cogar - OU SW 138 kV | Blanchard - OU SW 138 kV Ckt 1 Voltage Conversion | Regional Reliability | 2024-12-31 | 2018-12-31 | 2018-07-09 | DPA-2017-December-815 | 300000 | 2018 | 347908.026 | 360000 |  | Delay - Mitigation | 520828 | BLANCHARD | 521104 | OU SWITCH 4 | Convert 2.1 mile 69 kV line from Blanchard - OU SW to 138 kV. | 138
210489 | 51327 | 82115 | WFEC | OK | Line - Cogar - OU SW 138 kV | Cleveland Jct - Anadarko 138 kV Ckt 1 Voltage Conversion | Regional Reliability | 2024-12-31 | 2018-12-31 | 2018-07-09 | DPA-2017-December-815 | 6300000 | 2018 | 7306068.546 | 6300000 |  | Delay - Mitigation | 520509 |  | 520814 | ANADARKO | Convert 11.1 miles of double circuit 69 kV line from Cleveland Junction - Anadarko to single circuit 138 kV. | 138
210507 | 61347 | 92153 | SPS | NM | Multi - China Draw - Road Runner 345 kV | Bopco - Road Runner 345 kV Ckt 1 New Line | Regional Reliability | 2021-11-15 | 2018-12-01 | 2018-12-11 | DPA-2017-November-808 | 29927758 | 2019 | 31442850.7488 | 36990694 |  | Closed Out |  |  | 528027 | Road Runner 345 kV | Build new 21 mile 345 kV line from Bopco to Road Runner. | 345 | 21
210507 | 61347 | 92154 | SPS | NM | Multi - China Draw - Road Runner 345 kV | Bopco - China Draw 345 kV Ckt 1 New Line | Regional Reliability | 2021-11-15 | 2021-12-01 | 2018-12-11 | DPA-2017-November-808 | 30496976 | 2019 | 32040885.41 | 32450586 |  | Closed Out |  |  | 528223 |  | Build new 19 mile 345 kV line from Bopco to China Draw. | 345 | 19
210507 | 61347 | 102153 | SPS | NM | Multi - China Draw - Road Runner 345 kV | Bopco 345/115 kV Ckt 1 Transformer | Regional Reliability | 2021-11-15 | 2018-12-01 | 2018-12-11 | DPA-2017-November-808 | 6205015 | 2019 | 6519143.8844 | 5730720 |  | Closed Out |  |  | 528020 |  | Construct 345/115 kV transformer at Bopco substation. | 345/115
210507 | 61347 | 102154 | SPS | NM | Multi - China Draw - Road Runner 345 kV | Bopco 345/115 kV Ckt 2 Transformer | Regional Reliability | 2021-11-15 | 2021-12-01 | 2018-12-11 | DPA-2017-November-808 | 6122043 | 2019 | 6431971.4269 | 6086681 |  | Closed Out |  |  | 528020 |  | Construct second 345/115 kV transformer at Bopco substation. | 345/115
210507 | 61347 | 102157 | SPS | NM | Multi - China Draw - Road Runner 345 kV | Bopco 345 kV Substation | Regional Reliability | 2021-11-15 | 2018-12-01 | 2018-12-11 | DPA-2017-November-808 | 5153574 | 2019 | 5414473.6837 | 6461353 |  | Closed Out |  |  |  |  | Build 345 kV portion of new 345/115 kV Bopco substation. | 345
210507 | 61347 | 102158 | SPS | NM | Multi - China Draw - Road Runner 345 kV | Bopco 115 kV Substation | Regional Reliability | 2020-11-15 | 2018-12-01 | 2018-12-11 | DPA-2017-November-808 | 11741936 | 2019 | 12035484.4 | 15125912 |  | Closed Out |  |  |  |  | Build 115 kV portion of new 345/115 kV Bopco substation. This includes work to reterminate the Wood Draw - Red Bluff 115 kV line into the new substation. | 115
210560 | 81614 | 122570 | BEPC | ND | Multi - Neset - New Town 230 kV | Neset - Northshore 230 kV Ckt 1 | Regional Reliability | 2022-10-20 | 2019-06-01 | 2020-06-10 | DPA-2018-August-918 | 28246170.48 | 2023 | 28246170.48 | 28246170.48 | 28246170.48 | Closed Out | 659138 | Neset 230 kV Bus |  |  | Build new 28 mile 230kV line from Neset to Northshore. | 230 | 30
210559 | 81614 | 122571 | MWE | ND | Multi - Neset - New Town 230 kV | Northshore - New Town 115 kV Ckt 1 | Regional Reliability | 2021-09-05 | 2019-06-01 | 2020-06-10 | DPA-2018-August-918 | 19235485 | 2023 | 19235485 | 19262151 | 19262150 | Complete |  |  |  |  | Build new 20 mile 115 kV line from Northshore to New Town. | 115 | 20.5
210560 | 81614 | 122572 | BEPC | ND | Multi - Neset - New Town 230 kV | Northshore 230/115 kV Transformer | Regional Reliability | 2022-10-20 | 2019-06-01 | 2020-06-10 | DPA-2018-August-918 | 3831922 | 2023 | 3831922 | 3831922 | 3831922 | Closed Out |  |  |  |  | Build new 230/115 kV Transformer at Northshore substation | 230/115
210560 | 81614 | 122575 | BEPC | ND/ | Multi - Neset - New Town 230 kV | Northshore 230 kV Substation | Regional Reliability | 2023-01-18 | 2019-06-01 | 2020-06-10 | DPA-2018-August-918 | 12877495 | 2023 | 12877495 | 12877495 | 12877495 | Closed Out |  |  |  |  | Build new Northshore 230/115 kV Substation to replace existing switch | 230/115
210548 | 71348 | 102163 | OPPD | NE | Multi - S1361 | S1209 - S1231 Ckt 2 161 kV Reconductor | Regional Reliability | 2024-05-15 | 2021-06-01 | 2019-12-13 | DPA-2018-February-841 | 3647471 | 2019 | 4126778.6351 | 3647471 |  | Delay - Mitigation | 646209 | Sub 1209 | 646231 | Sub 1231 | Reconductor 3.3 miles of S1209 - S1231 161 kV Ckt 2 | 161 |  | 3.3
210505 | 71352 | 102172 | WFEC | OK | Device - Clear Creek Tap 69 kV Cap Bank | Clear Creek Tap 69 kV Cap Bank | Regional Reliability | 2024-01-31 | 2019-12-01 | 2018-12-06 | DPA-2018-June-902 | 717209 | 2019 | 811456.1509 | 887000 |  | Delay - Mitigation |  |  |  |  | New cap bank(s) totaling 18 MVAR at Clear Creek Tap 69kV substation. | 69
210600 | 91885 | 143178 | OPPD | NE | Multi - S3456 - S3458 345 kV, S3455 - S3740 345 kV, S1260 - S1362 161 kV | S3456 to S3458 345 kV Ckt 1 Terminal Upgrades | Regional Reliability | 2024-04-01 | 2024-04-01 | 2021-02-16 | DPA-2018-October-949 | 100000 | 2021 | 107689.062 | 100000 |  | On Schedule < 4 | 645456 | Sub 3456 | 645458 | Sub 3458 (Neb Cty) | The upgrade disconnect switch and associated jumpers on S3456 to S3458 345 kV line to achieve at least a 981 MVA summer emergency rating. | 345
210600 | 91885 | 143179 | OPPD | NE | Multi - S3456 - S3458 345 kV, S3455 - S3740 345 kV, S1260 - S1362 161 kV | S3455 to S3740 345 kV CKT1 Rebuild | Regional Reliability | 2024-04-01 | 2024-04-01 | 2021-02-16 | DPA-2018-October-949 | 600000 | 2021 | 646134.372 | 633400 |  | On Schedule < 4 | 645455 | Sub 3455 | 645740 | Sub 3740 | Replace structures to increase clearance on S3455 to S3740 345 kV CKT1 (approximately 6-7 structures) to achieve a 1112 MVA summer emergency rating. | 345
210552 | 81654 | 122661 | NPPD | NE | XFR-Riverdale 230/115 kV Transformer ckt 2 | Riverdale 230/115 kV Transformer ckt 2 | Regional Reliability | 2020-06-01 | 2021-06-01 | 2020-09-24 | DPA-2019-June-1058 | 3650000 | 2020 | 3650000 | 3704140 | 3704140 | Complete | 640330 | Riverdale | 640331 | Riverdale | Install a new 230/115 kV 187 MVA transformer located at Riverdale substation | 230/115
210617 | 91939 | 143253 | WFEC | OK | Multi - Lil Axe - Lexington 138 kV Voltage Conversion | Paoli - Lexington kV 138 kV | Regional Reliability | 2023-12-31 | 2021-06-01 | 2021-10-11 | DPA-2020-May-1203 | 7865000 | 2021 | 8263165.625 | 7865000 |  | Delay - Mitigation | 521022 | PAOLI | 520973 | LEXINGTON | Rebuild 14.3 miles of 69 kV line from Paoli to Lexington to 138 kV | 69
210617 | 91939 | 143254 | WFEC | OK | Multi - Lil Axe - Lexington 138 kV Voltage Conversion | Lexington - Lil Axe 138 kV | Regional Reliability | 2024-12-31 | 2021-06-01 | 2021-10-11 | DPA-2020-May-1203 | 5340500 | 2021 | 5751134.3561 | 5340500 |  | Delay - Mitigation | 520973 | LEXINGTON | 520976 | LITTLE AXE | Rebuild 9.7 miles of 69 kV line from Lexington to Lil Axe to 138 kV | 69
210617 | 91939 | 143255 | WFEC | OK | Multi - Lil Axe - Lexington 138 kV Voltage Conversion | Paoli 138 kV Terminal Upgrades | Regional Reliability | 2025-12-31 | 2021-06-01 | 2021-10-11 | DPA-2020-May-1203 | 450000 | 2021 | 484600.779 | 450000 |  | Delay - Mitigation |  |  |  |  | Convert 69 kV terminal equipment at Paoli Switch to 138 kV
210617 | 91939 | 143256 | WFEC | OK | Multi - Lil Axe - Lexington 138 kV Voltage Conversion | Canadian Switch138 kV Terminal Upgrades | Regional Reliability | 2024-12-31 | 2021-06-01 | 2021-10-11 | DPA-2020-May-1203 | 500000 | 2021 | 538445.31 | 500000 |  | Delay - Mitigation |  |  |  |  | Convert 69 kV terminal equipment at Canadian Switch to 138 kV
210718 | 92418 | 156387 | SPS | NM | Line-3 Bear Libby - Pearl 115 kV | 3 Bear Libby – Pearl 115 kV | Regional Reliability |  | 2024-06-01 | 2022-12-20 | DPA-2021-December-1478 | 1139526 | 2023 | 1168014.15 | 0 |  | Re-evaluation |  |  |  |  | Upgrade 3 Bear Libby – Pearl 115 kV line (upgrade terminal equipment and increase line clearances) to achieve an emergency rating of 99 MVA. | 115/115
220727 | 92237 | 144206 | SPS | TX | Line - Twist - Wilco 115 kV | Twist 115 kV Substation | Regional Reliability | 2024-12-15 | 2022-06-01 | 2023-08-24 | DPA-2021-Feb-1279-1280 | 9087788 | 2023 | 9314982.7 | 9087788 |  | Delay - Mitigation |  |  |  |  | Build a new 115 kV substation at Twist Substation, located 4 miles west and 2 miles south of RB-Exum, along the RB Exum-Hilmar Cheese Plant 115 kV line.
220727 | 92237 | 144207 | SPS | TX// | Line - Twist - Wilco 115 kV | RB-Exum - Hilmar Cheese Ckt 1, Twist 115 kV New Lines, north side. | Regional Reliability | 2024-12-15 | 2022-06-01 | 2023-08-24 | DPA-2021-Feb-1279-1280 | 3909647 | 2023 | 4007388.175 | 3909647 |  | Delay - Mitigation |  |  |  |  | Cut into the RB-Exum to Hilmar Cheese Plant 115 kV line, 4 miles west of RB-Exum, and build a new 2-mile double circuit 115 kV line south into the new Twist substation.
220727 | 92237 | 144208 | SPS | TX | Line - Twist - Wilco 115 kV | RB-Kemp - Moore County Ckt 1, Twist 115 kV New Lines, south side. | Regional Reliability | 2024-12-15 | 2022-06-01 | 2023-08-24 | DPA-2021-Feb-1279-1280 | 3561243 | 2023 | 3650274.075 | 3561243 |  | Delay - Mitigation |  |  |  |  | Cut into the RB-Kemp - Moore County 115 kV line, 2 miles east of RB-Kemp, and build a new 1.8-mile double circuit 115kV line north into the new Twist 115 kV substation.
210619 | 92180 | 143705 | NPPD | NE | Line - Kearney NE - Tower 115 kV | Kearney NE - Tower 115 kV Ckt 1 New Line | Regional Reliability | 2025-06-01 | 2022-06-01 | 2021-11-04 | DPA-2021-February-1278 | 11250834 | 2022 | 11820407.4712 | 12765472 |  | Delay - Mitigation | 640248 | Kearney Northeast | 640383 | Tower | Build a new 115 kV 10 mile line from Kearney to Tower with a minimum summer emergency rating of 160 MVA
210619 | 92180 | 144283 | NPPD | NE | Line - Kearney NE - Tower 115 kV | Tower 115 kV Terminal Equipment | Regional Reliability | 2025-06-01 | 2022-06-01 | 2021-11-04 | DPA-2021-February-1278 | 1288644 | 2022 | 1353881.6025 | 3077037 |  | Delay - Mitigation |  |  |  |  | Install terminal equipment at Tower 115 kV sub to support new line from Kearney 115 kV sub.
210619 | 92180 | 144284 | NPPD | NE | Line - Kearney NE - Tower 115 kV | Kearney 115 kV Terminal Equipment | Regional Reliability | 2025-06-01 | 2022-06-01 | 2021-11-04 | DPA-2021-February-1278 | 2692377 | 2022 | 2828678.5856 | 2996400 |  | Delay - Mitigation |  |  |  |  | Install 115 kV terminal equipment at Kearney 115 kV sub to support a new line from Tower 115 kV sub.
210665 | 92268 | 144276 | WFEC | AR | Multi - Elmore - Bradly 69 kV | Elmore 69 kV Terminal Upgrades | Regional Reliability | 2023-03-30 | 2022-06-01 | 2022-04-18 | DPA-2021-June-1332 | 228000 | 2022 | 233700 | 228000 |  | Delay - Mitigation |  |  |  |  | Upgrade string bus, jumpers, and any additional terminal equipment at Elmore 69 kV Substation.
210665 | 92268 | 144277 | WFEC | AR | Multi - Elmore - Bradly 69 kV | Bradly Tap 69 kV Cap Bank | Regional Reliability | 2023-06-01 | 2022-06-01 | 2022-04-18 | DPA-2021-June-1332 | 803000 | 2022 | 823075 | 803000 |  | Delay - Mitigation |  |  |  |  | Install new 12 MVAR capacitor bank at Bradly Tap 69 kV.
210664 | 92271 | 144278 | OGE |  | Multi - West Oaks - Council - Classen 138 kV Reconductor | West Oaks Terminal Upgrades | Regional Reliability | 2024-04-01 | 2024-04-01 | 2022-04-14 | DPA-2021-March-1296 | 400000 | 2022 | 420250 | 400000 |  | On Schedule < 4 |  |  |  |  | Upgrade any necessary terminal equipment at West Oaks substation.
210664 | 92271 | 144279 | OGE | AR | Multi - West Oaks - Council - Classen 138 kV Reconductor | Classen 138 kV Terminal Upgrades | Regional Reliability | 2024-04-01 | 2024-04-01 | 2022-04-14 | DPA-2021-March-1296 | 600000 | 2022 | 630375 | 600000 |  | On Schedule < 4 |  |  |  |  | Upgrade any necessary terminal equipment at Classen substation.
210664 | 92271 | 144280 | OGE | AR | Multi - West Oaks - Council - Classen 138 kV Reconductor | Council - Mustang 138 kV Ckt 1 Reconductor | Regional Reliability | 2024-04-01 | 2024-04-01 | 2022-04-14 | DPA-2021-March-1296 | 1390000 | 2022 | 1460368.75 | 1390000 |  | On Schedule < 4 |  |  |  |  | Reconductor of Mustang to Council 138 kV transmission line.
210664 | 92271 | 144281 | OGE | AR | Multi - West Oaks - Council - Classen 138 kV Reconductor | Classen - Douglas Tap 138 kV Reconductor | Regional Reliability | 2024-04-01 | 2024-04-01 | 2022-04-14 | DPA-2021-March-1296 | 790000 | 2022 | 829993.75 | 790000 |  | On Schedule < 4 |  |  |  |  | Reconductor of Douglas Tap to Classen 138 kV transmission line.
| 30959 | 51338 | EKC | KS | Sub - Tap Emporia Energy Center - Wichita 345kV (GEN-2014-001 Substation) | Burns 345kV (GEN-2014-001 NU) | Generation Interconnection | 2021-07-08 |  |  | GI STUDIES |  |  | 0 | 2098946 |  | In Service |  |  |  |  | Construct new terminal extension of the bus north to add another rung to the bus. Equipment includes two (2) 345kV breakers, four (4) 345kV switches, bus work, and all associated yard and conduit work.
| 30959 | 51360 | EKC | KS// | Sub - Tap Emporia Energy Center - Wichita 345kV (GEN-2014-001 Substation) | Tap Emporia Energy Center - Wichita 345kV (GEN-2014-001 TOIF) | Generation Interconnection | 2021-07-28 |  |  | GI STUDIES |  |  | 0 | 1886290 |  | In Service |  |  |  |  | Install three (3) 345 kV arresters, one (1) 345 kV 3000 Amp motor-operated switch, three (3) 345 kV arrester stands, one (1) 345 kV full tension dead-end structure, and one (1) 3-phase bus support into new Transmission Owner GEN-2014-001 Point of Interconnection substation. The estimate also includes three (3) 345 kV VTs, three (3) 345 kV CTs, and revenue interconnection metering plus all other associated yard, cable, grounding, communication, and conduit work.
| 51239 | 71933 | NPPD | NE/ | Sub - Holt County 345kV (Tap Grand Prairie - Grand Island 345kV) - GEN-2015-023 Addition | Holt County 345kV (Tap Grand Prairie - Grand Island 345kV) - GEN-2015-023 Addition (TOIF) | Generation Interconnection | 2024-04-01 |  |  | GI STUDIES |  |  | 0 | 4700000 |  | On Schedule < 4 | 640503 | Holt County 345 kV |  |  | Holt County 345kV Substation - Install 345kV line terminal to connect to the Interconnection Customer Interconnection Facilities. Work to include line switch, dead-end towers, metering, current transformers, potential transformers, and associated and miscellaneous material.; One (1) approximately five (5) mile 345 kV overhead transmission line from the Interconnection Customer's collector substation to the Transmission Owner's Holt County 345 kV substation.
| 51239 | 71934 | NPPD | NE | Sub - Holt County 345kV (Tap Grand Prairie - Grand Island 345kV) - GEN-2015-023 Addition | Holt County 345kV (Tap Grand Prairie - Grand Island 345kV) - GEN-2015-023 Addition (NU) | Generation Interconnection | 2024-04-01 |  |  | GI STUDIES |  |  | 0 | 5900000 |  | On Schedule < 4 | 640503 | Holt County 345 kV |  |  | Holt County 345 kV Substation – 345 kV substation bus work; add one (1) 345 kV line terminal, four (4) 345 kV circuit breakers, control panel, disconnect switches, and all associated and miscellaneous equipment. | 345
| 51255 | 71970 | WFEC | OK | Sub - Snyder 138kV (WFEC) - GEN-2015-013 Addition | Snyder 138kV (WFEC) - GEN-2015-013 Addition (NU) | Generation Interconnection | 2019-08-15 |  |  | GI STUDIES |  |  | 0 | 1700000 |  | On Schedule < 4 | 521052 | SNYDER |  |  | Snyder 138kV Substation: Install one (1) new line terminal, one (1) 2000A circuit breaker, line relaying, disconnect switches, additional 4” IPS aluminum buss, and associated equipment.
| 51283 | 72032 | EKC | KS/ | Sub - Wild Plains 345kV Switching Station GEN-2015-052 Interconnection | Wild Plains 345kV Switching Station GEN-2015-052 Interconnection (TOIF) | Generation Interconnection | 2019-12-01 |  |  | GI STUDIES |  |  | 0 | 591265 |  | In Service |  |  |  |  | Transmission Owner’s GEN-2015-052 Tap Interconnection Substation: Construct one (1) 345 kV line terminal, line switches, dead end structure, line relaying, communications, revenue metering, line arrestor and all associated equipment and facilities necessary to accept transmission line from Interconnection Customer’s Generating Facility.
| 51283 | 72033 | EKC | KS/ | Sub - Wild Plains 345kV Switching Station GEN-2015-052 Interconnection | Wild Plains 345kV Switching Station GEN-2015-052 Interconnection (NU) | Generation Interconnection | 2019-12-01 |  |  | GI STUDIES |  |  | 0 | 13383717 |  | In Service |  |  |  |  | Transmission Owner’s GEN-2015-052 Tap Interconnection Substation - Non-Shared Network Upgrades: Construct three (3) 345kV 4000 continuous ampacity breakers, cut in transmission line and re-terminate, control panels, line relaying, disconnect switches, structures, foundations, conductors, insulators, and all other associated work and materials. Allowance for Funds Used During Construction (AFUDC) and Contingency funds are included in this cost estimate.
| 51283 | 72034 | OGE | OK | Sub - Wild Plains 345kV Switching Station GEN-2015-052 Interconnection | Wild Plains 345kV Switching Station GEN-2015-052 Interconnection (NU - OGE) | Generation Interconnection | 2020-12-31 |  |  | GI STUDIES |  |  | 0 | 20000 |  | On Schedule < 4 |  |  |  |  | Oklahoma Gas and Electric Company – Checking and Verifying Relay Settings
| 51332 | 82126 | OGE | OK/ | Sub - Gracemont 345 kV Substation GEN-2015-093 Interconnection | Gracemont 345 kV Substation GEN-2015-093 Interconnection (TOIF) | Generation Interconnection | 2025-10-14 |  |  | GI STUDIES |  |  | 0 | 1099958 |  | On Schedule < 4 | 515800 | Gracemont 345kv |  |  | Transmission Owner Gracemont Interconnection Substation: Transmission Owner Interconnection Facilities 345kV Substation work for one (1) new line terminal, line switch, dead end structure, line relaying, communications, revenue metering, line arrestor, and all associated equipment and facilities necessary to accept transmission line from Interconnection Customer’s Generating Facility.
| 51332 | 82127 | OGE | OK/ | Sub - Gracemont 345 kV Substation GEN-2015-093 Interconnection | Gracemont 345 kV Substation GEN-2015-093 Interconnection (NU) | Generation Interconnection | 2025-10-14 |  |  | GI STUDIES |  |  | 0 | 1025042 |  | On Schedule < 4 |  |  |  |  | Transmission Owner Gracemont Interconnection Substation - Non-Shared Network Upgrades install one (1) 3000A circuit breakers, control panel replacement, line relaying, disconnect switches, and all other associated work and materials.
| 51333 | 82128 | OGE | OK/ | Sub - Tap Cleveland - Sooner 345 kV Substation GEN-2015-066 Interconnection | Tap Cleveland - Sooner 345 kV Substation GEN-2015-066 Interconnection (TOIF) | Generation Interconnection | 2025-10-15 |  |  | GI STUDIES |  |  | 0 | 1099958 |  | In Service |  |  |  |  | Transmission Owner GEN-2015-066 Tap Interconnection Substation: Transmission Owner Interconnection Facilities Construct one (1) 345 kV line terminal, line switches, dead end structure, line relaying, communications, revenue metering, line arrestor and all associated equipment and facilities necessary to accept transmission line from Interconnection Customer’s Generating Facility.
| 51333 | 82129 | OGE | OK | Sub - Tap Cleveland - Sooner 345 kV Substation GEN-2015-066 Interconnection | Tap Cleveland - Sooner 345 kV Substation GEN-2015-066 Interconnection (NU) | Generation Interconnection | 2025-10-15 |  |  | GI STUDIES |  |  | 0 | 9213042 |  | In Service |  |  |  |  | Transmission Owner GEN-2015-066 Tap Interconnection Substation - Non-Shared Network Upgrades* Install three (3) 3000 continuous ampacity breakers, cut in transmission line and re-terminate, control panels, line relaying, disconnect switches, structures, foundations, conductors, insulators, and all other associated work and materials.
| 81483 | 112331 | AEP | LA | Sub - Lieberman - North Benton 138 kV Substation GEN-2016-167 Interconnection | Lieberman - North Benton 138 kV Substation GEN-2016-167 Interconnection (TOIF) (AEPW) | Generation Interconnection | 2024-09-30 |  |  | GI STUDIES |  |  | 0 | 1175646 |  | In Service |  |  |  |  | Construct one (1) 138 kV line terminal, line switches, dead end structure, line relaying, communications, revenue metering, line arrestor, and all associated equipment and facilities necessary to accept transmission line from Interconnection Customer’s Generating |  | 0.04
| 81483 | 112332 | AEP | LA | Sub - Lieberman - North Benton 138 kV Substation GEN-2016-167 Interconnection | Lieberman - North Benton 138 kV Substation GEN-2016-167 Interconnection (Non-Shared NU) (AEPW) | Generation Interconnection | 2024-09-30 |  |  | GI STUDIES |  |  | 0 | 9959548.73 |  | In Service |  |  |  |  | Build a 3-breaker ring bus station on the Lieberman-North Benton 138 kV section of the Lieberman-Red Point 138 kV line to facilitate the new generation interconnection. |  | 1.32
| 81489 | 112333 | AEP | OK | Sub - Gracemont - Lawton East Side 345 kV | Gracemont - Lawton East Side 345 kV Substation GEN-2016-091 (TOIF) (AEPW) | Generation Interconnection | 2023-05-01 |  |  | GI STUDIES |  |  | 0 | 1704279 |  | In Service |  |  |  |  | : Construct one (1) 345 kV line terminal, line switches, dead end structure, line relaying, communications, revenue metering, line arrestor, and all associated equipment and facilities necessary to accept transmission line from Interconnection Customer’s Generating Facility. |  | 0.18
| 81489 | 112334 | AEP | OK | Sub - Gracemont - Lawton East Side 345 kV | Gracemont - Lawton East Side 345 kV Substation GEN-2016-091 (NU) (AEPW) | Generation Interconnection | 2023-05-01 |  |  | GI STUDIES |  |  | 0 | 17798882 |  | In Service |  |  |  |  | Construct new 345 kV four (4) breaker ring bus, control panels, line relaying, disconnect switches, structures, foundations, conductors, insulators ,and all other associated work and materials. |  | 0.32
| 81491 | 112337 | AEP | OK | GEN-2016-097 Interconnection Costs | Tap Southwestern - Fletcher Tap 138 kV Substation GEN-2016-097 (TOIF) (AEPW) | Generation Interconnection |  |  |  | GI STUDIES |  |  | 0 | 918474 |  | On Schedule < 4 |  |  |  |  | Construct one (1) 138 kV line terminal, line switches, dead end structure, line relaying, communications, revenue metering, line arrestor, and all associated equipment and facilities necessary to accept transmission line from Interconnection Customer’s Generating Facility. |  | 0.04
| 81491 | 112338 | AEP | OK | GEN-2016-097 Interconnection Costs | Tap Southwestern - Fletcher Tap 138 kV Substation GEN-2016-097 (Non-Shared NU) (AEPW) | Generation Interconnection |  |  |  | GI STUDIES |  |  | 0 | 7400346 |  | On Schedule < 4 |  |  |  |  | Construct new 138 kV three (3) breaker ring bus, control panels, line relaying, disconnect switches, structures, foundations, conductors, insulators, and all other associated work and materials.
| 81488 | 112339 | WAPA | SD | Ft. Thompson to Oahe 230kV GEN-2016-094 Interconnection Costs | Ft. Thompson to Oahe 230kV GEN-2016-094 Interconnection (TOIF) (WAPA) | Generation Interconnection | 2024-09-30 |  |  | GI STUDIES |  |  | 0 | 250000 |  | In Service |  |  |  |  | Construct one (1) 230 kV line terminal, line switches, dead end structure, line relaying, communications, revenue metering, line arrestor, and all associated equipment and facilities necessary to accept transmission line from Interconnection Customer’s Generating Facility.
| 81488 | 112340 | WAPA | SD | Ft. Thompson to Oahe 230kV GEN-2016-094 Interconnection Costs | Ft. Thompson to Oahe 230kV GEN-2016-094 Interconnection (Non-Shared NU) (WAPA) | Generation Interconnection | 2024-09-30 |  |  | GI STUDIES |  |  | 0 | 8805000 |  | In Service |  |  |  |  | Construct one (1) new 230 kV switchyard on the Oahe - Fort Thompson North 230 kV transmission that will consist of a three (3) breaker ring bus, three (3) 230 kV power circuit breakers, nine (9) 230 kV disconnect switches, instrument transformers, associated control and protection equipment, high voltage bus, three (3) line take-off structures, conductor, overhead optical ground wire, communication equipment, and a control building.
| 81495 | 112353 | SPS | TX | XTO to Cornell GEN-2016-177 Interconnection Costs | XTO to Cornell GEN-2016-177 Interconnection (TOIF) (SPS) | Generation Interconnection |  |  |  | GI STUDIES |  |  | 0 |  |  | On Schedule < 4 |  |  |  |  | TOIF Interconnection upgrade and cost estimates needed to interconnect GEN-2016-177 (17.0 MW/Gas Turbine) into the POI at XTO_Cornell 115kV.
| 81594 | 122540 | SPS | NM | Device - Crossroads 345 kV Capacitive Reactive Support (DISIS-2016-002-1) | Crossroads 345 kV Capacitive Reactive Support (DISIS-2016-002) | Generation Interconnection | 2021-12-31 |  |  | GI STUDIES |  |  | 0 | 6616797 |  | In Service |  |  |  |  | Install + 100 MVAR Capacitor Bank(s) at Crossroads 345 kV. Network Upgrade shared among four requests: GEN-2016-121, GEN-2016-123, GEN-2016-124, and GEN-2016-125
| 81600 | 122546 | SPS | TX | Line - Crossroads - Tolk 345 kV Ckt 1 | Crossroads - Tolk 345 kV Ckt 1 Rebuild (DISIS-2016-002) | Generation Interconnection | 2020-12-01 |  |  | GI STUDIES |  |  | 0 | 184651 |  | On Schedule < 4 |  |  |  |  | Replace approximately four structures on the Crossroads - Tolk 345 kV line to achieve a minimum rating of 956 MVA. Network Upgrade shared among four requests: GEN-2016-123, GEN-2016-124, and GEN-2016-125
| 81599 | 122547 | SPS | TX | Line - Crossroads - Eddy County 345 kV Ckt 1 | Crossroads - Eddy County 345 kV Ckt 1 Rebuild (DISIS-2016-002) | Generation Interconnection | 2022-12-15 |  |  | GI STUDIES |  |  | 0 | 210533 |  | On Schedule < 4 |  |  |  |  | Replace two 345 kV structures, wave traps (3X), and jumpers to achieve minimum emergency rating of 956 MVA. Network Upgrade Shared among three requests: GEN-2016-123, GEN-2016-124, and GEN-2016-125
| 81606 | 122554 | SPS | NM | Roadrunner 115kV GEN-2016-121 Interconnection Costs | Roadrunner 115kV GEN-2016-121 Interconnection (TOIF) (SPS) | Generation Interconnection | 2020-12-31 |  |  | GI STUDIES |  |  | 0 | 483969 |  | In Service |  |  |  |  | TOIF Interconnection upgrade and cost estimates needed to interconnect GEN-2016-121 (110.0 MW/Solar) into the POI at Roadrunner 115kV.
| 81607 | 122556 | SPS | NM | Eddy County to Tolk GEN-2016-123 Interconnection Costs | Eddy County to Tolk GEN-2016-123 Interconnection (TOIF) (SPS) | Generation Interconnection | 2020-12-31 |  |  | GI STUDIES |  |  | 0 | 219080 |  | In Service |  |  |  |  | TOIF Interconnection upgrade and cost estimates needed to interconnect GEN-2016-123 (298.0 MW/Wind) into the POI at Eddy County - Tolk (Crossroads) 345kV.
| 81608 | 122558 | SPS | NM | Eddy County to Tolk GEN-2016-124 Interconnection Costs | Eddy County to Tolk GEN-2016-124 Interconnection (TOIF) (SPS) | Generation Interconnection |  |  |  | GI STUDIES |  |  | 0 | 413496 |  | On Schedule < 4 |  |  |  |  | TOIF Interconnection upgrade and cost estimates needed to interconnect GEN-2016-124 (150.0 MW/Wind) into the POI at Eddy County - Tolk (Crossroads) 345kV.
| 81609 | 122560 | SPS | NM | Eddy County to Tolk GEN-2016-125 Interconnection Costs | Eddy County to Tolk GEN-2016-125 Interconnection (TOIF) (SPS) | Generation Interconnection |  |  |  | GI STUDIES |  |  | 0 | 413496 |  | On Schedule < 4 |  |  |  |  | TOIF Interconnection upgrade and cost estimates needed to interconnect GEN-2016-125 (74.0 MW/Wind) into the POI at Eddy County - Tolk (Crossroads) 345kV.
| 81613 | 122568 | SPS | TX | XFR - Tolk 345/230 kV Ckt2 | Tolk 345/230 kV CKT 2 Transformer (DISIS-2016-002) | Generation Interconnection | 2021-12-31 |  |  | GI STUDIES |  |  | 0 | 16379655 |  | In Service |  |  |  |  | Build new 345/230 kV Transformer Ckt 2 at Tolk to achieve a minimum emergency rating of 921 MVA on the Crossroads - Tolk 345 kV Ckt 1 line. Network Upgrade shared among three requests: GEN-2016-123, GEN-2016-124, and GEN-2016-125 |  | 0.5
| 81481 | 122623 | EKC | KS | Multi - West Gardner 345 kV, Swissvale 345 kV | Swissvale 345 kV Terminal Upgrades | Generation Interconnection | 2025-12-31 |  |  | GI STUDIES | 10000 | 2020 | 11038.1289 | 10000 |  | In Service |  |  |  |  | Reviewing and applying new relaying settings at the Swissvale substation for the interconnection of GEN-2016-158.
| 81636 | 122635 | OGE | OK | Spring Creek to Sooner 345kV GEN-2016-119 Interconnection Costs | GEN-2016-119 Interconnection (TOIF) (OKGE) | Generation Interconnection | 2025-03-14 |  |  | GI STUDIES |  |  | 0 | 1099871 |  | On Schedule < 4 |  |  |  |  | Add a single 345kV line terminal to a new EHV Substation. Dead end structure, line switch, line relaying, revenue metering including CTs and PTs.
| 81639 | 122640 | SPS | NM | Deaf Smith - Plant X 230 kV Ckt 1 Rebuild (DISIS-2016-002) | Deaf Smith - Plant X 230 kV Ckt 1 Rebuild (DISIS-2016-002) | Generation Interconnection | 2021-12-17 |  |  | GI STUDIES |  |  | 0 | 4578401 |  | On Schedule < 4 |  |  |  |  | Rebuild line to achieve minimum system emergency rating of 430 MVA. Network Upgrade shared among four requests: GEN-2016-121, GEN-2016-123, GEN-2016-124, and GEN-2016-125
| 81640 | 122641 | SPS | NM | Newhart - Plant X 230 kV Ckt 1 Rebuild (DISIS-2016-002) | Newhart - Plant X 230 kV Ckt 1 Rebuild (DISIS-2016-002) | Generation Interconnection | 2020-12-31 |  |  | GI STUDIES |  |  | 0 | 697513 |  | On Schedule < 4 |  |  |  |  | Rebuild line to achieve minimum emergency rating of 456 MVA. Network Upgrade shared among four requests: GEN-2016-121, GEN-2016-123, GEN-2016-124, and GEN-2016-125
| 81641 | 122642 | SPS | NM | Tolk West - Plant X 230 kV Ckt 1 Rebuild (DISIS-2016-002) | Tolk West - Plant X 230 kV Ckt 1 Rebuild (DISIS-2016-002) | Generation Interconnection |  |  |  | GI STUDIES |  |  | 0 |  |  | On Schedule < 4 |  |  |  |  | Rebuild line to achieve minimum normal/emergency rating of 796 MVA. Network Upgrade shared among three requests: GEN-2016-123, GEN-2016-124, and GEN-2016-125
| 81642 | 122643 | SPS | NM | Tolk East - Plant X 230 kV Ckt 2 Rebuild (DISIS-2016-002) | Tolk East - Plant X 230 kV Ckt 2 Rebuild (DISIS-2016-002) | Generation Interconnection |  |  |  | GI STUDIES |  |  | 0 |  |  | On Schedule < 4 |  |  |  |  | Rebuild line to achieve minimum normal/emergency rating of 796 MVA. Network Upgrade shared among three requests: GEN-2016-123, GEN-2016-124, and GEN-2016-125
| 81645 | 122645 | SPS | NM | Curry - Deafsmith 115 kV Ckt 1 Rebuild (DISIS-2016-002) | Curry - Deafsmith 115 kV Ckt 1 Rebuild (DISIS-2016-002) | Generation Interconnection | 2021-12-15 |  |  | GI STUDIES |  |  | 0 | 4852215 |  | On Schedule < 4 |  |  |  |  | Rebuild line to achieve minimum normal/emergency rating of 90/90 MVA. Network Upgrade shared among four requests: GEN-2016-121, GEN-2016-123, GEN-2016-124, and GEN-2016-125 |  |  | 13
| 81644 | 122646 | SPS | NM | Tolk East - Tuco 230 kV Ckt 1 Rebuild (DISIS-2016-002) | Tolk East - Tuco 230 kV Ckt 1 Rebuild (DISIS-2016-002) | Generation Interconnection | 2020-12-15 |  |  | GI STUDIES |  |  | 0 | 968567 |  | On Schedule < 4 |  |  |  |  | Rebuild line to achieve minimum normal/emergency rating of 478 MVA. Network Upgrade shared among four requests: GEN-2016-121, GEN-2016-123, GEN-2016-124, and GEN-2016-125
| 81646 | 122647 | SPS | TX | Tuco 230 kV Capacitive Reactive Power Support (DISIS-2016-002) | Tuco 230 kV Capacitive Reactive Power Support (DISIS-2016-002) | Generation Interconnection | 2020-12-31 |  |  | GI STUDIES |  |  | 0 | 5943138 |  | On Schedule < 4 |  |  |  |  | Build 100 MVAR at Tuco 230 kV Substation. Network Upgrade shared among four requests: GEN-2016-121, GEN-2016-123, GEN-2016-124, and GEN-2016-125
| 81647 | 122648 | SPS | TX | Deafsmith 115 kV Capacitive Reactive Power Support (DISIS-2016-002) | Deafsmith 115 kV Capacitive Reactive Power Support (DISIS-2016-002) | Generation Interconnection | 2021-10-28 |  |  | GI STUDIES |  |  | 0 | 3318135 |  | On Schedule < 4 |  |  |  |  | Build 100 MVAR at Deaf Smith 115 kV substation. Network Upgrade shared among four requests: GEN-2016-121, GEN-2016-123, GEN-2016-124, and GEN-2016-125
| 81655 | 122662 | OGE | OK | Woodring 345kV GEN-2016-128 Interconnection Costs | Woodring 345kV GEN-2016-128 Interconnection (TOIF) (OKGE) | Generation Interconnection |  |  |  | GI STUDIES |  |  | 0 | 15000 |  | On Schedule < 4 |  |  |  |  | At an existing EHV substation, update relay settings on an existing Gen-Tie line to accommodate new protection settings.
| 81657 | 122665 | AEP | OK | Multi - Riverside 345 kV Substation | Riverside 345kV GEN-2016-133 thru 146 Interconnection (TOIF) (AEP) | Generation Interconnection |  |  |  | GI STUDIES |  |  | 0 | 1388819 |  | On Schedule < 4 |  |  |  |  | Construct one (1) 345 kV line terminal, line switches, dead end structure, line relaying, communications, revenue metering, line arrestor, and all associated equipment and facilities necessary to accept transmission line from Interconnection Customer’s Generating Facility. |  | 0.18
| 81657 | 122666 | AEP | OK | Multi - Riverside 345 kV Substation | Riverside 345kV GEN-2016-133 thru 146 Interconnection (Non-Shared NU) (AEP) | Generation Interconnection |  |  |  | GI STUDIES |  |  | 0 | 10361130 |  | On Schedule < 4 |  |  |  |  | Expand the 345 kV breaker and a half scheme, control panels, line relaying, disconnect switches, structures, foundations, conductors, insulators, and all other associated work and materials.
| 81658 | 122669 | BEPC | ND | GEN-2016-130 Interconnection Costs | Leland Olds 345 kV Substation Reconfiguration (DISIS-2016-002-2) | Generation Interconnection | 2025-06-30 |  |  | GI STUDIES |  |  | 0 | 2776827 |  | On Schedule < 4 |  |  |  |  | Build out of a new line terminal for relocation of LOS Unit 2 main transformer. This includes one (1) 345 kV power circuit breaker, two (2) 345 kV breaker disconnect switches, three (3) 345 kV PTs, three (3) 345 kV surge arrestors, and protection and control package.
| 81660 | 122673 | EKC | KS | Viola 345kV GEN-2016-153 Interconnection Costs | Viola 345kV GEN-2016-153 Interconnection (Non-Shared NU) (WERE) | Generation Interconnection |  |  |  | GI STUDIES |  |  | 0 | 90000 |  | In Service |  |  |  |  | Review relay settings and apply adjusted settings at Flat Ridge 2 East and Viola 345 kV substations. Install PMU at Viola Substation
| 81662 | 122677 | NPPD | NE | Sweetwater 345kV GEN-2016-074 Interconnection Costs | GEN-2016-074 Interconnection (TOIF) (NPPD) | Generation Interconnection | 2024-02-01 |  |  | GI STUDIES |  |  | 0 |  |  | On Schedule < 4 |  |  |  |  | Expanding the existing Sweetwater 345kV Substation to accommodate the GEN-2016-074 interconnection request
| 81662 | 122678 | NPPD | NE | Sweetwater 345kV GEN-2016-074 Interconnection Costs | Sweetwater 345kV GEN-2016-074 Interconnection (TOIF) (NPPD) | Generation Interconnection | 2024-02-01 |  |  | GI STUDIES |  |  | 0 |  |  | On Schedule < 4 |  |  |  |  | Expand the existing Sweetwater 345kV Substation to accommodate GEN-2016-074 interconnection request
| 81665 | 122684 | TSGT | NE | Sidney 115kV GEN-2016-147 Interconnection Costs | Sidney 115kV GEN-2016-147 Interconnection Costs (TOIF) (TSGT) | Generation Interconnection | 2023-10-05 |  |  | GI STUDIES |  |  | 0 | 1636796 |  | On Schedule < 4 |  |  |  |  | Construct one (1) 115 kV line terminal, line switches, dead end structure, line relaying, communications, revenue metering, line arrestor, and all associated equipment and facilities necessary to accept transmission line from Interconnection Customer’s Generating Facility.
| 81665 | 122687 | TSGT | NE | Sidney 115kV GEN-2016-147 Interconnection Costs | Sidney 115kV GEN-2016-147 Interconnection Costs (Non-Shared NU) (TSGT) | Generation Interconnection | 2023-10-05 |  |  | GI STUDIES |  |  | 0 | 2155837 |  | On Schedule < 4 |  |  |  |  | Construct one (1) 230 kV power circuit breaker, two (2) 115 kV power circuit breakers, control panels, line relaying, disconnect switches, structures, foundations, conductors, insulators, and all other associated work and materials.
| 81666 | 122688 | WAPA | SD | Bismark to Glenham GEN-2016-087 Interconnection Costs | Bismark to Glenham 230kV GEN-2016-087 Interconnection (TOIF) (WAPA) | Generation Interconnection | 2026-10-30 |  |  | GI STUDIES |  |  | 0 | 644488 |  | In Service |  |  |  |  | Construct one (1) 230 kV line terminal, line switches, dead end structure, line relaying, communications, revenue metering, line arrestor, and the re-route of the Glenham line to the new 230 kV line bay.
| 81670 | 122792 | EKC | KS | Viola 345/138 kV Transformer CKT 2 | Viola 345/138 kV Transformer CKT 2 (DISIS-2016-002-2) | Generation Interconnection |  |  |  | GI STUDIES |  |  | 0 | 11450023 |  | In Service |  |  |  |  | Install a new 345 kV terminal on a new rung consisting of two (2) breakers, four (4) switches, and two (2) control panels. Install a new 138 kV terminal on an existing rung consisting of one (1) breaker, three (3) switches, three (3) PTs, and one (1) 400/440 MVA 345-138 kV transformer with LTCs. Network Upgrade shared among fourteen requests: GEN-2016-100, GEN-2016-101, GEN-2016-119, GEN-2016-128, GEN-2016-133, GEN-2016-134, GEN-2016-137, GEN-2016-138, GEN-2016-139, GEN-2016-141, GEN-2016-142, GEN-2016-145, GEN-2016-146, GEN-2016-153
| 92013 | 143370 | WR | KS | Swissvale 345kV GEN-2017-125 Interconnection Costs | Swissvale 345kV Interconnection Expansion (DISIS-2017-002) | Generation Interconnection |  |  |  | GI STUDIES |  |  | 0 | 25565648 |  | On Schedule < 4 |  |  |  |  | Expand the Swissvale 345kV substation to accommodate the interconnection of GEN-2017-125, GEN-2017-128, GEN-2017-142, GEN-2017-191 and GEN-2017-192 | 345
200277 | 30678 | 50889 | NPPD | NE | XFR - Thedford 345/115 kV | Thedford 345/115 kV Transformer | High Priority | 2026-12-31 | 2016-06-01 | 2014-05-19 | HPILS | 9306000 | 2014 | 11912466.7292 | 9797157 |  | Delay - Mitigation | 640500 | Cherry County 345 kV | 640381 | Thedford | Install new 345/115 kV 400 MVA transformer at Thedford substation. Install any necessary 115 kV terminal equipment. | 345/115
200277 | 30678 | 51002 | NPPD | NE | XFR - Thedford 345/115 kV | Thedford 345 kV Terminal Upgrades | High Priority | 2026-12-31 | 2016-06-01 | 2014-05-19 | HPILS | 930800 | 2014 | 1191502.6898 | 913714 |  | Delay - Mitigation | 640500 | Cherry County 345 kV |  |  | Install any necessary 345 kV terminal equipment at Thedford associated with new 345/115 kV transformer. | 345
220722 | 92371 | 156240 | BEPC | ND | Line - North Dakota/Saskatchewan Border (Tableland) - Tande 230 kV | North Dakota/Saskatchewan Border (Tableland) - Tande 230 kV Ckt 1 | Transmission Service | 2027-10-01 | 2027-10-01 | 2023-05-24 | SPP- 2021-AG2 | 78880406 | 2023 | 80852416.15 | 78880406 |  | On Schedule < 4 |  |  |  |  | Build new 67 mile 230 kV line from Tande substation to the United Sates/Canada border toward Sask Power’s Tableland substation. | 230
220722 | 92371 | 156241 | BEPC | ND | Line - North Dakota/Saskatchewan Border (Tableland) - Tande 230 kV | Tande 230 kV Terminal Equipment | Transmission Service | 2027-10-01 | 2027-10-01 | 2023-05-24 | SPP- 2021-AG2 | 2562090 | 2023 | 2626142.25 | 2562090 |  | On Schedule < 4 |  |  |  |  | Install any necessary terminal equipment at the Tande substation to accommodate a terminal for the North Dakota/Saskatchewan Border (Tableland) - Tande 230 kV Ckt 1. | 230
220722 | 92372 | 156248 | BEPC | ND | Line - North Dakota/Saskatchewan Border (Tableland) - Wheelock 230 kV | North Dakota/Saskatchewan Border (Tableland) - Wheelock 230 kV Ckt 1 | Transmission Service | 2027-10-01 | 2027-10-01 | 2023-05-24 | SPP- 2021-AG2 | 65123051 | 2023 | 66751127.275 | 65123051 |  | On Schedule < 4 |  |  |  |  | Build new 70 mile 230 kV line from Wheelock substation to the United States/Canada border toward Sask Power’s Tableland substation. | 230
220722 | 92372 | 156249 | BEPC | ND | Line - North Dakota/Saskatchewan Border (Tableland) - Wheelock 230 kV | Wheelock 230 kV Terminal Upgrade | Transmission Service | 2027-10-01 | 2027-10-01 | 2023-05-24 | SPP- 2021-AG2 | 2476563 | 2023 | 2538477.075 | 2476563 |  | On Schedule < 4 |  |  |  |  | Install any necessary terminal equipment at Wheelock substation to accommodate a new terminal for the North Dakota/Saskatchewan Border (Tableland) - Wheelock 230 kV Ckt 1. | 230
210679 | 92402 | 156334 | MWE | ND | Device - Twelve Mile 115 kV Capacitor Bank | Twelve Mile 115 kV Capacitor Bank | Transmission Service | 2029-10-01 | 2029-10-01 | 2022-06-30 | SPP- 2021-AG2 | 571195 | 2022 | 600111.7469 | 571195 |  | On Schedule > 4 |  |  |  |  | Install 12 MVAR capacitor bank at Twelve Mile 115 kV substation. | 115
200420 | 31063 | 51567 | SPS | NM | Sub - Carlsbad - Pecos 115 kV Terminal Upgrades | Carlsbad - Pecos 115 kV Terminal Upgrades | Regional Reliability | 2021-06-01 | 2021-06-01 | 2017-01-12 | SPP-2015-AG1-AFS-6 | 767347 | 2017 | 847007.5097 | 0 |  | Re-evaluation | 528160 | Carlsbad Interchange 115 kV | 528178 | Pecos Interchange 115 kV | Install terminal upgrades at Carlsbad and/or Pecos to increase the rating of the 115 kV line between the substations. | 115 |  | 0.03
200466 | 51249 | 71955 | EKC | KS | Line - City of Winfield - Oak 69 kV Reconductor | Oak - Rainbow 69 kV Ckt 1 | Regional Reliability | 2021-04-12 | 2021-06-01 | 2017-09-21 | SPP-2016-AG2-AFS-1 | 7831427 | 2017 | 8644430.0697 | 5156586 | 5156585 | Closed Out |  |  |  |  | Reconductor 5.1 miles of 69 kV transmission line from Oak to Rainbow. | 69 |  | 5.1
200479 | 51249 | 71954 | KPP | KS | Line - City of Winfield - Oak 69 kV Reconductor | City of Winfield - Rainbow 69 kV Ckt 1 | Regional Reliability | 2020-12-31 | 2021-06-01 | 2018-02-27 | SPP-2016-AG2-AFS-2 | 3600000 | 2018 | 3782250 | 5066520 |  | Closed Out |  |  |  |  | Reconductor 4 miles of 69 kV transmission line from City of Winfield to Rainbow. |  |  | 4
210570 | 81559 | 112456 | EDE | KS | Line - Neosho - Riverton 161 kV | Neosho - Riverton 161kV Rebuild (EDE) | Transmission Service | 2023-01-13 | 2023-10-01 | 2020-11-12 | SPP-2019-AG1-AFS-2 | 69054450 | 2022 | 70780811.25 | 73054450 | 72381260 | Complete | 532937 | NEOSHO 161 KV | 547469 | SUB 452 - RIVERTON | Rebuild 28.41 miles of 161kV line from Neosho to Riverton and upgrade any necessary terminal equipment to increase the summer emergency rating to 250 MVA | 161 |  | 25.9
210558 | 81673 | 122713 | AEP | OK | Line - Kerr - Locust Grove 115 kV | Kerr - Locust Grove 115 kV Ckt 1 | Transmission Service | 2022-06-15 | 2022-06-01 | 2020-05-29 | SPP-2019-AG2-AFS-3 | 3160967 | 2020 | 3320990.9544 | 2752417 | 3093201 | Complete | 510423 | LOCUST GROVE | 512634 | KERR 115 | Rebuild 0.47 miles of 115 kV line from Kerr - Locust Grove | 115 |  | 0.49
210716 | 92639 | 156844 | OPPD | NE | Line - S1254 - S1281 161 kV Ckt 1 Reconductor | S1254 - S1281 161 kV Ckt 1 Reconductor | Transmission Service | 2024-04-15 | 2023-10-01 | 2022-11-29 | SPP-2022-AG1-AFS-2 | 1171441 | 2022 | 1230745.2006 | 1171441 |  | Delay - Mitigation |  |  |  |  | Reconductor 3.1 miles of S1254 - S1281 161 kV line. Line will share common right of way with S3454 - S3740 345 kV line.
210486 | 51278 | 72006 | WAPA | ND | Sub - Bismarck 115 kV and North Bismarck 115 kV Terminal Upgrades | Bismarck 115 kV Terminal Upgrades | Sponsored Upgrade | 2024-06-30 | 2024-06-01 | 2018-08-17 | SUS-002 | 90000 | 2018 | 104372.4078 | 90000 |  | Delay - Mitigation Window | 652427 | BISMARK | 655652 |  | Replace CTs at Bismarck 115 kV substation to increase rating of Bismarck - East Bismarck 115 kV line to at least 85 MVA. This is a mitigation upgrade resulting from the Sponsored Upgrade Study #SUS-002 CPEC North Bismarck Breaker. Costs will be Directly Assigned to CPEC. | 115
210522 | 81616 | 122599 | NWE | SD | Line - Aberdeen City - Aberdeen Industrial Park 115 kV | Aberdeen A-Tap Breaker 115 kV | Sponsored Upgrade | 2019-06-01 | 2021-12-31 | 2019-09-06 | SUS-006 | 552668 | 2019 | 552668 | 552668 | 555000 | Complete |  |  |  |  | Add breaker at Aberdeen A-tap for the new Aberdeen City - Aberdeen Industrial Park 115 kV line. | 115
210563 | 81656 | 122664 | NPPD | NE | Line-Pauline-Hastings 115 kV Reconductor | Pauline - Hastings 115 kV Ckt 1 & Ckt 2 Reconductor | Sponsored Upgrade | 2022-12-01 | 2022-12-01 | 2020-07-14 | SUS-014 | 6000000 | 2020 | 6303750 | 5119643 | 5119643 | Complete | 640313 | Pauline | 640215 | Hastings | A reconductor of the Pauline – Hastings 115 kV transmission lines to achieve 193 MVA for normal and emergency ratings. The Pauline to Hastings 115 kV transmission lines are 13 miles each.
210661 | 92308 | 144328 | EREC | SD// | Line Carpenter – Willow Lake 69 kV | Carpenter – Willow Lake 69 kV | Sponsored Upgrade | 2025-01-01 | 2021-11-23 | 2022-03-21 | SUS-018 | 13720246 | 2022 | 14414833.4537 | 0 |  | Delay - Mitigation |  |  |  |  | Build a new 14-mile 69 kV line from Carpenter – Willow Lake with a minimal emergency rating of 114 MVA | 69 | 14
220723 | 93895 | 158446 | OPPD | NE | Line - S1363 - S1362 161 kV | S1363 - S1362 161 kV | Sponsored Upgrade | 2023-11-22 | 2023-10-02 | 2023-10-03 | SUS-038 | 7754624 | 2023 | 7754624 | 7754624 |  | Delay - Mitigation Window |  |  |  |  | Build a new 161 kV line from S1363 to S1362 |  | 2.7
220723 | 93896 | 158447 | OPPD | NE | Line - S1281 - S1361 161 kV | S1281 - S1361 161 kV | Sponsored Upgrade | 2024-12-31 | 2024-12-31 | 2023-10-03 | SUS-038 | 3111647 | 2023 | 3189438.175 | 3111647 |  | On Schedule < 4 |  |  |  |  | Replace S1361 - S1362 161 kV with new S1281 - S1361 161 kV line |  | 3.1
220723 | 93897 | 158448 | OPPD | NE | Tap S1345 - S1236 161 kV | Tap S1345 - S1236 161 kV | Sponsored Upgrade | 2023-12-31 | 2023-12-31 | 2023-10-03 | SUS-038 | 13199959 | 2023 | 13199959 | 13199959 |  | On Schedule < 4 |  |  |  |  | Tap the existing S1345 - S1236 161 kV line and connect to substation S1252