## Schedule
Exhibit A | Total Plan Completion
Reynolds Station Replacement Schedule | 95.36%
Anticipated Replacement Schedule - End Dec 2025
| Start | End | 2024-01-01 | 2024-02-01 | 2024-03-01 | 2024-04-01 | 2024-05-01 | 2024-06-01 | 2024-07-01 | 2024-08-01 | 2024-09-01 | 2024-10-01 | 2024-11-01 | 2024-12-01 | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01
Phase 1 - Temp Reg Stations In Progress (7 Stations) [Kingshighway LP Stations & Hampton/Scanlan]
ROW Acquisition | 2023-07-01 | 2024-01-01
Engineering Design | 2023-10-01 | 2024-01-01
Material Acquisition | 2023-12-01 | 2024-03-01
Construction - installation of temporary stations [COMPLETE] | 2024-03-01 | 2024-08-01
System Balance/Review - Consider status of pipe replacements completed and stations remaining | 2024-06-01 | 2024-09-01
Phase 2 - Additional Temp Reg Stations (7 Stations) [Remaining Reynolds LP Station]
ROW Acquisition | 2024-05-01 | 2025-02-01
Engineering Design | 2024-08-01 | 2024-12-01
Material Acquisition | 2024-09-01 | 2025-03-01
Construction - installation of temporary stations | 2025-03-01 | 2025-07-01
12 Stations Abandoned (not including existing stations temp regs are replacing)
Anticipated stations abandoned due To construction (6 Stations) [Field Ops will complete/grid work] [Removed Sidney & Nebraska since added to Phase 2] | 2024-01-01 | 2025-12-01
Stations currently shut off - to be abandoned (3 Stations) | 2024-01-01 | 2025-12-01
Stations no longer needed due to replacement of other stations - to be abandoned (4 Stations) [turned off - not to be used - to be abandoned with grid work] | 2024-01-01 | 2025-12-01

## Stations
Station # | Station Name | Status | % Complete | Total Plan Completion
Phase 1 - Temp Reg Stations In Progress (7 Stations) |  |  | 100% | 95.36%
| Hampton & Scanlan | Installed | 100%
| Thirty Ninth & Flora | Installed | 100%
| Kingshgihway & Eichelberger | Installed | 100%
| Nottingham & Macklind | Installed | 100%
| Bancroft & Kingshighway | Installed | 100%
| Kingshighway & Schollmeyer | Installed | 100%
| Virginia & Osceola | Installed | 100%
Phase 2 - Additional Temp Reg Stations (7 Stations) |  |  | 98.57% | Tentative Completion Timeline
| Grand & Bates | Installed | 100%
| Eichelberger & Hampton | Installed | 100%
| Grand & Magnolia | Installed | 100%
| Grand & Meramec | Easement - Install INPRG | 90% | 2026-05-01
| Utah & Grand | Installed | 100%
| January & Loughborough | Installed | 100%
| Sidney & Nebraska | Installed | 100%
12 Stations Abandoned (not including existing stations temp regs are replacing) |  |  | 87.5%
Abandon with Grid |  |  | 100%
3 | Arsenal & January | Abandoned 12/26/25 | 100%
16 | Broadway N of Keokuk | Abandoned 11/12/24 | 100%
104 | Tower Grove & Magnolia | Abandoned 1/16/25 | 100%
97 | Missouri & Lynch | Abandoned 6/20/24 | 100%
22 | Ridgewood & Chippewa | Abandoned 8/29/24 | 100%
No longer Needed Due to Replacement of Other Stations |  |  | 62.5%
56 | Piedmont & Gasconade | Offline (not abandoned) | 50% | Late Fall/Winter 2026
84 | Jefferson & Utah | Offline (not abandoned) | 50% | Summer 2026
120 | Phillips & Rogers | Offline (not abandoned) | 50% | Summer 2027
132 | Deminil & Cherokee | Abandoned 2/6/26 | 100%
Currently Offline/To be Abandoned |  |  | 100%
36 | Gravois & Delor | Abandoned 8/26/25 | 100%
116 | Page & Walton | Abandoned 2/28/24 | 100%
515 | Virginia & Osceola | Abandoned 8/21/24 | 100%