## Index
2015-02-26
Ameren Missouri
Demand Side Programs Annual Report per 4 CSR 240-3.163 (5)
Electric Utility Demand-Side Programs Investment Mechanisms Filing and Submission Requirements
Index of Annual Report Information
Information | Workbook Tab | Responding to Requirement
Index | 1
Relationship of Programs to IRP Filing | 1 | (5)(A)11
Costs | 2 | (5)(A)1
Energy Savings (2013-2015) | 3 | (5)(A)2,3
Peak Demand Savings | 4 | (5)(A)2,3
Gross Benefits | 5 | (5)(A)6
Net Benefits | 6 | (5)(A)8
DSIM Performance Measures | 7 | (5)(A)1,11(b), 5(B)
Cost Effectiveness | 8 | (5)(A)7
Opt-out Customer List (HC) | 9 | (5)(A)9
10% Cost Variances | 10 | (5)(A)5
Market Transformation | 11 | (5)(A)4
EM&V Annual Report | 12 | (5)(A)10
Response to (5)(A)11:
Ameren Missouri 2013 MEEIA programs were consistent with the information provided in File No. EO-2013-0392, where Ameren Missouri notified the Missouri Public Service Commission and all parties to its last Integrated Resource Plan filing, that it had determined its preferred resource plan was no longer appropriate and adopted as its preferred resource plan a contingency plan identified in its 2011 Integrated Resource Planning filing (File No. EO-2012-0271.) Specifically, Tab 2 (Costs) of the report that was attached to the pleading, Ameren Missouri lists all of the programs currently being administered as part of its MEEIA plan along with proposed funding levels.

## Costs
DSM Advisory Group Annual Report: Programs' and Portfolio Costs vs. Targets | Utility: Ameren Missouri |  |  |  |  | Utility: Ameren Missouri |  |  |  |  | Utility: Ameren Missouri
| Report Date: 02/26/2015 |  |  |  |  | Report Date: 02/26/2015 |  |  |  |  | Report Date: 02/26/2015
| Period: 01/02/13 - 12/31/13 |  |  |  |  | Period: 01/02/14 - 12/31/14 |  |  |  |  | Period: 01/02/15 - 12/31/15
| Portfolio Start Date: 01/02/2013 |  |  |  |  | Portfolio Start Date: 01/02/2013 |  |  |  |  | Portfolio Start Date: 01/02/2013
Programs' Costs (Recorded) | 1ST QUARTER | 2ND QUARTER | 3RD QUARTER | 4TH QUARTER | 1ST YTD TOTAL | 5TH QUARTER | 6TH QUARTER | 7TH QUARTER | 8TH QUARTER | 2ND YTD TOTAL | 9TH QUARTER | 10TH QUARTER | 11TH QUARTER | 12TH QUARTER | 3RD YTD TOTAL | PORTFOLIO TO DATE TOTAL
Standard | 239218.01 | 664011.13 | 416288.21 | 1004313.44 | 2323830.79 | 672918.56 | 753614.01 | 1012033.42 | 1476759.74 | 3915325.73
Custom | 773728.97 | 1374208.23 | 1964948.26 | 2468445.3 | 6581330.76 | 1740744.76 | 2557711.85 | 2162206.59 | 1058108.96 | 7518772.16
Retro-commissioning | 124245 | 62707.68 | 60338.98 | 73343.27 | 320634.93 | 302201.51 | 98057.82 | 127091.39 | 1218867.38 | 1746218.1
New Construction | 93183.75 | 108903.84 | 42653.83 | 120252.83 | 364994.25 | 90851.28 | 488899.1 | 628299.67 | 387880.42 | 1595930.47
Business Subtotal | 1230375.73 | 2209830.88 | 2484229.28 | 3666354.84 | 9590790.73 | 2806716.11 | 3898282.78 | 3929631.07 | 4141616.5 | 14776246.46
Lighting | 1138006.41 | 1184551.1 | 2284706.25 | 2469950.4 | 7077214.16 | 2140858.63 | 2253041.79 | 1832175.03 | 1645207.74 | 7871283.19
Energy Efficient Products | 201070.51 | 146947.99 | 404954.05 | 640039.39 | 1393011.94 | 559215.13 | 341011.23 | 305058.77 | 522183.27 | 1727468.4
HVAC | 373961.1 | 1539594.97 | 1803160.42 | 1247284.67 | 4964001.16 | 1099643.32 | 1774339.23 | 2596959.59 | 1658362.47 | 7129304.61
Refrigerator Recycling | 174274.33 | 289879.44 | 333464.95 | 261164.59 | 1058783.31 | 174720.42 | 382673.02 | 469035.89 | 248063.72 | 1274493.05
Home Energy Performance | 0 | 31754.62 | 86430.7 | 63683.29 | 181868.61 | 73556.8 | 76654.82 | 95530.63 | 77659.06 | 323401.31
New Homes | 77520.87 | 118905.78 | 112550.47 | 99472.25 | 408449.37 | 105251.46 | 76588.04 | 93252.77 | 41223.12 | 316315.39
Low Income | 492935.33 | 977601.58 | 1330864.73 | 1017486.02 | 3818887.66 | 465657.48 | 1396472.4 | 808179.36 | 869138.63 | 3539447.87
Residential Subtotal | 2457768.55 | 4289235.48 | 6356131.57 | 5799080.61 | 18902216.21 | 4618903.24 | 6300780.53 | 6200192.04 | 5061838.01 | 22181713.82
EM&V Subtotal | 19120.45 | 812215.48 | 618094.07 | 1100021.97 | 2549451.97 | 536950.82 | 302838.94 | 661301.6 | 378994.77 | 1880086.13
Portfolio Subtotal | 1409309.21 | 755539.31 | 551143.03 | 673951.45 | 3389943 | 718221.43 | 1198446.77 | 456462.72 | 306912.54 | 2680043.46
Quarterly Total Program | 5116573.94 | 8066821.15 | 10009597.95 | 11239408.87 | 34432401.91 | 8680791.6 | 11700349.02 | 11247587.43 | 9889361.82 | 41518089.87
Cumulative Total Program | 5116573.94 | 13183395.09 | 23192993.04 | 34432401.91 |  | 43113193.51 | 54813542.53 | 66061129.96 | 75950491.78
Programs' Costs Budgets (MEEIA Plan) | 1ST QUARTER | 2ND QUARTER | 3RD QUARTER | 4TH QUARTER | 1ST YTD TOTAL | 5TH QUARTER | 6TH QUARTER | 7TH QUARTER | 8TH QUARTER | 2ND YTD TOTAL | 9TH QUARTER | 10TH QUARTER | 11TH QUARTER | 12TH QUARTER | 3RD YTD TOTAL | PORTFOLIO TO DATE TOTAL
Standard | 102715.4089 | 850483.2172 | 1120635.1162 | 1148246.2578 | 3222080 | 719154.0909 | 1051071.3636 | 1382988.6364 | 1714905.9091 | 4868120 | 1146180.7495 | 1738594.9205 | 2331009.0914 | 2835655.2386 | 8051440 | 16141640
Custom | 21527.8745 | 1244667.4659 | 2640092.7024 | 4451001.9572 | 8357290 | 1305944.5455 | 1908688.1818 | 2511431.8182 | 3114175.4545 | 8840240 | 1869522.0697 | 2835801.9234 | 3802081.7772 | 4625204.2297 | 13132610 | 30330140
Retro-commissioning | 0 | 0 | 48077.7828 | 207092.2172 | 255170 | 38617.3864 | 56440.7955 | 74264.2045 | 92087.6136 | 261410 | 45773.5459 | 69432.0284 | 93090.5109 | 113243.9148 | 321540 | 838120
New Construction | 0 | 0 | 122482.7537 | 527587.2463 | 650070 | 152185.6818 | 222425.2273 | 292664.7727 | 362904.3182 | 1030180 | 255556.8641 | 387643.804 | 519730.7439 | 632248.588 | 1795180 | 3475430
Business Subtotal | 124243.2833 | 2095150.6831 | 3931288.3552 | 6333927.6784 | 12484610 | 2215901.7045 | 3238625.5682 | 4261349.4318 | 5284073.2955 | 14999950 | 3317033.2292 | 5031472.6763 | 6745912.1234 | 8206351.971 | 23300770 | 50785330
Lighting | 1131316.2706 | 1651921.988 | 1561817.1523 | 1892201.5499 | 6237256.9608 | 1680746.6699 | 1372937.0895 | 1298049.6119 | 1572637.0298 | 5924370.401 | 1253492.0888 | 990107.1512 | 926027.8149 | 1160985.3813 | 4330612.4363 | 16492239.7981
Energy Efficient Products | 54087.0694 | 254981.8986 | 316795.6923 | 332249.1407 | 958113.801 | 600612.0863 | 508207.8283 | 460732.7774 | 493946.8609 | 2063499.553 | 686877.8888 | 893151.2553 | 796804.4653 | 864209.7712 | 3241043.3806 | 6262656.7345
HVAC | 200652.08 | 1203790.9461 | 1304056.2193 | 635377.9976 | 3343877.243 | 953703.688 | 3178811.2172 | 2304532.5675 | 1278384.4177 | 7715431.8903 | 1417369.6996 | 4980348.4289 | 5489201.7275 | 2605699.702 | 14492619.558 | 25551928.6913
Refrigerator Recycling | 376409.6806 | 455865.029 | 436121.5788 | 370631.1098 | 1639027.3982 | 355249.2399 | 510101.4726 | 521812.986 | 340935.1679 | 1728098.8664 | 430221.1269 | 683425.8697 | 662640.4058 | 231814.4254 | 2008101.8278 | 5375228.0924
Home Energy Performance | 4310.3448 | 202586.2069 | 142241.3793 | 81896.5517 | 431034.4828 | 87768.7526 | 130753.5504 | 130753.5504 | 87525.481 | 436801.3344 | 117283.0343 | 143269.7964 | 143186.5234 | 40798.1591 | 444537.5131 | 1312373.3303
New Homes | 0 | 35897.8791 | 64998.5267 | 43332.3511 | 144228.757 | 122221.2626 | 109557.3727 | 104256.2095 | 154322.7508 | 490357.5956 | 311041.0701 | 273586.8795 | 258507.9197 | 406379.0097 | 1249514.879 | 1884101.2316
Low Income | 591741.34 | 982513.923 | 893194.4755 | 658730.9257 | 3126180.6642 | 709589.1133 | 1178185.6976 | 1071077.9069 | 789919.9563 | 3748772.6742 | 693186.5761 | 1260053.5673 | 1130483.9693 | 790363.7746 | 3874087.8873 | 10749041.2256
Residential Subtotal | 2358516.7854 | 4787557.8708 | 4719225.0241 | 4014419.6265 | 15879719.3069 | 4509890.8125 | 6988554.2283 | 5891215.6096 | 4717671.6644 | 22107332.3148 | 4909471.4846 | 9223942.9484 | 9406852.8259 | 6100250.2233 | 29640517.4821 | 67627569.1038
EM&V Subtotal | 164360.3841 | 354913.505 | 420407.638 | 522148.4729 | 1461830 | 372369.6506 | 497005.8395 | 509211.8914 | 545992.6185 | 1924580 | 477440.9708 | 681158.573 | 780802.999 | 793847.4572 | 2733250 | 6119660
Portfolio Subtotal | 707567.1642 | 1527893.3766 | 1809843.9099 | 2247835.5493 | 6293140 | 1565023.2563 | 2088853.6329 | 2140154.1482 | 2294738.9627 | 8088770 | 1469601.1262 | 2096660.0419 | 2403373.4782 | 2443525.3537 | 8413160 | 22795070
Quarterly Total Program | 3354687.617 | 8765515.4355 | 10880764.9271 | 13118331.3272 | 36119299.3069 | 8663185.4239 | 12813039.2688 | 12801931.081 | 12842476.5411 | 47120632.3148 | 10173546.8108 | 17033234.2396 | 19336941.4265 | 17543975.0052 | 64087697.4821 | 147327629.1038
Cumulative Total Program | 3354687.617 | 12120203.0525 | 23000967.9797 | 36119299.3069 |  | 44782484.7308 | 57595523.9997 | 70397455.0806 | 83239931.6217 |  | 93413478.4325 | 110446712.6721 | 129783654.0986 | 147327629.1038 |  | 147327629.1038
Programs' Costs vs. Budgets ($) Variance | 1ST QUARTER | 2ND QUARTER | 3RD QUARTER | 4TH QUARTER | 1ST YTD TOTAL | 5TH QUARTER | 6TH QUARTER | 7TH QUARTER | 8TH QUARTER | 2ND YTD TOTAL | 9TH QUARTER | 10TH QUARTER | 11TH QUARTER | 12TH QUARTER | 3RD YTD TOTAL | PORTFOLIO TO DATE TOTAL
Standard | 136502.6011 | -186472.0872 | -704346.9062 | -143932.8178 | -898249.21 | -46235.5309 | -297457.3536 | -370955.2164 | -238146.1691 | -952794.27
Custom | 752201.0955 | 129540.7641 | -675144.4424 | -1982556.6572 | -1775959.24 | 434800.2145 | 649023.6682 | -349225.2282 | -2056066.4945 | -1321467.84
Retro-commissioning | 124245 | 62707.68 | 12261.1972 | -133748.9472 | 65464.93 | 263584.1236 | 41617.0245 | 52827.1855 | 1126779.7664 | 1484808.1
New Construction | 93183.75 | 108903.84 | -79828.9237 | -407334.4163 | -285075.75 | -61334.4018 | 266473.8727 | 335634.8973 | 24976.1018 | 565750.47
Business Subtotal | 1106132.4467 | 114680.1969 | -1447059.0752 | -2667572.8384 | -2893819.27 | 590814.4055 | 659657.2118 | -331718.3618 | -1142456.7955 | -223703.54
Lighting | 6690.1394 | -467370.888 | 722889.0977 | 577748.8501 | 839957.1992 | 460111.9601 | 880104.7005 | 534125.4181 | 72570.7102 | 1946912.789
Energy Efficient Products | 146983.4406 | -108033.9086 | 88158.3577 | 307790.2493 | 434898.139 | -41396.9563 | -167196.5983 | -155674.0074 | 28236.4091 | -336031.153
HVAC | 173309.02 | 335804.0239 | 499104.2007 | 611906.6724 | 1620123.917 | 145939.632 | -1404471.9872 | 292427.0225 | 379978.0523 | -586127.2803
Refrigerator Recycling | -202135.3506 | -165985.589 | -102656.6288 | -109466.5198 | -580244.0882 | -180528.8199 | -127428.4526 | -52777.096 | -92871.4479 | -453605.8164
Home Energy Performance | -4310.3448 | -170831.5869 | -55810.6793 | -18213.2617 | -249165.8728 | -14211.9526 | -54098.7304 | -35222.9204 | -9866.421 | -113400.0244
New Homes | 77520.87 | 83007.9009 | 47551.9433 | 56139.8989 | 264220.613 | -16969.8026 | -32969.3327 | -11003.4395 | -113099.6308 | -174042.2056
Low Income | -98806.01 | -4912.343 | 437670.2545 | 358755.0943 | 692706.9958 | -243931.6333 | 218286.7024 | -262898.5469 | 79218.6737 | -209324.8042
Residential Subtotal | 99251.7646 | -498322.3908 | 1636906.5459 | 1784660.9835 | 3022496.9031 | 109012.4275 | -687773.6983 | 308976.4304 | 344166.3456 | 74381.5052
EM&V Subtotal | -145239.9341 | 457301.975 | 197686.432 | 577873.4971 | 1087621.97 | 164581.1694 | -194166.8995 | 152089.7086 | -166997.8485 | -44493.87
Portfolio Subtotal | 701742.0458 | -772354.0666 | -1258700.8799 | -1573884.0993 | -2903197 | -846801.8263 | -890406.8629 | -1683691.4282 | -1987826.4227 | -5408726.54
Quarterly Total Program | 1761886.323 | -698694.2855 | -871166.9771 | -1878922.4572 | -1686897.3969 | 17606.1761 | -1112690.2488 | -1554343.651 | -2953114.7211 | -5602542.4448
Cumulative Total Program | 1761886.323 | 1063192.0375 | 192025.0603 | -1686897.3969 |  | -1669291.2208 | -2781981.4697 | -4336325.1206 | -7289439.8417
Programs' Costs vs. Budgets (%) Variance | 1ST QUARTER | 2ND QUARTER | 3RD QUARTER | 4TH QUARTER | 1ST YTD TOTAL | 5TH QUARTER | 6TH QUARTER | 7TH QUARTER | 8TH QUARTER | 2ND YTD TOTAL | 9TH QUARTER | 10TH QUARTER | 11TH QUARTER | 12TH QUARTER | 3RD YTD TOTAL | PORTFOLIO TO DATE TOTAL
Standard | 132.9% | -21.93% | -62.85% | -12.54% | -27.88% | -6.429% | -28.3% | -26.82% | -13.89% | -19.57%
Custom | 3494% | 10.41% | -25.57% | -44.54% | -21.25% | 33.29% | 34% | -13.91% | -66.02% | -14.95%
Retro-commissioning |  |  | 25.5% | -64.58% | 25.66% | 682.6% | 73.74% | 71.13% | 1224% | 568%
New Construction |  |  | -65.18% | -77.21% | -43.85% | -40.3% | 119.8% | 114.7% | 6.882% | 54.92%
Business Subtotal | 890.3% | 5.474% | -36.81% | -42.12% | -23.18% | 26.66% | 20.37% | -7.784% | -21.62% | -1.491%
Lighting | 0.5914% | -28.29% | 46.29% | 30.53% | 13.47% | 27.38% | 64.1% | 41.15% | 4.615% | 32.86%
Energy Efficient Products | 271.8% | -42.37% | 27.83% | 92.64% | 45.39% | -6.892% | -32.9% | -33.79% | 5.716% | -16.28%
HVAC | 86.37% | 27.9% | 38.27% | 96.31% | 48.45% | 15.3% | -44.18% | 12.69% | 29.72% | -7.597%
Refrigerator Recycling | -53.7% | -36.41% | -23.54% | -29.54% | -35.4% | -50.82% | -24.98% | -10.11% | -27.24% | -26.25%
Home Energy Performance | -100% | -84.33% | -39.24% | -22.24% | -57.81% | -16.19% | -41.37% | -26.94% | -11.27% | -25.96%
New Homes |  | 231.2% | 73.16% | 129.6% | 183.2% | -13.88% | -30.09% | -10.55% | -73.29% | -35.49%
Low Income | -16.7% | -0.5% | 49% | 54.46% | 22.16% | -34.38% | 18.53% | -24.55% | 10.03% | -5.584%
Residential Subtotal | 4.208% | -10.41% | 34.69% | 44.46% | 19.03% | 2.417% | -9.841% | 5.245% | 7.295% | 0.3365%
EM&V Subtotal | -88.37% | 128.8% | 47.02% | 110.7% | 74.4% | 44.2% | -39.07% | 29.87% | -30.59% | -2.312%
Portfolio Subtotal | 99.18% | -50.55% | -69.55% | -70.02% | -46.13% | -54.11% | -42.63% | -78.67% | -86.63% | -66.87%
Quarterly Total Program | 52.52% | -7.971% | -8.006% | -14.32% | -4.67% | 0.2032% | -8.684% | -12.14% | -22.99% | -11.89%
Cumulative Total Program | 52.52% | 8.772% | 0.8349% | -4.67% |  | -3.728% | -4.83% | -6.16% | -8.757%
* The financial information contained within this report is confidential and may contain immaterial revisions from other company financial statements.

## Energy Savings
DSM Advisory Group Annual Report: Programs' and Portfolio Energy Savings vs. Targets | Utility: Ameren Missouri |  |  |  |  | Utility: Ameren Missouri |  |  |  |  | Utility: Ameren Missouri
| Report Date: 02/26/2015 |  |  |  |  | Report Date: 02/26/2015 |  |  |  |  | Report Date: 02/26/2015
| Period: 01/02/13 - 12/31/13 |  |  |  |  | Period: 01/02/14 - 12/31/14 |  |  |  |  | Period: 01/02/15 - 12/31/15
| Portfolio Start Date: 01/02/2013 |  |  |  |  | Portfolio Start Date: 01/02/2013 |  |  |  |  | Portfolio Start Date: 01/02/2013
Programs' Energy Savings (MWh) | 1ST QUARTER | 2ND QUARTER | 3RD QUARTER | 4TH QUARTER | 1ST YTD TOTAL | 5TH QUARTER | 6TH QUARTER | 7TH QUARTER | 8TH QUARTER | 2ND YTD TOTAL | 9TH QUARTER | 10TH QUARTER | 11TH QUARTER | 12TH QUARTER | 3RD YTD TOTAL | PORTFOLIO TO DATE TOTAL
Standard | 904.4179 | 4169.4254 | 6201.7582 | 11326.0883 | 22601.6898 | 6936.7034 | 8315.2998 | 10493.1109 | 13130.1504 | 38875.2646
Custom | 214.1702 | 7685.3429 | 12070.3359 | 31560.19 | 51530.039 | 13313.9758 | 24188.2941 | 21914.5999 | 20956.738 | 80373.6078
Retro-commissioning | 0 | 0 | 316.031 | 0 | 316.031 | 1027.01 | 0 | 257.881 | 10355.969 | 11640.86
New Construction | 0 | 372.0766 | -214.435 | 10.421 | 168.0626 | 385.4094 | 4640.1602 | 5077.2979 | 3517.6302 | 13620.4975
Business Subtotal | 1118.588 | 12226.8449 | 18373.6901 | 42896.6993 | 74615.8224 | 21663.0986 | 37143.754 | 37742.8897 | 47960.4876 | 144510.2299
Lighting | 24657.5675 | 47770.5334 | 58732.459 | 67574.5364 | 198735.0964 | 41753.2927 | 41519.1431 | 32141.9838 | 32334.4818 | 147748.9015
Energy Efficient Products | 211.0714 | 385.4662 | 4809.8686 | 16066.9609 | 21473.3671 | 3796.6372 | 467.2875 | 2340.7096 | 5136.6492 | 11741.2835
HVAC | 1163.6473 | 6923.9634 | 11871.5952 | 7916.5631 | 27875.769 | 6252.607 | 10423.1546 | 16798.0028 | 8740.0988 | 42213.8632
Refrigerator Recycling | 1023.9398 | 1173.3395 | 2160.7469 | 1976.0269 | 6334.0531 | 1138.1978 | 2201.7382 | 3122.7091 | 1713.4528 | 8176.0979
Home Energy Performance | 1.5696 | 72.3503 | 174.7016 | 179.0638 | 427.6853 | 149.5669 | 135.5203 | 191.6741 | 173.0433 | 649.8046
New Homes | 0 | 0 | 30.1261 | 404.4563 | 434.5824 | 180.9404 | 7.694 | 312.0502 | 134.038 | 634.7227
Low Income | 831.9342 | 1778.0986 | 2321.3611 | 2540.5778 | 7471.9717 | 1028.0041 | 1891.9302 | 1470.2279 | 1849.4717 | 6239.634
Residential Subtotal | 27889.7297 | 58103.7516 | 80100.8585 | 96658.1853 | 262752.525 | 54299.2462 | 56646.4679 | 56377.3576 | 50081.2356 | 217404.3074
Quarterly Total Program (MWh) | 29008.3178 | 70330.5965 | 98474.5486 | 139554.8846 | 337368.3474 | 75962.3447 | 93790.222 | 94120.2473 | 98041.7233 | 361914.5373
Cumulative Total Program (MWh) | 29008.3178 | 99338.9143 | 197813.4629 | 337368.3474 |  | 413330.6921 | 507120.9141 | 601241.1614 | 699282.8847
Programs' Energy Savings (MWH) Goal (MEEIA Plan) | 1ST QUARTER | 2ND QUARTER | 3RD QUARTER | 4TH QUARTER | 1ST YTD TOTAL | 5TH QUARTER | 6TH QUARTER | 7TH QUARTER | 8TH QUARTER | 2ND YTD TOTAL | 9TH QUARTER | 10TH QUARTER | 11TH QUARTER | 12TH QUARTER | 3RD YTD TOTAL | PORTFOLIO TO DATE TOTAL
Standard | 800.9351 | 6631.7396 | 8738.2798 | 8953.5808 | 25124.5353 | 4976.4003 | 7273.2004 | 9570.0006 | 11866.8007 | 33686.402 | 7649.9483 | 11180.6937 | 14711.4391 | 18242.1844 | 51784.2655 | 110595.2028
Custom | 141.5765 | 8185.4638 | 17362.375 | 29271.6862 | 54961.1015 | 8079.4073 | 11808.3645 | 15537.3217 | 19266.2789 | 54691.3723 | 11006.9684 | 16087.1076 | 21167.2468 | 26247.3861 | 74508.7089 | 184161.1827
Retro-commissioning | 0 | 0 | 494.6603 | 2130.7202 | 2625.3805 | 380.5894 | 556.246 | 731.9026 | 907.5592 | 2576.2972 | 455.3235 | 665.4729 | 875.6222 | 1085.7715 | 3082.1901 | 8283.8677
New Construction | 0 | 0 | 528.7348 | 2277.4942 | 2806.229 | 607.6314 | 888.0766 | 1168.5219 | 1448.9672 | 4113.1971 | 944.1181 | 1379.8649 | 1815.6117 | 2251.3585 | 6390.9531 | 13310.3792
Business Subtotal | 942.5116 | 14817.2035 | 27124.05 | 42633.4814 | 85517.2464 | 14044.0283 | 20525.8875 | 27007.7467 | 33489.6059 | 95067.2685 | 20056.3583 | 29313.139 | 38569.9197 | 47826.7005 | 135766.1175 | 316350.6324
Lighting | 21993.7989 | 32114.8391 | 30363.1206 | 36786.0884 | 121257.847 | 27472.6204 | 22441.3233 | 21217.2512 | 25705.5158 | 96836.7107 | 17694.7431 | 14454.1528 | 13665.7444 | 16556.575 | 62371.2153 | 280465.773
Energy Efficient Products | 424.1094 | 1999.3731 | 2484.0696 | 2605.2437 | 7512.7958 | 4589.4775 | 3883.3857 | 3520.613 | 3774.4129 | 15767.889 | 5455.8391 | 6819.7989 | 6182.7164 | 6628.4265 | 25086.781 | 48367.4658
HVAC | 1033.187 | 6198.496 | 6714.7766 | 3271.6544 | 17218.1139 | 4529.4182 | 15097.1058 | 10944.9004 | 6071.4222 | 36642.8466 | 8266.1257 | 22735.9299 | 19292.0172 | 13092.1165 | 63386.1893 | 117247.1498
Refrigerator Recycling | 2696.0288 | 3265.1266 | 3123.7144 | 2654.6399 | 11739.5098 | 2456.5086 | 3527.2944 | 3608.2782 | 2357.5284 | 11949.6097 | 3047.7853 | 4543.7678 | 4420.9633 | 1875.5602 | 13888.0766 | 37577.1961
Home Energy Performance | 10.702 | 502.9935 | 353.1656 | 203.3378 | 1070.1989 | 215.0406 | 320.3569 | 320.3569 | 214.4446 | 1070.1989 | 280.1952 | 333.6401 | 333.4689 | 122.8947 | 1070.1989 | 3210.5967
New Homes | 0 | 168.9976 | 305.9956 | 203.9971 | 678.9903 | 358.8268 | 321.6472 | 306.0836 | 453.0729 | 1439.6304 | 701.3958 | 629.2897 | 600.26 | 884.9386 | 2815.8841 | 4934.5048
Low Income | 1097.4299 | 1822.1477 | 1656.4979 | 1221.6672 | 5797.7428 | 857.5547 | 1423.8645 | 1294.4223 | 954.6364 | 4530.4779 | 631.8716 | 1049.1453 | 953.7685 | 703.4043 | 3338.1897 | 13666.4104
Residential Subtotal | 27255.256 | 46071.9736 | 45001.3404 | 46946.6286 | 165275.1985 | 40479.4469 | 47014.9778 | 41211.9054 | 39531.0331 | 168237.3632 | 36077.9559 | 50565.7245 | 45448.9387 | 39863.9158 | 171956.5349 | 505469.0966
Quarterly Total Program Goal (MWh) | 28197.7676 | 60889.177 | 72125.3904 | 89580.11 | 250792.4449 | 54523.4752 | 67540.8653 | 68219.6522 | 73020.6391 | 263304.6317 | 56134.3142 | 79878.8635 | 84018.8584 | 87690.6163 | 307722.6524 | 821819.729
Cumulative Energy Savings Goal (MWh) | 28197.7676 | 89086.9446 | 161212.3349 | 250792.4449 |  | 305315.9201 | 372856.7854 | 441076.4375 | 514097.0766 |  | 570231.3907 | 650110.2542 | 734129.1127 | 821819.729 | 821819.729 | 821819.729
Programs' Energy Savings vs. Targets (MWh) Variance | 1ST QUARTER | 2ND QUARTER | 3RD QUARTER | 4TH QUARTER | 1ST YTD TOTAL | 5TH QUARTER | 6TH QUARTER | 7TH QUARTER | 8TH QUARTER | 2ND YTD TOTAL | 9TH QUARTER | 10TH QUARTER | 11TH QUARTER | 12TH QUARTER | 3RD YTD TOTAL | PORTFOLIO TO DATE TOTAL
Standard | 103.4828 | -2462.3142 | -2536.5216 | 2372.5075 | -2522.8456 | 1960.3031 | 1042.0994 | 923.1104 | 1263.3498 | 5188.8626
Custom | 72.5937 | -500.1209 | -5292.0391 | 2288.5038 | -3431.0625 | 5234.5685 | 12379.9296 | 6377.2782 | 1690.4591 | 25682.2355
Retro-commissioning | 0 | 0 | -178.6293 | -2130.7202 | -2309.3495 | 646.4206 | -556.246 | -474.0216 | 9448.4098 | 9064.5628
New Construction | 0 | 372.0766 | -743.1698 | -2267.0732 | -2638.1664 | -222.222 | 3752.0835 | 3908.776 | 2068.663 | 9507.3005
Business Subtotal | 176.0765 | -2590.3585 | -8750.3599 | 263.2179 | -10901.424 | 7619.0703 | 16617.8665 | 10735.143 | 14470.8817 | 49442.9614
Lighting | 2663.7686 | 15655.6943 | 28369.3384 | 30788.448 | 77477.2494 | 14280.6724 | 19077.8198 | 10924.7327 | 6628.966 | 50912.1908
Energy Efficient Products | -213.0381 | -1613.9068 | 2325.799 | 13461.7172 | 13960.5713 | -792.8403 | -3416.0982 | -1179.9033 | 1362.2363 | -4026.6055
HVAC | 130.4603 | 725.4675 | 5156.8187 | 4644.9087 | 10657.6551 | 1723.1887 | -4673.9512 | 5853.1024 | 2668.6766 | 5571.0166
Refrigerator Recycling | -1672.089 | -2091.7871 | -962.9676 | -678.613 | -5405.4567 | -1318.3109 | -1325.5562 | -485.5691 | -644.0756 | -3773.5118
Home Energy Performance | -9.1324 | -430.6432 | -178.4641 | -24.274 | -642.5136 | -65.4737 | -184.8366 | -128.6828 | -41.4012 | -420.3943
New Homes | 0 | -168.9976 | -275.8696 | 200.4593 | -244.4079 | -177.8863 | -313.9531 | 5.9667 | -319.0349 | -804.9077
Low Income | -265.4957 | -44.0491 | 664.8631 | 1318.9105 | 1674.2289 | 170.4494 | 468.0657 | 175.8057 | 894.8353 | 1709.1561
Residential Subtotal | 634.4737 | 12031.778 | 35099.5181 | 49711.5567 | 97477.3265 | 13819.7993 | 9631.4902 | 15165.4522 | 10550.2025 | 49166.9442
Quarterly Total Program (MWh) | 810.5502 | 9441.4195 | 26349.1582 | 49974.7746 | 86575.9025 | 42877.7391 | 52498.7134 | 51801.1903 | 50042.1684 | 197219.8112
Cumulative Total Program (MWh) | 810.5502 | 10251.9697 | 36601.1279 | 86575.9025 |  | 129453.6416 | 181952.355 | 233753.5453 | 283795.7137
Programs' Energy Savings vs. Targets (%) Variance | 1ST QUARTER | 2ND QUARTER | 3RD QUARTER | 4TH QUARTER | 1ST YTD TOTAL | 5TH QUARTER | 6TH QUARTER | 7TH QUARTER | 8TH QUARTER | 2ND YTD TOTAL | 9TH QUARTER | 10TH QUARTER | 11TH QUARTER | 12TH QUARTER | 3RD YTD TOTAL | PORTFOLIO TO DATE TOTAL
Standard | 12.92% | -37.13% | -29.03% | 26.5% | -10.04% | 39.39% | 14.33% | 9.646% | 10.65% | 15.4%
Custom | 51.28% | -6.11% | -30.48% | 7.818% | -6.243% | 64.79% | 104.8% | 41.04% | 8.774% | 46.96%
Retro-commissioning |  |  | -36.11% | -100% | -87.96% | 169.8% | -100% | -64.77% | 1041% | 351.8%
New Construction |  |  | -140.6% | -99.54% | -94.01% | -36.57% | 422.5% | 334.5% | 142.8% | 231.1%
Business Subtotal | 18.68% | -17.48% | -32.26% | 0.6174% | -12.75% | 54.25% | 80.96% | 39.75% | 43.21% | 52.01%
Lighting | 12.11% | 48.75% | 93.43% | 83.7% | 63.89% | 51.98% | 85.01% | 51.49% | 25.79% | 52.58%
Energy Efficient Products | -50.23% | -80.72% | 93.63% | 516.7% | 185.8% | -17.28% | -87.97% | -33.51% | 36.09% | -25.54%
HVAC | 12.63% | 11.7% | 76.8% | 142% | 61.9% | 38.04% | -30.96% | 53.48% | 43.95% | 15.2%
Refrigerator Recycling | -62.02% | -64.06% | -30.83% | -25.56% | -46.04% | -53.67% | -37.58% | -13.46% | -27.32% | -31.58%
Home Energy Performance | -85.33% | -85.62% | -50.53% | -11.94% | -60.04% | -30.45% | -57.7% | -40.17% | -19.31% | -39.28%
New Homes |  | -100% | -90.15% | 98.27% | -36% | -49.57% | -97.61% | 1.949% | -70.42% | -55.91%
Low Income | -24.19% | -2.417% | 40.14% | 108% | 28.88% | 19.88% | 32.87% | 13.58% | 93.74% | 37.73%
Residential Subtotal | 2.328% | 26.12% | 78% | 105.9% | 58.98% | 34.14% | 20.49% | 36.8% | 26.69% | 29.22%
Quarterly Total Program (MWh) | 2.875% | 15.51% | 36.53% | 55.79% | 34.52% | 39.32% | 38.86% | 37.97% | 34.27% | 37.45%
Cumulative Total Program (MWh) | 2.875% | 11.51% | 22.7% | 34.52% |  | 35.38% | 36.01% | 36.31% | 36.02%
* The financial information contained within this report is confidential and may contain immaterial revisions from other company financial statements.

## Demand Savings
DSM Advisory Group Annual Report: Programs' and Portfolio Demand Savings vs. Targets | Utility: Ameren Missouri |  |  |  |  | Utility: Ameren Missouri |  |  |  |  | Utility: Ameren Missouri
| Report Date: 02/26/2015 |  |  |  |  | Report Date: 02/26/2015 |  |  |  |  | Report Date: 02/26/2015
| Period: 01/02/13 - 12/31/13 |  |  |  |  | Period: 01/02/14 - 12/31/14 |  |  |  |  | Period: 01/02/15 - 12/31/15
| Portfolio Start Date: 01/02/2013 |  |  |  |  | Portfolio Start Date: 01/02/2013 |  |  |  |  | Portfolio Start Date: 01/02/2013
Programs' Demand Savings (MW) | 1ST QUARTER | 2ND QUARTER | 3RD QUARTER | 4TH QUARTER | 1ST YTD TOTAL | 5TH QUARTER | 6TH QUARTER | 7TH QUARTER | 8TH QUARTER | 2ND YTD TOTAL | 9TH QUARTER | 10TH QUARTER | 11TH QUARTER | 12TH QUARTER | 3RD YTD TOTAL | PORTFOLIO TO DATE TOTAL
Standard | 0.14436 | 0.66849 | 0.99424 | 1.8073 | 3.6144 | 1.0767 | 1.3273 | 1.672 | 1.9914 | 6.0674
Custom | 0.034185 | 1.4143 | 1.6263 | 6.206 | 9.2808 | 2.1179 | 3.2224 | 3.4563 | 2.8381 | 11.6346
Retro-commissioning | 0 | 0 | 0.051832 | 0 | 0.051832 | 0.16844 | 0 | 0.00012301 | 0.62799 | 0.79655
New Construction | 0 | 0.034551 | -0.0093886 | 0.0016634 | 0.026825 | 0.061532 | 0.70941 | 0.94201 | 0.69564 | 2.4086
Business Subtotal | 0.17854 | 2.1174 | 2.6629 | 8.015 | 12.9739 | 3.4245 | 5.2591 | 6.0704 | 6.1531 | 20.9071
Lighting | 0.98127 | 1.9011 | 2.3373 | 2.6892 | 7.9088 | 1.6616 | 1.6523 | 1.2791 | 1.2868 | 5.8798
Energy Efficient Products | -0.0018644 | 0.015059 | 0.43646 | 1.5768 | 2.0265 | 0.30001 | 0.032069 | 0.23559 | 0.49182 | 1.0595
HVAC | 0.48029 | 2.5135 | 4.3256 | 2.5061 | 9.8255 | 1.8657 | 3.6867 | 6.0095 | 2.902 | 14.4639
Refrigerator Recycling | 0.18828 | 0.21269 | 0.39301 | 0.35814 | 1.1521 | 0.20401 | 0.39834 | 0.56774 | 0.31044 | 1.4805
Home Energy Performance | 8.2659e-05 | 0.0044425 | 0.014137 | 0.01596 | 0.034622 | 0.021741 | 0.011358 | 0.01696 | 0.021329 | 0.071389
New Homes | 0 | 0 | 0.0017307 | 0.071147 | 0.072878 | 0.047233 | 0.0013926 | 0.023278 | 0.026608 | 0.098512
Low Income | 0.065475 | 0.21818 | 0.3508 | 0.093466 | 0.72792 | -0.025187 | 0.49209 | 0.22607 | -0.038818 | 0.65416
Residential Subtotal | 1.7135 | 4.865 | 7.8591 | 7.3108 | 21.7483 | 4.0751 | 6.2742 | 8.3583 | 5.0002 | 23.7078
Quarterly Total Program (MW) | 1.8921 | 6.9823 | 10.522 | 15.3258 | 34.7222 | 7.4996 | 11.5333 | 14.4287 | 11.1533 | 44.6149
Cumulative Total Program (MW) | 1.8921 | 8.8744 | 19.3964 | 34.7222 |  | 42.2219 | 53.7552 | 68.1839 | 79.3372
Programs' Demand Savings Targets (MW) (MEEIA Plan) | 1ST QUARTER | 2ND QUARTER | 3RD QUARTER | 4TH QUARTER | 1ST YTD TOTAL | 5TH QUARTER | 6TH QUARTER | 7TH QUARTER | 8TH QUARTER | 2ND YTD TOTAL | 9TH QUARTER | 10TH QUARTER | 11TH QUARTER | 12TH QUARTER | 3RD YTD TOTAL | PORTFOLIO TO DATE TOTAL
Standard | 0.10583 | 0.87628 | 1.8488 | 1.7093 | 4.5402 | 0.9255 | 1.3527 | 1.7798 | 2.207 | 6.2649 | 1.3313 | 2.0194 | 2.7075 | 3.2936 | 9.3517 | 20.1569
Custom | 0.023778 | 1.3748 | 4.5208 | 7.1031 | 13.0225 | 2.1993 | 3.2143 | 4.2294 | 5.2444 | 14.8874 | 3.1245 | 4.7394 | 6.3543 | 7.73 | 21.9481 | 49.858
Retro-commissioning | 0 | 0 | 0.094558 | 0.43635 | 0.53091 | 0.084243 | 0.12313 | 0.16201 | 0.20089 | 0.57026 | 0.09264 | 0.14052 | 0.1884 | 0.22919 | 0.65075 | 1.7519
New Construction | 0 | 0 | 0.14203 | 0.65541 | 0.79744 | 0.17976 | 0.26272 | 0.34569 | 0.42866 | 1.2168 | 0.28792 | 0.43673 | 0.58554 | 0.71231 | 2.0225 | 4.0368
Business Subtotal | 0.12961 | 2.2511 | 6.6062 | 9.9042 | 18.8911 | 3.3888 | 4.9528 | 6.5169 | 8.0809 | 22.9394 | 4.8363 | 7.336 | 9.8357 | 11.965 | 33.973 | 75.8035
Lighting | 0.66159 | 0.96603 | 0.91334 | 1.1065 | 3.6475 | 0.82585 | 0.67461 | 0.63781 | 0.77273 | 2.911 | 0.54272 | 0.42868 | 0.40094 | 0.50267 | 1.875 | 8.4335
Energy Efficient Products | 0.071885 | 0.33889 | 0.42104 | 0.44158 | 1.2734 | 0.74277 | 0.62849 | 0.56978 | 0.61086 | 2.5519 | 0.81346 | 1.0577 | 0.94364 | 1.0235 | 3.8383 | 7.6636
HVAC | 0.74175 | 4.4501 | 4.8207 | 2.3488 | 12.3613 | 3.0041 | 10.0132 | 7.2592 | 4.0269 | 24.3034 | 3.5936 | 12.6273 | 13.9174 | 6.6065 | 36.7449 | 73.4096
Refrigerator Recycling | 0.37565 | 0.45494 | 0.43524 | 0.36988 | 1.6357 | 0.34211 | 0.49124 | 0.50252 | 0.32833 | 1.6642 | 0.41441 | 0.65831 | 0.63829 | 0.22329 | 1.9343 | 5.2342
Home Energy Performance | 0.003519 | 0.16539 | 0.11613 | 0.066861 | 0.3519 | 0.070448 | 0.10495 | 0.10495 | 0.070253 | 0.3506 | 0.092394 | 0.11287 | 0.1128 | 0.03214 | 0.3502 | 1.0527
New Homes | 0 | 0.020484 | 0.03709 | 0.024726 | 0.0823 | 0.067721 | 0.060704 | 0.057767 | 0.085508 | 0.2717 | 0.15894 | 0.1398 | 0.1321 | 0.20766 | 0.6385 | 0.9925
Low Income | 0.14654 | 0.24332 | 0.2212 | 0.16313 | 0.7742 | 0.15923 | 0.26438 | 0.24034 | 0.17725 | 0.8412 | 0.13307 | 0.24189 | 0.21702 | 0.15172 | 0.7437 | 2.3591
Residential Subtotal | 2.0009 | 6.6391 | 6.9647 | 4.5215 | 20.1263 | 5.2123 | 12.2375 | 9.3724 | 6.0718 | 32.894 | 5.7486 | 15.2666 | 16.3622 | 8.7475 | 46.1249 | 99.1452
Quarterly Total Program (MW) | 2.1305 | 8.8902 | 13.571 | 14.4257 | 39.0174 | 8.601 | 17.1904 | 15.8893 | 14.1527 | 55.8334 | 10.5849 | 22.6026 | 26.1979 | 20.7125 | 80.0979 | 174.9487
Cumulative Total Program (MW) | 2.1305 | 11.0207 | 24.5917 | 39.0174 |  | 47.6185 | 64.8088 | 80.6981 | 94.8508 |  | 105.4357 | 128.0383 | 154.2362 | 174.9487
Programs' Demand Savings vs. Targets (MW) Variance | 1ST QUARTER | 2ND QUARTER | 3RD QUARTER | 4TH QUARTER | 1ST YTD TOTAL | 5TH QUARTER | 6TH QUARTER | 7TH QUARTER | 8TH QUARTER | 2ND YTD TOTAL | 9TH QUARTER | 10TH QUARTER | 11TH QUARTER | 12TH QUARTER | 3RD YTD TOTAL | PORTFOLIO TO DATE TOTAL
Standard | 0.038528 | -0.20779 | -0.85455 | 0.098001 | -0.92581 | 0.15116 | -0.025315 | -0.10782 | -0.21559 | -0.19756
Custom | 0.010407 | 0.039574 | -2.8946 | -0.89709 | -3.7417 | -0.081413 | 0.0080407 | -0.77309 | -2.4063 | -3.2527
Retro-commissioning | 0 | 0 | -0.042726 | -0.43635 | -0.47907 | 0.084196 | -0.12313 | -0.16188 | 0.4271 | 0.22629
New Construction | 0 | 0.034551 | -0.15142 | -0.65375 | -0.77062 | -0.11823 | 0.44668 | 0.59632 | 0.26699 | 1.1918
Business Subtotal | 0.048935 | -0.13366 | -3.9433 | -1.8892 | -5.9172 | 0.035714 | 0.30628 | -0.44647 | -1.9278 | -2.0322
Lighting | 0.31968 | 0.93503 | 1.424 | 1.5826 | 4.2613 | 0.83575 | 0.97768 | 0.6413 | 0.51404 | 2.9688
Energy Efficient Products | -0.07375 | -0.32383 | 0.015416 | 1.1352 | 0.75307 | -0.44276 | -0.59642 | -0.33419 | -0.11904 | -1.4924
HVAC | -0.26146 | -1.9365 | -0.49506 | 0.15728 | -2.5358 | -1.1384 | -6.3265 | -1.2497 | -1.1249 | -9.8395
Refrigerator Recycling | -0.18737 | -0.24225 | -0.042229 | -0.011736 | -0.48358 | -0.1381 | -0.0929 | 0.065226 | -0.017888 | -0.18366
Home Energy Performance | -0.0034363 | -0.16095 | -0.10199 | -0.050901 | -0.31728 | -0.048706 | -0.093592 | -0.08799 | -0.048923 | -0.27921
New Homes | 0 | -0.020484 | -0.035359 | 0.046421 | -0.0094223 | -0.020488 | -0.059312 | -0.034489 | -0.0589 | -0.17319
Low Income | -0.08107 | -0.025141 | 0.1296 | -0.069669 | -0.046277 | -0.18441 | 0.22772 | -0.014272 | -0.21607 | -0.18704
Residential Subtotal | -0.28741 | -1.7742 | 0.89434 | 2.7893 | 1.622 | -1.1371 | -5.9633 | -1.0141 | -1.0716 | -9.1862
Quarterly Total Program (MW) | -0.23847 | -1.9078 | -3.0489 | 0.90007 | -4.2952 | -1.1014 | -5.657 | -1.4606 | -2.9994 | -11.2185
Cumulative Total Program (MW) | -0.23847 | -2.1463 | -5.1952 | -4.2952 |  | -5.3966 | -11.0536 | -12.5142 | -15.5136
Programs' Demand Savings vs. Targets (%) Variance | 1ST QUARTER | 2ND QUARTER | 3RD QUARTER | 4TH QUARTER | 1ST YTD TOTAL | 5TH QUARTER | 6TH QUARTER | 7TH QUARTER | 8TH QUARTER | 2ND YTD TOTAL | 9TH QUARTER | 10TH QUARTER | 11TH QUARTER | 12TH QUARTER | 3RD YTD TOTAL | PORTFOLIO TO DATE TOTAL
Standard | 36.41% | -23.71% | -46.22% | 5.733% | -20.39% | 16.33% | -1.872% | -6.058% | -9.768% | -3.153%
Custom | 43.77% | 2.879% | -64.03% | -12.63% | -28.73% | -3.702% | 0.2502% | -18.28% | -45.88% | -21.85%
Retro-commissioning |  |  | -45.18% | -100% | -90.24% | 99.94% | -100% | -99.92% | 212.6% | 39.68%
New Construction |  |  | -106.6% | -99.75% | -96.64% | -65.77% | 170% | 172.5% | 62.28% | 97.94%
Business Subtotal | 37.76% | -5.938% | -59.69% | -19.07% | -31.32% | 1.054% | 6.184% | -6.851% | -23.86% | -8.859%
Lighting | 48.32% | 96.79% | 155.9% | 143% | 116.8% | 101.2% | 144.9% | 100.5% | 66.52% | 102%
Energy Efficient Products | -102.6% | -95.56% | 3.661% | 257.1% | 59.14% | -59.61% | -94.9% | -58.65% | -19.49% | -58.48%
HVAC | -35.25% | -43.52% | -10.27% | 6.696% | -20.51% | -37.89% | -63.18% | -17.22% | -27.93% | -40.49%
Refrigerator Recycling | -49.88% | -53.25% | -9.703% | -3.173% | -29.56% | -40.37% | -18.91% | 12.98% | -5.448% | -11.04%
Home Energy Performance | -97.65% | -97.31% | -87.83% | -76.13% | -90.16% | -69.14% | -89.18% | -83.84% | -69.64% | -79.64%
New Homes |  | -100% | -95.33% | 187.7% | -11.45% | -30.25% | -97.71% | -59.7% | -68.88% | -63.74%
Low Income | -55.32% | -10.33% | 58.59% | -42.71% | -5.977% | -115.8% | 86.13% | -5.938% | -121.9% | -22.23%
Residential Subtotal | -14.36% | -26.72% | 12.84% | 61.69% | 8.059% | -21.82% | -48.73% | -10.82% | -17.65% | -27.93%
Quarterly Total Program (MW) | -11.19% | -21.46% | -22.47% | 6.239% | -11.01% | -12.81% | -32.91% | -9.192% | -21.19% | -20.09%
Cumulative Total Program (MW) | -11.19% | -19.48% | -21.13% | -11.01% |  | -11.33% | -17.06% | -15.51% | -16.36%
* The financial information contained within this report is confidential and may contain immaterial revisions from other company financial statements.

## Gross Benefits (Avoided Costs)
DSM Advisory Group Annual Report: Programs' and Portfolio Gross Benefits vs. Plan | Utility: Ameren Missouri |  |  |  |  | Utility: Ameren Missouri |  |  |  |  | Utility: Ameren Missouri
| Report Date: 02/26/2015 |  |  |  |  | Report Date: 02/26/2015 |  |  |  |  | Report Date: 02/26/2015
| Period: 01/02/13 - 12/31/13 |  |  |  |  | Period: 01/02/14 - 12/31/14 |  |  |  |  | Period: 01/02/15 - 12/31/15
| Portfolio Start Date: 01/02/2013 |  |  |  |  | Portfolio Start Date: 01/02/2013 |  |  |  |  | Portfolio Start Date: 01/02/2013
Programs' Gross Benefits (Recorded) | 1ST QUARTER | 2ND QUARTER | 3RD QUARTER | 4TH QUARTER | 1ST YTD TOTAL | 5TH QUARTER | 6TH QUARTER | 7TH QUARTER | 8TH QUARTER | 2ND YTD TOTAL | 9TH QUARTER | 10TH QUARTER | 11TH QUARTER | 12TH QUARTER | 3RD YTD TOTAL | PORTFOLIO TO DATE TOTAL
Standard | 541574.5005 | 3059352.5417 | 4183808.4193 | 7254256.7001 | 15038992.1616 | 4657177.0778 | 6151386.7857 | 7878493.0777 | 9581261.099 | 28268318.0401
Custom | 140313.4749 | 6356219.9185 | 9127505.5245 | 26981016.1012 | 42605055.0191 | 10595668.5616 | 17816855.1563 | 17794546.4181 | 15138309.1043 | 61345379.2403
Retro-commissioning | 0 | 0 | 172341.2235 | 0 | 172341.2235 | 566444.6141 | 0 | 133521.9183 | 6293448.7609 | 6993415.2933
New Construction | 0 | 170892.7779 | -46505.729 | 8239.3098 | 132626.3587 | 285173.9603 | 3245499.2994 | 4201159.6766 | 2777644.3116 | 10509477.2478
Business Subtotal | 681887.9754 | 9586465.2381 | 13437149.4383 | 34243512.1111 | 57949014.7628 | 16104464.2137 | 27213741.2414 | 30007721.0906 | 33790663.2758 | 107116589.8215
Lighting | 9226372.3092 | 17652250.51 | 21825147.1417 | 25021264.0792 | 73725034.0402 | 15388552.1687 | 16120244.3816 | 14392659.7772 | 15477093.1042 | 61378549.4317
Energy Efficient Products | 105622.7928 | 219814.5866 | 2186961.4775 | 6467841.9435 | 8980240.8003 | 1716654.5361 | 224091.5428 | 1226098.4499 | 2660129.6875 | 5826974.2163
HVAC | 1172420.3032 | 6267663.6255 | 11178137.2199 | 7662327.8257 | 26280548.9743 | 5987321.7184 | 9055205.4514 | 15935627.9151 | 8781581.8915 | 39759736.9764
Refrigerator Recycling | 535236.7819 | 617105.2733 | 1133866.8962 | 1039050.5269 | 3325259.4782 | 610167.7222 | 1176619.7142 | 1667026.6645 | 915054.8533 | 4368868.9543
Home Energy Performance | 640.7694 | 31384.8865 | 78344.6535 | 84827.4696 | 195197.779 | 101307.0978 | 82551.7685 | 121216.7465 | 123594.2167 | 428669.8294
New Homes | 0 | 0 | 20939.5238 | 339138.4082 | 360077.932 | 231781.2162 | 7335.4228 | 305354.2754 | 137806.3687 | 682277.2831
Low Income | 533658.7837 | 1189601.755 | 1541346.9472 | 1362941.074 | 4627548.5599 | 505938.1651 | 1641940.8582 | 948927.7311 | 1069310.0888 | 4166116.8433
Residential Subtotal | 11573951.7402 | 25977820.6369 | 37964743.8599 | 41977391.3271 | 117493907.564 | 24541722.6245 | 28307989.1395 | 34596911.5599 | 29164570.2107 | 116611193.5345
Quarterly Total Program (Gross Benefits) | 12255839.7156 | 35564285.8749 | 51401893.2982 | 76220903.4382 | 175442922.3268 | 40646186.8381 | 55521730.3809 | 64604632.6505 | 62955233.4865 | 223727783.356
Cumulative Total Program (Gross Benefits) | 12255839.7156 | 47820125.5905 | 99222018.8887 | 175442922.3268 |  | 216089109.165 | 271610839.5459 | 336215472.1963 | 399170705.6828
Programs' Planned Gross Benefits (MEEIA Plan) | 1ST QUARTER | 2ND QUARTER | 3RD QUARTER | 4TH QUARTER | 1ST YTD TOTAL | 5TH QUARTER | 6TH QUARTER | 7TH QUARTER | 8TH QUARTER | 2ND YTD TOTAL | 9TH QUARTER | 10TH QUARTER | 11TH QUARTER | 12TH QUARTER | 3RD YTD TOTAL | PORTFOLIO TO DATE TOTAL
Standard | 533381.8872 | 4416400.1138 | 5819248.3461 | 5962627.8345 | 16731658.1817 | 3109107.4964 | 4544080.1871 | 5979052.8777 | 7414025.5684 | 21046266.1296 | 5565107.3273 | 7352751.5411 | 9178907.1371 | 10072467.6949 | 32169233.7004 | 69947158.0117
Custom | 92622.2775 | 5355100.6914 | 11358826.8699 | 19150145.9716 | 35956695.8103 | 5426329.7786 | 7930789.6764 | 10435249.5742 | 12939709.4719 | 36732078.501 | 9483689.9995 | 12530075.7304 | 15642090.0269 | 17164837.1776 | 54820692.9344 | 127509467.2456
Retro-commissioning | 0 | 0 | 252435.9573 | 1087353.0151 | 1339788.9724 | 193366.5917 | 282612.7109 | 371858.8301 | 461104.9493 | 1308943.082 | 263741.5969 | 348461.6413 | 435006.8173 | 477354.4441 | 1524564.4996 | 4173296.554
New Construction | 0 | 0 | 380201.0589 | 1637693.6636 | 2017894.7225 | 409566.464 | 598597.1397 | 787627.8154 | 976658.4912 | 2772449.9104 | 763554.0534 | 1008825.6906 | 1259381.2371 | 1381981.1702 | 4413742.1514 | 9204086.7842
Business Subtotal | 626004.1647 | 9771500.8052 | 17810712.2322 | 27837820.4848 | 56046037.6868 | 9138370.3307 | 13356079.7141 | 17573789.0974 | 21791498.4808 | 61859737.623 | 16076092.9772 | 21240114.6034 | 26515385.2184 | 29096640.4868 | 92928233.2858 | 210834008.5956
Lighting | 8513072.4443 | 12430592.5071 | 11752560.1886 | 14238678.69 | 46934903.83 | 10969093.0953 | 8960228.8188 | 8471489.0651 | 10263534.8288 | 38664345.808 | 7418401.5489 | 6059805.9266 | 5729271.0578 | 6941232.2432 | 26148710.7765 | 111747960.4145
Energy Efficient Products | 246546.081 | 1162288.6674 | 1444055.6171 | 1514497.3545 | 4367387.72 | 2680692.3448 | 2268267.4326 | 2056373.5855 | 2204616.9217 | 9209950.2846 | 3285759.8209 | 4107199.7761 | 3723519.109 | 3991946.4507 | 15108425.1567 | 28685763.1613
HVAC | 1114520.411 | 6686447.4085 | 7243370.0851 | 3529202.1253 | 18573540.03 | 5006930.8882 | 16688713.9808 | 12098763.4217 | 6711500.1321 | 40505908.4228 | 8941670.7237 | 24594012.3118 | 20868647.6474 | 14162063.1341 | 68566393.817 | 127645842.2699
Refrigerator Recycling | 1398293.7506 | 1693455.9709 | 1620112.6313 | 1376827.4073 | 6088689.76 | 1296642.6401 | 1861845.8422 | 1904592.3029 | 1244396.966 | 6307477.7512 | 1629489.9358 | 2429312.8346 | 2363655.731 | 1002763.0374 | 7425221.5387 | 19821389.0499
Home Energy Performance | 10084.9928 | 473994.6616 | 332804.7624 | 191614.8632 | 1008499.28 | 203037.6071 | 302475.3934 | 302475.3934 | 202474.8408 | 1010463.2347 | 264545.4896 | 315005.3754 | 314843.6797 | 116030.7166 | 1010425.2613 | 3029387.776
New Homes | 0 | 103884.198 | 188098.0152 | 125398.6768 | 417380.89 | 262772.2004 | 235545.2013 | 224147.8528 | 331789.4771 | 1054254.7316 | 544448.9013 | 488477.519 | 465943.5858 | 686921.511 | 2185791.5171 | 3657427.1387
Low Income | 734330.2394 | 1219265.3031 | 1108423.0029 | 817461.9646 | 3879480.51 | 699341 | 1161169.9623 | 1055609.0566 | 778511.6793 | 3694631.6982 | 584360.1257 | 970258.3219 | 882053.0199 | 650514.1022 | 3087185.5696 | 10661297.7778
Residential Subtotal | 12016847.9191 | 23769928.7166 | 23689424.3025 | 21793681.0818 | 81269882.02 | 21118509.7759 | 31478246.6315 | 26113450.678 | 21736824.8457 | 100447031.9311 | 22668676.5459 | 38964072.0653 | 34347933.8306 | 27551471.1952 | 123532153.637 | 305249067.5882
Quarterly Total Program (Gross Benefits) | 12642852.0838 | 33541429.5218 | 41500136.5347 | 49631501.5665 | 137315919.7068 | 30256880.1066 | 44834326.3456 | 43687239.7755 | 43528323.3266 | 162306769.5542 | 38744769.523 | 60204186.6687 | 60863319.049 | 56648111.682 | 216460386.9228 | 516083076.1838
Cumulative Total Program (Gross Benefits) | 12642852.0838 | 46184281.6056 | 87684418.1403 | 137315919.7068 |  | 167572799.8134 | 212407126.1589 | 256094365.9344 | 299622689.261 |  | 338367458.784 | 398571645.4527 | 459434964.5018 | 516083076.1838 | 516083076.1838
Programs' Gross Benefits ($) Variance | 1ST QUARTER | 2ND QUARTER | 3RD QUARTER | 4TH QUARTER | 1ST YTD TOTAL | 5TH QUARTER | 6TH QUARTER | 7TH QUARTER | 8TH QUARTER | 2ND YTD TOTAL | 9TH QUARTER | 10TH QUARTER | 11TH QUARTER | 12TH QUARTER | 3RD YTD TOTAL | PORTFOLIO TO DATE TOTAL
Standard | 8192.6133 | -1357047.5721 | -1635439.9268 | 1291628.8655 | -1692666.0201 | 1548069.5813 | 1607306.5986 | 1899440.1999 | 2167235.5306 | 7222051.9104
Custom | 47691.1974 | 1001119.2271 | -2231321.3453 | 7830870.1296 | 6648359.2088 | 5169338.783 | 9886065.48 | 7359296.8439 | 2198599.6324 | 24613300.7392
Retro-commissioning | 0 | 0 | -80094.7339 | -1087353.0151 | -1167447.7489 | 373078.0224 | -282612.7109 | -238336.9118 | 5832343.8116 | 5684472.2113
New Construction | 0 | 170892.7779 | -426706.7879 | -1629454.3538 | -1885268.3638 | -124392.5038 | 2646902.1596 | 3413531.8612 | 1800985.8204 | 7737027.3375
Business Subtotal | 55883.8107 | -185035.5671 | -4373562.7939 | 6405691.6263 | 1902977.076 | 6966093.883 | 13857661.5274 | 12433931.9932 | 11999164.7949 | 45256852.1985
Lighting | 713299.865 | 5221658.0029 | 10072586.9531 | 10782585.3892 | 26790130.2102 | 4419459.0734 | 7160015.5628 | 5921170.7122 | 5213558.2754 | 22714203.6237
Energy Efficient Products | -140923.2882 | -942474.0809 | 742905.8604 | 4953344.589 | 4612853.0803 | -964037.8087 | -2044175.8899 | -830275.1355 | 455512.7658 | -3382976.0683
HVAC | 57899.8922 | -418783.783 | 3934767.1348 | 4133125.7003 | 7707008.9443 | 980390.8302 | -7633508.5294 | 3836864.4934 | 2070081.7594 | -746171.4464
Refrigerator Recycling | -863056.9687 | -1076350.6976 | -486245.7351 | -337776.8804 | -2763430.2818 | -686474.9179 | -685226.128 | -237565.6383 | -329342.1126 | -1938608.7969
Home Energy Performance | -9444.2234 | -442609.7751 | -254460.1089 | -106787.3936 | -813301.501 | -101730.5093 | -219923.6249 | -181258.6469 | -78880.6241 | -581793.4052
New Homes | 0 | -103884.198 | -167158.4914 | 213739.7314 | -57302.958 | -30990.9842 | -228209.7785 | 81206.4226 | -193983.1083 | -371977.4485
Low Income | -200671.4557 | -29663.5482 | 432923.9444 | 545479.1094 | 748068.0499 | -193402.8349 | 480770.8959 | -106681.3255 | 290798.4096 | 471485.1451
Residential Subtotal | -442896.1789 | 2207891.9202 | 14275319.5573 | 20183710.2453 | 36224025.544 | 3423212.8486 | -3170257.492 | 8483460.8818 | 7427745.365 | 16164161.6034
Quarterly Total Program (Benefits) | -387012.3682 | 2022856.3531 | 9901756.7635 | 26589401.8716 | 38127002.62 | 10389306.7316 | 10687404.0353 | 20917392.875 | 19426910.16 | 61421013.8018
Cumulative Total Program (Benefits) | -387012.3682 | 1635843.9849 | 11537600.7484 | 38127002.62 |  | 48516309.3516 | 59203713.3869 | 80121106.2619 | 99548016.4218
Programs' Gross Benefits (%) Variance | 1ST QUARTER | 2ND QUARTER | 3RD QUARTER | 4TH QUARTER | 1ST YTD TOTAL | 5TH QUARTER | 6TH QUARTER | 7TH QUARTER | 8TH QUARTER | 2ND YTD TOTAL | 9TH QUARTER | 10TH QUARTER | 11TH QUARTER | 12TH QUARTER | 3RD YTD TOTAL | PORTFOLIO TO DATE TOTAL
Standard | 1.536% | -30.73% | -28.1% | 21.66% | -10.12% | 49.79% | 35.37% | 31.77% | 29.23% | 34.32%
Custom | 51.49% | 18.69% | -19.64% | 40.89% | 18.49% | 95.26% | 124.7% | 70.52% | 16.99% | 67.01%
Retro-commissioning |  |  | -31.73% | -100% | -87.14% | 192.9% | -100% | -64.09% | 1265% | 434.3%
New Construction |  |  | -112.2% | -99.5% | -93.43% | -30.37% | 442.2% | 433.4% | 184.4% | 279.1%
Business Subtotal | 8.927% | -1.894% | -24.56% | 23.01% | 3.395% | 76.23% | 103.8% | 70.75% | 55.06% | 73.16%
Lighting | 8.379% | 42.01% | 85.71% | 75.73% | 57.08% | 40.29% | 79.91% | 69.9% | 50.8% | 58.75%
Energy Efficient Products | -57.16% | -81.09% | 51.45% | 327.1% | 105.6% | -35.96% | -90.12% | -40.38% | 20.66% | -36.73%
HVAC | 5.195% | -6.263% | 54.32% | 117.1% | 41.49% | 19.58% | -45.74% | 31.71% | 30.84% | -1.842%
Refrigerator Recycling | -61.72% | -63.56% | -30.01% | -24.53% | -45.39% | -52.94% | -36.8% | -12.47% | -26.47% | -30.74%
Home Energy Performance | -93.65% | -93.38% | -76.46% | -55.73% | -80.64% | -50.1% | -72.71% | -59.93% | -38.96% | -57.58%
New Homes |  | -100% | -88.87% | 170.4% | -13.73% | -11.79% | -96.89% | 36.23% | -58.47% | -35.28%
Low Income | -27.33% | -2.433% | 39.06% | 66.73% | 19.28% | -27.66% | 41.4% | -10.11% | 37.35% | 12.76%
Residential Subtotal | -3.686% | 9.289% | 60.26% | 92.61% | 44.57% | 16.21% | -10.07% | 32.49% | 34.17% | 16.09%
Quarterly Total Program (Gross Benefits) | -3.061% | 6.031% | 23.86% | 53.57% | 27.77% | 34.34% | 23.84% | 47.88% | 44.63% | 37.84%
Cumulative Total Program (Gross Benefits) | -3.061% | 3.542% | 13.16% | 27.77% |  | 28.95% | 27.87% | 31.29% | 33.22%
*Benefits have been calculated using the DSMore model used in the MEEIA filling.
* The financial information contained within this report is confidential and may contain immaterial revisions from other company financial statements.

## Net Benefits
Annual Report: Programs' and Portfolio Net Benefits vs. Plan | Utility: Ameren Missouri |  |  |  |  | Utility: Ameren Missouri |  |  |  |  | Utility: Ameren Missouri
| Report Date: 02/26/2015 |  |  |  |  | Report Date: 02/26/2015 |  |  |  |  | Report Date: 02/26/2015
| Period: 01/02/13 - 12/31/13 |  |  |  |  | Period: 01/02/14 - 12/31/14 |  |  |  |  | Period: 01/02/15 - 12/31/15
| Portfolio Start Date: 01/02/2013 |  |  |  |  | Portfolio Start Date: 01/02/2013 |  |  |  |  | Portfolio Start Date: 01/02/2013
Programs' Net Benefits (Recorded) | 1ST QUARTER | 2ND QUARTER | 3RD QUARTER | 4TH QUARTER | 1ST YTD TOTAL | 5TH QUARTER | 6TH QUARTER | 7TH QUARTER | 8TH QUARTER | 2ND YTD TOTAL | 9TH QUARTER | 10TH QUARTER | 11TH QUARTER | 12TH QUARTER | 3RD YTD TOTAL | PORTFOLIO TO DATE TOTAL
Standard | 302356.4905 | 2395341.4117 | 3767520.2093 | 6249943.2601 | 12715161.3716 | 4027987.2133 | 5446745.3551 | 6932225.2703 | 8200466.5782 | 24607424.4169
Custom | -633415.4951 | 4982011.6885 | 7162557.2645 | 24512570.8012 | 36023724.2591 | 8968043.7275 | 15425352.7253 | 15772847.8767 | 14148959.9131 | 54315204.2426
Retro-commissioning | -124245 | -62707.68 | 112002.2435 | -73343.27 | -148293.7065 | 283881.2574 | -91685.6662 | 14689.3891 | 5153787.8166 | 5360672.7968
New Construction | -93183.75 | 61988.9379 | -89159.559 | -112013.5202 | -232367.8913 | 200226.5269 | 2788370.6411 | 3613689.2044 | 2414969.772 | 9017256.1445
Business Subtotal | -548487.7546 | 7376634.3581 | 10952920.1583 | 30577157.2711 | 48358224.0328 | 13480138.7251 | 23568783.0554 | 26333451.7404 | 29918184.0799 | 93300557.6008
Lighting | 8088365.8992 | 16467699.41 | 19540440.8917 | 22551313.6792 | 66647819.8802 | 13386814.3192 | 14013613.4419 | 12679546.1447 | 13938796.9471 | 54018770.8529
Energy Efficient Products | -95447.7172 | 72866.5966 | 1782007.4275 | 5827802.5535 | 7587228.8603 | 1193779.2392 | -94759.5372 | 940863.5084 | 2171879.7857 | 4211762.9961
HVAC | 798459.2032 | 4728068.6555 | 9374976.7999 | 6415043.1557 | 21316547.8143 | 4959137.2209 | 7396169.2382 | 13507428.205 | 7230985.8466 | 33093720.5108
Refrigerator Recycling | 360962.4519 | 327225.8333 | 800401.9462 | 777885.9369 | 2266476.1682 | 446801.2706 | 818814.1789 | 1228470.4327 | 683111.2161 | 3177197.0983
Home Energy Performance | 640.7694 | -369.7335 | -8086.0465 | 21144.1796 | 13329.169 | 32530.2862 | 10878.2575 | 31894.0443 | 50981.7249 | 126284.3128
New Homes | -77520.87 | -118905.78 | -91610.9462 | 239666.1582 | -48371.438 | 133369.3789 | -64275.6478 | 218161.4096 | 99262.077 | 386517.2176
Low Income | 40723.4537 | 212000.175 | 210482.2172 | 345455.054 | 808660.8999 | 70540.8019 | 336216.3141 | 193266.8054 | 256651.2482 | 856675.1696
Residential Subtotal | 9116183.1902 | 21688585.1569 | 31608612.2899 | 36178310.7171 | 98591691.354 | 20222972.5169 | 22416656.2456 | 28799630.55 | 24431668.8456 | 95870928.1582
EM&V Subtotal | -19120.45 | -812215.48 | -618094.07 | -1100021.97 | -2549451.97 | -502057.8027 | -283159.3642 | -618327.8167 | -354366.3114 | -1757911.295
Portfolio Subtotal | -1409309.21 | -755539.31 | -551143.03 | -673951.45 | -3389943 | -671548.7892 | -1120567.3399 | -426800.1122 | -286968.2468 | -2505884.4881
Quarterly Total Program (Net Benefits) | 7139265.7756 | 27497464.7249 | 41392295.3482 | 64981494.5682 | 141010520.4168 | 32529504.6502 | 44581712.5969 | 54087954.3615 | 53708518.3673 | 184907689.9759
Cumulative Total Program (Net Benefits) | 7139265.7756 | 34636730.5005 | 76029025.8487 | 141010520.4168 |  | 173540025.067 | 218121737.6639 | 272209692.0254 | 325918210.3927
Programs' Net Benefits (Approved Plan) | 1ST QUARTER | 2ND QUARTER | 3RD QUARTER | 4TH QUARTER | 1ST YTD TOTAL | 5TH QUARTER | 6TH QUARTER | 7TH QUARTER | 8TH QUARTER | 2ND YTD TOTAL | 9TH QUARTER | 10TH QUARTER | 11TH QUARTER | 12TH QUARTER | 3RD YTD TOTAL | PORTFOLIO TO DATE TOTAL
Standard | 430666.4784 | 3565916.8967 | 4698613.2298 | 4814381.5768 | 13509578.1817 | 2436686.6541 | 3561311.2636 | 4685935.8732 | 5810560.4828 | 16494494.2736 | 4563052.3899 | 5832775.198 | 7141009.3884 | 7593380.2267 | 25130217.203 | 55134289.6583
Custom | 71094.403 | 4110433.2255 | 8718734.1675 | 14699144.0143 | 27599405.8103 | 4205250.2597 | 6146134.9949 | 8087019.7301 | 10027904.4654 | 28466309.4501 | 7849249.8632 | 10050860.0221 | 12318098.7465 | 13121226.4847 | 43339435.1166 | 99405150.3769
Retro-commissioning | 0 | 0 | 204358.1745 | 880260.7979 | 1084618.9724 | 157258.7035 | 229839.6436 | 302420.5837 | 375001.5238 | 1064520.4546 | 223723.8182 | 287760.3017 | 353621.9169 | 378350.3176 | 1243456.3544 | 3392595.7814
New Construction | 0 | 0 | 257718.3052 | 1110106.4173 | 1367824.7225 | 267270.3613 | 390625.9127 | 513981.4641 | 637337.0155 | 1809214.7538 | 540132.0342 | 669925.9247 | 805003.7244 | 829234.3024 | 2844295.9857 | 6021335.462
Business Subtotal | 501760.8814 | 7676350.1221 | 13879423.877 | 21503892.8063 | 43561427.6868 | 7066465.9786 | 10327911.8149 | 13589357.6511 | 16850803.4874 | 47834538.932 | 13176158.1055 | 16841321.4465 | 20617733.7763 | 21922191.3314 | 72557404.6597 | 163953371.2786
Lighting | 7381756.1737 | 10778670.5191 | 10190743.0363 | 12346477.1401 | 40697646.8692 | 9397567.4573 | 7676510.1751 | 7257791.4382 | 8793093.4732 | 33124962.5438 | 6472849.6335 | 5112768.3798 | 4781872.0783 | 5995158.5404 | 22362648.6319 | 96185258.045
Energy Efficient Products | 192459.0116 | 907306.7688 | 1127259.9248 | 1182248.2139 | 3409273.919 | 2119110.2164 | 1793084.7975 | 1625580.8997 | 1742768.5244 | 7280544.438 | 2601438.3101 | 3382665.1546 | 3017767.3551 | 3273053.9991 | 12274924.8189 | 22964743.176
HVAC | 913868.3311 | 5482656.4624 | 5939313.8658 | 2893824.1277 | 15229662.787 | 4115202.3347 | 13716473.4786 | 9943987.7626 | 5516189.7836 | 33291853.3595 | 5466609.7347 | 19208553.1527 | 21171133.8475 | 10049843.287 | 55896140.0219 | 104417656.1683
Refrigerator Recycling | 1021884.07 | 1237590.9419 | 1183991.0525 | 1006196.2975 | 4449662.3618 | 964478.788 | 1384892.6186 | 1416688.6226 | 925617.0053 | 4691677.0346 | 1214676.1811 | 1929568.4571 | 1870883.2654 | 654499.3907 | 5669627.2943 | 14810966.6908
Home Energy Performance | 5774.648 | 271408.4547 | 190563.3831 | 109718.3115 | 577464.7972 | 120972.3872 | 180218.6843 | 180218.6843 | 120637.0839 | 602046.8397 | 164046.7306 | 200395.0984 | 200278.6203 | 57065.411 | 621785.8603 | 1801297.4973
New Homes | 0 | 67986.3188 | 123099.4885 | 82066.3257 | 273152.133 | 148493.32 | 133107.2651 | 126666.591 | 187495.1799 | 595762.3561 | 272178.5131 | 239403.9789 | 226209.0339 | 355604.6156 | 1093396.1414 | 1962310.6305
Low Income | 142588.8994 | 236751.3801 | 215228.5274 | 158731.0389 | 753299.8458 | 35863.5682 | 59547.0566 | 54133.6879 | 39923.5948 | 189467.9075 | -53635.2951 | -97496.6159 | -87471.1694 | -61154.3749 | -299757.4552 | 643010.2981
Residential Subtotal | 9658331.1337 | 18982370.8458 | 18970199.2784 | 17779261.4552 | 65390162.7131 | 16901688.0718 | 24943834.0758 | 20605067.6864 | 17325724.6452 | 79776314.4792 | 16138163.808 | 29975857.6055 | 31180673.0311 | 20324070.8689 | 97618765.3135 | 242785242.5059
EM&V Subtotal | -164360.3841 | -354913.505 | -420407.638 | -522148.4729 | -1461830 | -348171.7163 | -464708.5924 | -476121.4506 | -510512.0323 | -1799513.7915 | -417405.4418 | -595506.696 | -682621.3934 | -694025.584 | -2389559.1151 | -5650902.9066
Portfolio Subtotal | -707567.1642 | -1527893.3766 | -1809843.9099 | -2247835.5493 | -6293140 | -1463322.3528 | -1953112.3262 | -2001079.1475 | -2145618.4784 | -7563132.3048 | -1284807.0124 | -1833016.7802 | -2101162.719 | -2136265.721 | -7355252.2326 | -21211524.5374
Quarterly Total Program (Net Benefits) | 9288164.4667 | 24775914.0863 | 30619371.6076 | 36513170.2393 | 101196620.4 | 22156659.9813 | 32853924.9722 | 31717224.7395 | 31520397.622 | 118248207.315 | 27612109.4594 | 44388655.5758 | 49014622.695 | 39415970.8954 | 160431358.6256 | 379876186.3405
Cumulative Total Program (Net Benefits) | 9288164.4667 | 34064078.5531 | 64683450.1606 | 101196620.4 |  | 123353280.3813 | 156207205.3534 | 187924430.0929 | 219444827.7149 |  | 247056937.1743 | 291445592.7501 | 340460215.4451 | 379876186.3405 |  | 379876186.3405
Programs' Net Benefits ($) Variance | 1ST QUARTER | 2ND QUARTER | 3RD QUARTER | 4TH QUARTER | 1ST YTD TOTAL | 5TH QUARTER | 6TH QUARTER | 7TH QUARTER | 8TH QUARTER | 2ND YTD TOTAL | 9TH QUARTER | 10TH QUARTER | 11TH QUARTER | 12TH QUARTER | 3RD YTD TOTAL | PORTFOLIO TO DATE TOTAL
Standard | -128309.9878 | -1170575.485 | -931093.0206 | 1435561.6833 | -794416.8101 | 1591300.5593 | 1885434.0915 | 2246289.3971 | 2389906.0954 | 8112930.1433
Custom | -704509.8981 | 871578.463 | -1556176.9029 | 9813426.7868 | 8424318.4488 | 4762793.4678 | 9279217.7304 | 7685828.1466 | 4121055.4477 | 25848894.7925
Retro-commissioning | -124245 | -62707.68 | -92355.931 | -953604.0679 | -1232912.6789 | 126622.5539 | -321525.3098 | -287731.1946 | 4778786.2928 | 4296152.3422
New Construction | -93183.75 | 61988.9379 | -346877.8641 | -1222119.9376 | -1600192.6138 | -67043.8344 | 2397744.7284 | 3099707.7403 | 1777632.7565 | 7208041.3908
Business Subtotal | -1050248.636 | -299715.7641 | -2926503.7187 | 9073264.4647 | 4796796.346 | 6413672.7465 | 13240871.2405 | 12744094.0893 | 13067380.5925 | 45466018.6688
Lighting | 706609.7255 | 5689028.8909 | 9349697.8554 | 10204836.5391 | 25950173.0109 | 3989246.8619 | 6337103.2669 | 5421754.7065 | 5145703.4738 | 20893808.3091
Energy Efficient Products | -287906.7288 | -834440.1722 | 654747.5026 | 4645554.3397 | 4177954.9413 | -925330.9772 | -1887844.3346 | -684717.3914 | 429111.2613 | -3068781.4419
HVAC | -115409.1279 | -754587.8068 | 3435662.9341 | 3521219.0279 | 6086885.0273 | 843934.8862 | -6320304.2404 | 3563440.4424 | 1714796.063 | -198132.8487
Refrigerator Recycling | -660921.6181 | -910365.1086 | -383589.1063 | -228310.3606 | -2183186.1936 | -517677.5174 | -566078.4398 | -188218.19 | -242505.7892 | -1514479.9363
Home Energy Performance | -5133.8786 | -271778.1882 | -198649.4296 | -88574.1319 | -564135.6282 | -88442.101 | -169340.4268 | -148324.64 | -69655.3591 | -475762.5269
New Homes | -77520.87 | -186892.0988 | -214710.4347 | 157599.8326 | -321523.5709 | -15123.9411 | -197382.913 | 91494.8186 | -88233.1029 | -209245.1384
Low Income | -101865.4457 | -24751.2051 | -4746.3101 | 186724.015 | 55361.0541 | 34677.2337 | 276669.2574 | 139133.1176 | 216727.6535 | 667207.2621
Residential Subtotal | -542147.9435 | 2706214.3111 | 12638413.0114 | 18399049.2619 | 33201528.6409 | 3321284.4451 | -2527177.8302 | 8194562.8637 | 7105944.2004 | 16094613.679
EM&V Subtotal | 145239.9341 | -457301.975 | -197686.432 | -577873.4971 | -1087621.97 | -153886.0864 | 181549.2282 | -142206.3662 | 156145.7209 | 41602.4965
Portfolio Subtotal | -701742.0458 | 772354.0666 | 1258700.8799 | 1573884.0993 | 2903197 | 791773.5636 | 832544.9863 | 1574279.0352 | 1858650.2316 | 5057247.8167
Quarterly Total Program (Net Benefits) | -2148898.6911 | 2721550.6386 | 10772923.7406 | 28468324.3288 | 39813900.0169 | 10372844.6689 | 11727787.6247 | 22370729.622 | 22188120.7453 | 66659482.661
Cumulative Total Program (Net Benefits) | -2148898.6911 | 572651.9475 | 11345575.688 | 39813900.0169 |  | 50186744.6857 | 61914532.3105 | 84285261.9325 | 106473382.6778
Programs' Net Benefits (%) Variance | 1ST QUARTER | 2ND QUARTER | 3RD QUARTER | 4TH QUARTER | 1ST YTD TOTAL | 5TH QUARTER | 6TH QUARTER | 7TH QUARTER | 8TH QUARTER | 2ND YTD TOTAL | 9TH QUARTER | 10TH QUARTER | 11TH QUARTER | 12TH QUARTER | 3RD YTD TOTAL | PORTFOLIO TO DATE TOTAL
Standard | -29.79% | -32.83% | -19.82% | 29.82% | -5.88% | 65.31% | 52.94% | 47.94% | 41.13% | 49.19%
Custom | -990.9% | 21.2% | -17.85% | 66.76% | 30.52% | 113.3% | 151% | 95.04% | 41.1% | 90.81%
Retro-commissioning |  |  | -45.19% | -108.3% | -113.7% | 80.52% | -139.9% | -95.14% | 1274% | 403.6%
New Construction |  |  | -134.6% | -110.1% | -117% | -25.08% | 613.8% | 603.1% | 278.9% | 398.4%
Business Subtotal | -209.3% | -3.904% | -21.09% | 42.19% | 11.01% | 90.76% | 128.2% | 93.78% | 77.55% | 95.05%
Lighting | 9.572% | 52.78% | 91.75% | 82.65% | 63.76% | 42.45% | 82.55% | 74.7% | 58.52% | 63.08%
Energy Efficient Products | -149.6% | -91.97% | 58.08% | 392.9% | 122.5% | -43.67% | -105.3% | -42.12% | 24.62% | -42.15%
HVAC | -12.63% | -13.76% | 57.85% | 121.7% | 39.97% | 20.51% | -46.08% | 35.84% | 31.09% | -0.5951%
Refrigerator Recycling | -64.68% | -73.56% | -32.4% | -22.69% | -49.06% | -53.67% | -40.88% | -13.29% | -26.2% | -32.28%
Home Energy Performance | -88.9% | -100.1% | -104.2% | -80.73% | -97.69% | -73.11% | -93.96% | -82.3% | -57.74% | -79.02%
New Homes |  | -274.9% | -174.4% | 192% | -117.7% | -10.18% | -148.3% | 72.23% | -47.06% | -35.12%
Low Income | -71.44% | -10.45% | -2.205% | 117.6% | 7.349% | 96.69% | 464.6% | 257% | 542.9% | 352.1%
Residential Subtotal | -5.613% | 14.26% | 66.62% | 103.5% | 50.77% | 19.65% | -10.13% | 39.77% | 41.01% | 20.17%
EM&V Subtotal | -88.37% | 128.8% | 47.02% | 110.7% | 74.4% | 44.2% | -39.07% | 29.87% | -30.59% | -2.312%
Portfolio Subtotal | 99.18% | -50.55% | -69.55% | -70.02% | -46.13% | -54.11% | -42.63% | -78.67% | -86.63% | -66.87%
Quarterly Total Program (Net Benefits) | -23.14% | 10.98% | 35.18% | 77.97% | 39.34% | 46.82% | 35.7% | 70.53% | 70.39% | 56.37%
Cumulative Total Program (Net Benefits) | -23.14% | 1.681% | 17.54% | 39.34% |  | 40.69% | 39.64% | 44.85% | 48.52%
* The financial information contained within this report is confidential and may contain immaterial revisions from other company financial statements.
* 2014 Net Benefits = Benefits - (Costs/1.0695) 2015 Net Benefits = Benefits - (Costs/1.0695^2) This allows comparison of benefits and costs both in 2013 dollars.

## DSIM
DSM Advisory Group Annual Report: Portfolio DSIM Performance Measures | Utility: Ameren Missouri |  |  |  |  | Utility: Ameren Missouri |  |  |  |  | Utility: Ameren Missouri
| Report Date: 02/26/2015 |  |  |  |  | Report Date: 02/26/2015 |  |  |  |  | Report Date: 02/26/2015
| Period: 01/02/13 - 12/31/13 |  |  |  |  | Period: 01/02/14 - 12/31/14 |  |  |  |  | Period: 01/02/15 - 12/31/15
| Portfolio Start Date: 01/02/2013 |  |  |  |  | Portfolio Start Date: 01/02/2013 |  |  |  |  | Portfolio Start Date: 01/02/2013
DSM Programs' Costs | 1ST QUARTER | 2ND QUARTER | 3RD QUARTER | 4TH QUARTER | 1ST YTD TOTAL | 5TH QUARTER | 6TH QUARTER | 7TH QUARTER | 8TH QUARTER | 2ND YTD TOTAL | 9TH QUARTER | 10TH QUARTER | 11TH QUARTER | 12TH QUARTER | 3RD YTD TOTAL | PORTFOLIO TO DATE TOTAL
Billed Programs' Costs | 10373264.39 | 11062034.1 | 13668013.8 | 11654966.05 | 46758278.34 | 11904477.27 | 7578193.34 | 9388754.4 | 7874467.18 | 36745892.19 | 0 | 0 | 0 | 0 | 0 | 83504170.53
Actual Programs' Costs | 5116573.94 | 8066821.15 | 10009597.95 | 11239408.87 | 34432401.91 | 8680791.6 | 11700349.02 | 11247587.43 | 9889361.82 | 41518089.87 | 0 | 0 | 0 | 0 | 0 | 75950491.78
Variance | 5256690.45 | 2995212.95 | 3658415.85 | 415557.18 | 12325876.43 | 3223685.67 | -4122155.68 | -1858833.03 | -2014894.64 | -4772197.68 | 0 | 0 | 0 | 0 | 0 | 7553678.75
Interest for DSM Programs' Cost Recovery | -5874.62 | 1209 | -10008.7039 | -11424.3845 | -26098.7084 | -17581.563 | -10088.6543 | -7467.2661 | -6523.0016 | -41660.485 | 0 | 0 | 0 | 0 | 0 | -67759.1934
Net Benefits | 1ST QUARTER | 2ND QUARTER | 3RD QUARTER | 4TH QUARTER | 1ST YTD TOTAL | 5TH QUARTER | 6TH QUARTER | 7TH QUARTER | 8TH QUARTER | 2ND YTD TOTAL | 9TH QUARTER | 10TH QUARTER | 11TH QUARTER | 12TH QUARTER | 3RD YTD TOTAL | PORTFOLIO TO DATE TOTAL
MEEIA Planned Net Benefits (1) | 9288164.4667 | 24775914.0863 | 30619371.6076 | 36513170.2393 | 101196620.4 | 22156659.9813 | 32853924.9722 | 31717224.7395 | 31520397.622 | 118248207.315 |  |  |  |  | 0 | 219444827.7149
Deemed Net Benefits (2) | 7139265.7756 | 27497464.7249 | 41392295.3482 | 64981494.5682 | 141010520.4168 | 32529504.6502 | 44581712.5969 | 54087954.3615 | 53708518.3673 | 184907689.9759 | 0 | 0 | 0 | 0 | 0 | 325918210.3927
Variance of MEEIA Planned v. Actual Net Shared Benefits | 2148898.6911 | -2721550.6386 | -10772923.7406 | -28468324.3288 | -39813900.0169 | -10372844.6689 | -11727787.6247 | -22370729.622 | -22188120.7453 | -66659482.661 | 0 | 0 | 0 | 0 | 0 | -106473382.6778
Planned Company TD-NSB Share | 1ST QUARTER | 2ND QUARTER | 3RD QUARTER | 4TH QUARTER | 1ST YTD TOTAL | 5TH QUARTER | 6TH QUARTER | 7TH QUARTER | 8TH QUARTER | 2ND YTD TOTAL | 9TH QUARTER | 10TH QUARTER | 11TH QUARTER | 12TH QUARTER | 3RD YTD TOTAL | PORTFOLIO TO DATE TOTAL
100% of MEEIA Planned Company TD-NSB Share (3) | 2446502.5205 | 6525975.7703 | 8065142.4814 | 9617569.041 | 26655189.8133 | 5836064.2391 | 8653723.8377 | 8354316.9964 | 8302472.7336 | 31146577.8068 | 0 | 0 | 0 | 0 | 0 | 57801767.6201
Actual Company TD-NSB Share Disinentive (4) (2013 $) | 1880482.6053 | 7242832.2085 | 10902730.5947 | 17116125.6693 | 37142171.0778 | 8568271.5249 | 11742823.098 | 14246767.1788 | 14146823.7379 | 48704685.5397 | 0 | 0 | 0 | 0 | 0 | 85846856.6174
Variance | 566019.9152 | -716856.4382 | -2837588.1133 | -7498556.6282 | -10486981.2644 | -2732207.2858 | -3089099.2604 | -5892450.1824 | -5844351.0043 | -17558107.7329 | 0 | 0 | 0 | 0 | 0 | -28045088.9973
90% of Planned Company TD-NSB Share | 1ST QUARTER | 2ND QUARTER | 3RD QUARTER | 4TH QUARTER | 1ST YTD TOTAL | 5TH QUARTER | 6TH QUARTER | 7TH QUARTER | 8TH QUARTER | 2ND YTD TOTAL | 9TH QUARTER | 10TH QUARTER | 11TH QUARTER | 12TH QUARTER | 3RD YTD TOTAL | PORTFOLIO TO DATE TOTAL
Billed @ 90% of Planned Company TD-NSB Share | 6275018.65 | 6471334.97 | 8127765.57 | 6856542.76 | 27730661.95 | 12509751.58 | 10364924.55 | 12862793.81 | 10769581.61 | 46507051.55 | 0 | 0 | 0 | 0 | 0 | 74237713.5
Actual Company TD-NSB Share Disinentive (3) | 1880482.6053 | 7242832.2085 | 10902730.5947 | 17116125.6693 | 37142171.0778 | 8568271.5249 | 11742823.098 | 14246767.1788 | 14146823.7379 | 48704685.5397 | 0 | 0 | 0 | 0 | 0 | 85846856.6174
Variance | 4394536.0447 | -771497.2385 | -2774965.0247 | -10259582.9093 | -9411509.1278 | 3941480.0551 | -1377898.548 | -1383973.3688 | -3377242.1279 | -2197633.9897 | 0 | 0 | 0 | 0 | 0 | -11609143.1174
Interest for Company TD-NSB Share Recovery | -57579.7375 | -83508.5251 | -42861.4761 | 92358.143 | -91591.5957 | 37164.8034 | 5692.9667 | 7230.6661 | 11366.736 | 61455.1722 | [5 empty] | -30136.4235
(1) Present value of Net Benefits in the Plan (and DSMore Model) approved by the Commission in Case No. EO-2012-0142.
(2) Present value of Net Benefits derived from using the DSM Model in Note (1) which is re-run to account for (i) the actual number of energy efficiency measures (by type) installed in each month up to that point; (ii) the actual program costs in each month incurred up to that point; and (3) for C&I custom measures for which the TRM does not provide a deemed value, savings determined according to the protocol provided for at pages 85 to 98 of the TRM.
(3) 26.34% of the pre-tax planned Net Benefit calculated using an assumed combined marginal federal/state tax rate of 38.39%.
* The financial information contained within this report is confidential and may contain immaterial revisions from other company financial statements.

## Cost Effectiveness
Annual Report: Programs' and Portfolio Cost Effectiveness Tests | Utility: Ameren Missouri |  |  |  |  | Utility: Ameren Missouri
| Report Date: 02/26/2015 |  |  |  |  | Report Date: 02/26/2015
| Period: 01/02/13 - 12/31/13 |  |  |  |  | Period: 01/02/14 - 12/31/14
| Portfolio Start Date: 01/02/2013 |  |  |  |  | Portfolio Start Date: 01/02/2013
| Program Year 1 |  |  |  |  | Program Year 2
Deemed Cost Effectiveness Tests (Ameren run model) (note that only the Portfolio level tests include BTL costs) | TRC | UCT | Participant Test | Non-Partic'p't Test | Societal Test | TRC | UCT | Participant Test | Non-Partic'p't Test | Societal Test
Standard | 2.79 | 6.47 | 4.35 | 0.79 |  | 3.5243 | 7.6181 | 5.003 | 0.81583 | 4.3118
Custom | 2.07 | 6.47 | 2.57 | 0.9 |  | 2.2686 | 8.7542 | 2.6404 | 0.89709 | 2.7814
Retro-commissioning | 0.54 | 0.54 | 9.8 | 0.36 |  | 4.3462 | 4.3208 | 8.4689 | 0.84957 | 5.2028
New Construction | 0.34 | 0.36 | 3.64 | 0.26 |  | 1.753 | 7.0934 | 1.9736 | 0.91483 | 2.1249
Business Subtotal | 2.18 | 6.04 | 2.92 | 0.86 |  | 2.5106 | 7.7518 | 3.0865 | 0.87262 | 3.0682
Lighting | 7.34 | 10.42 | 28.84 | 0.58 |  | 3.6104 | 8.3397 | 8.5631 | 0.57967 | 4.4162
Energy Efficient Products | 2.75 | 6.45 | 5.76 | 0.62 |  | 2.2936 | 3.6213 | 5.2877 | 0.59151 | 2.783
HVAC | 2.39 | 5.29 | 3.36 | 0.82 |  | 2.7397 | 5.926 | 3.6944 | 0.83579 | 3.3584
Refrigerator Recycling | 3.14 | 3.14 | N/A | 0.62 |  | 3.4736 | 3.4736 | ∞ | 0.64717 | 3.9403
Home Energy Performance | 0.98 | 1.07 | 3.18 | 0.43 |  | 0.93853 | 1.4176 | 2.0562 | 0.51465 | 1.1892
New Homes | 0.72 | 0.88 | 3.18 | 0.45 |  | 1.2702 | 2.3069 | 2.895 | 0.63814 | 1.6611
Low Income | 1.21 | 1.21 | 3.62 | 0.47 |  | 1.2618 | 1.2618 | 3.3212 | 0.4894 | 1.543
Residential Subtotal | 3.93 | 6.22 | 10 | 0.62 |  | 2.9442 | 5.5967 | 6.0319 | 0.64614 | 3.5946
Portfolio (includes BTL costs) | 2.81 | 5.1 | 6.17 | 0.67 |  | 2.5801 | 5.7227 | 4.3443 | 0.72718 | 3.1515
Program Effectiveness Tests (Approved Plan) | TRC | UCT | Participant Test | Non-Partic'p't Test | Societal Test | TRC | UCT | Participant Test | Non-Partic'p't Test | Societal Test
Standard | 2.14 | 3.15 | 4.1 | 0.75 |  | 2.1121 | 3.0811 | 4.1533 | 0.74556 | 2.5091
Custom | 1.77 | 3.55 | 2.62 | 0.82 |  | 1.751 | 3.4956 | 2.627 | 0.81566 | 2.0974
Retro-commissioning | 1.7 | 3.77 | 2.51 | 0.79 |  | 1.6698 | 3.5893 | 2.5358 | 0.78688 | 1.9703
New Construction | 1.36 | 2.22 | 2.42 | 0.71 |  | 1.3375 | 2.1768 | 2.4174 | 0.70107 | 1.6314
Business Subtotal | 1.85 | 3.33 | 2.98 | 0.79 |  | 1.8302 | 3.2597 | 3.0056 | 0.78422 | 2.1873
Lighting | 3.66 | 6.01 | 10.18 | 0.56 |  | 3.745 | 5.7763 | 11.5762 | 0.5603 | 4.4775
Energy Efficient Products | 1.55 | 3.9 | 2.85 | 0.62 |  | 1.5651 | 4.0234 | 2.8954 | 0.61337 | 1.8981
HVAC | 2.11 | 4.61 | 2.63 | 0.94 |  | 2.0689 | 4.6902 | 2.4971 | 0.94792 | 2.4291
Refrigerator Recycling | 2.23 | 2.93 | 11.67 | 0.63 |  | 2.9036 | 2.9036 | ∞ | 0.62942 | 3.2819
Home Energy Performance | 1.64 | 3 | 3.11 | 0.68 |  | 1.6183 | 2.9138 | 3.1084 | 0.67416 | 2.0037
New Homes | 1.26 | 1.77 | 3.61 | 0.57 |  | 1.2608 | 1.8088 | 3.3957 | 0.58446 | 1.5622
Low Income | 0.84 | 0.84 | 2.85 | 0.43 |  | 0.79084 | 0.79084 | 2.7225 | 0.41536 | 0.98166
Residential Subtotal | 2.24 | 4 | 4.52 | 0.68 |  | 2.2734 | 3.9485 | 4.7437 | 0.67427 | 2.699
Portfolio | 2.07 | 3.71 | 3.86 | 0.72 |  | 2.0912 | 3.6695 | 4.0259 | 0.71009 | 2.4886
Plan vs. Deemed Cost Effectiveness Variance | TRC | UCT | Participant Test | Non-Partic'p't Test | Societal Test | TRC | UCT | Participant Test | Non-Partic'p't Test | Societal Test
Standard | 0.65 | 3.32 | 0.25 | 0.04 |  | 1.4122 | 4.537 | 0.84966 | 0.070275 | 1.8026
Custom | 0.3 | 2.92 | -0.05 | 0.08 |  | 0.51757 | 5.2586 | 0.01339 | 0.081429 | 0.68397
Retro-commissioning | -1.16 | -3.23 | 7.29 | -0.43 |  | 2.6764 | 0.73142 | 5.9332 | 0.062686 | 3.2324
New Construction | -1.02 | -1.86 | 1.22 | -0.45 |  | 0.41555 | 4.9166 | -0.44375 | 0.21376 | 0.49347
Business Subtotal | 0.33 | 2.71 | -0.06 | 0.07 |  | 0.68033 | 4.4921 | 0.080906 | 0.088405 | 0.88088
Lighting | 3.68 | 4.41 | 18.66 | 0.02 |  | -0.1346 | 2.5634 | -3.013 | 0.019361 | -0.061282
Energy Efficient Products | 1.2 | 2.55 | 2.91 | 0 |  | 0.72857 | -0.40208 | 2.3922 | -0.021866 | 0.88491
HVAC | 0.28 | 0.68 | 0.73 | -0.12 |  | 0.67079 | 1.2358 | 1.1973 | -0.11213 | 0.92924
Refrigerator Recycling | 0.91 | 0.21 |  | -0.01 |  | 0.57002 | 0.57002 |  | 0.017749 | 0.65836
Home Energy Performance | -0.66 | -1.93 | 0.07 | -0.25 |  | -0.6798 | -1.4961 | -1.0521 | -0.15951 | -0.81453
New Homes | -0.54 | -0.89 | -0.43 | -0.12 |  | 0.0093547 | 0.49807 | -0.50063 | 0.053681 | 0.098813
Low Income | 0.37 | 0.37 | 0.77 | 0.04 |  | 0.47097 | 0.47097 | 0.59864 | 0.074046 | 0.56138
Residential Subtotal | 1.69 | 2.22 | 5.48 | -0.06 |  | 0.67085 | 1.6482 | 1.2882 | -0.028131 | 0.89563
Portfolio | 0.74 | 1.39 | 2.31 | -0.05 |  | 0.48888 | 2.0532 | 0.3184 | 0.017085 | 0.66288
Plan vs. Deemed Cost Effectiveness (%) Variance | TRC | UCT | Participant Test | Non-Partic'p't Test | Societal Test | TRC | UCT | Participant Test | Non-Partic'p't Test | Societal Test
Standard | 30.37% | 105.4% | 6.098% | 5.333% |  | 66.86% | 147.3% | 20.46% | 9.426% | 71.84%
Custom | 16.95% | 82.25% | -1.908% | 9.756% |  | 29.56% | 150.4% | 0.5097% | 9.983% | 32.61%
Retro-commissioning | -68.24% | -85.68% | 290.4% | -54.43% |  | 160.3% | 20.38% | 234% | 7.966% | 164.1%
New Construction | -75% | -83.78% | 50.41% | -63.38% |  | 31.07% | 225.9% | -18.36% | 30.49% | 30.25%
Business Subtotal | 17.84% | 81.38% | -2.013% | 8.861% |  | 37.17% | 137.8% | 2.692% | 11.27% | 40.27%
Lighting | 100.5% | 73.38% | 183.3% | 3.571% |  | -3.594% | 44.38% | -26.03% | 3.455% | -1.369%
Energy Efficient Products | 77.42% | 65.38% | 102.1% | 0% |  | 46.55% | -9.994% | 82.62% | -3.565% | 46.62%
HVAC | 13.27% | 14.75% | 27.76% | -12.77% |  | 32.42% | 26.35% | 47.95% | -11.83% | 38.25%
Refrigerator Recycling | 40.81% | 7.167% |  | -1.587% |  | 19.63% | 19.63% |  | 2.82% | 20.06%
Home Energy Performance | -40.24% | -64.33% | 2.251% | -36.76% |  | -42.01% | -51.35% | -33.85% | -23.66% | -40.65%
New Homes | -42.86% | -50.28% | -11.91% | -21.05% |  | 0.7419% | 27.54% | -14.74% | 9.185% | 6.325%
Low Income | 44.05% | 44.05% | 27.02% | 9.302% |  | 59.55% | 59.55% | 21.99% | 17.83% | 57.19%
Residential Subtotal | 75.45% | 55.5% | 121.2% | -8.824% |  | 29.51% | 41.74% | 27.16% | -4.172% | 33.18%
Portfolio | 35.75% | 37.47% | 59.84% | -6.944% |  | 23.38% | 55.95% | 7.909% | 2.406% | 26.64%
* The financial information contained within this report is confidential and may contain immaterial revisions from other company financial statements.

## HC Opt-Out
Annual Report: Opt-Out Customers and Energy Savings Targets | Utility: Ameren Missouri
Report Date: 02/26/2015
Period: 01/02/13 - 12/31/15
Portfolio Start Date: 01/02/2013
HIGHLY CONFIDENTIAL | Pgm Year 1 - 2013 | Pgm Year 2 - 2014 | Pgm Year 3 - 2015
Company Name | Energy (kWh) | Energy (kWh) | Energy (kWh)
Total Opt-Out Customers
Total Non-Residential Usage
% Opt-Out
* The financial information contained within this report is confidential and may contain immaterial revisions from other company financial statements.

## >10% Cost Variances
Annual Report: >10% Program Cost Variance Explanation | Utility: Ameren Missouri | Utility: Ameren Missouri
| Report Date: 02/26/2015 | Report Date: 02/26/2015
| Period: 01/02/13 - 12/31/13 | Period: 01/02/14 - 12/31/14
| Portfolio Start Date: 01/02/2013 | Portfolio Start Date: 01/02/2013
| Program Year 1 | Program Year 2
Program | Variance Explanation | Variance Explanation
Standard | Lower spend due to lower participation and lower than cycle average $/kWh customer incentive to-date. | Lower spend due to lower than cycle average $/kWh customer incentive to-date.
Custom | Lower spend due to lower participation and lower than cycle average $/kWh customer incentive to-date. | Lower spend due to lower than cycle average $/kWh customer admin. and incentive to-date.
Retro-commissioning | Higher spend due to commitment payments to implementation contractor for committed projects to complete in 2014. | Higher spend due to higher participation than planned.
New Construction | Lower spend due to lower participation than planned. | Higher spend due to higher participation than planned.
Lighting | Higher spend due to higher sales of CFLs in grocery, drug store, and discount stores than planned. | Higher spend due to high CFL sales through urban and low income channels. Increase in LED sales due to lower priced products available in the marketplace.
Energy Efficient Products | Higher spend due to successful marketing campaign that increased customer participation in advanced power strips and heat pumps. Also increased electric EE Kit distribution due to higher participation than planned. | Lower spend due to removal of programmable thermostat.
HVAC | Higher spend due to higher participation than planned. | N/A
Refrigerator Recycling | Lower spend due to lower participation than planned. | Lower spend due to lower participation than planned.
Home Energy Performance | Lower spend due to number of customer audits and follow-on major measures lower than planned. | Lower spend due to lower number of customer audits and follow-on major measure replacements than planned.
New Homes | Lower spend due to lower participation than planned. | Lower spend due to close out of the program in 2014.
Low Income | Higher spend due to increased participation of property management companies representing federally subsidized MF properties. | N/A
* The financial information contained within this report is confidential and may contain immaterial revisions from other company financial statements.

## Market Transf
Annual Report: Quantitative and Qualitative Assessment of Market Transformation Programs | Utility: Ameren Missouri |  | Utility: Ameren Missouri
| Report Date: 02/26/2015 |  | Report Date: 02/26/2015
| Period: 01/02/13 - 12/31/13 |  | Period: 01/02/14 - 12/31/14
| Portfolio Start Date: 01/02/2013 |  | Portfolio Start Date: 01/02/2013
| Program Year 1 |  | Program Year 2
Program Name | Quantitative | Qualitative | Quantitative | Qualitative
Lighting | Number of retailers: 513 | From EM&V Draft Report: "Market effects are systemic changes to standard business practices, caused by program activities and that tend to persist long after program interventions have ended. The potential for DSM programs to cause structural changes when intervening in a given market has become increasingly apparent as: Program delivery models have evolved (e.g., more upstream-focused programs); and Energy-efficiency investment has grown dramatically. Programs have established long-term relationships with key market actors and trade allies. The LightSavers program works closely with retailers and manufacturers to: increase the availability and dedicated shelf space for efficient lighting products; and to offer education to help retail staff communicate the value of efficient purchasing decisions to local consumers. LightSavers’ potential to generate market effects also has become readily evident, given its significant role within Ameren’s 2013–2015 residential portfolio. In addition, Act On Energy, Ameren’s umbrella marketing campaign, seeks to raise general awareness and adoption of energy efficiency, and, by doing so, create a more energy-conscious customer base, more likely to buy energy-efficient lighting, whether or not it has been discounted through Ameren’s program." | Number of retailers: 435 | From EM&V Draft Report: "Market effects are systemic changes to standard business practices, caused by program activities; they tend to persist long after program interventions have ended. The potential for demand-side management (DSM) programs to cause structural changes when intervening in a given market has become increasingly apparent as the following has occurred: • Program delivery models have evolved (e.g., more have become upstream-focused programs); and • Energy-efficiency investments have grown dramatically. Programs have established long-term relationships with key market actors and trade allies. These relationships serve as a channel through which the program impacts the broader market—not only customers that experience program marketing and purchase program-discounted products. " From Ameren Missouri: Through 2014 the program continued to market ENERGY STAR® CFLs and LEDs. Feedback from GE and Walmart indicated that Ameren Missouri stores offering program rebates sold significantly more lighting products then stores without a program. As a result they were re-organizing shelf space and identifying in-store locations that would position the products for greater sales.
| Number of manufacturers: 20 |  | Number of manufacturers: 27
| Number of lamp types: 304 |  | Number of lamp types: 333
| In-store demonstration events: 221 |  | In-store demonstration events: 233
| Retail personnel trainings: 24,682 |  | Retail personnel trainings: 27,594
| From EM&V Draft Report: "Market Effects (19%), structural market or behavior changes caused by program activity that result in additional purchases of non-discounted bulbs....Ameren's LightSavers program creates spillover and market effects by increasing availability and stocking of energy-efficient light bulbs among retailers and by educating customers about the benefits of using efficient lighting…... Our analysis resulted in a NTG including both nonparticipant lighting and non-lighting spillover and market effects of 1.21." |  | From EM&V Draft Report: "In PY13, we used results from the home inventory study completed that year to determine the saturation of efficient bulbs in Missouri homes. The saturation value supported an estimate of the total market for efficient bulbs in Ameren’s territory, and allowed us to attribute a portion of that market to spillover and the market effects we described above. The scope of work for PY14 did not include an inventory survey to update the saturation value for PY14. While we did not know the precise rate of adoption or where exactly PY14 consumers sit on the “S” curve, we can reasonably expect market effects greater than zero. At the same time, as the rate of increase in market share decreases over time, program market effects were likely less than in PY13. As we did not have the information to make a more precise estimate, we adopted the midway point of zero and the PY13 market effects value. We applied the same principle to the rate of lighting spillover, taking the mid-point between 0 and the PY13 value. Table 38 shows suggested market effects and spillover values for PY14. Table 38. Market Effects and Lighting Spillover Net Impact PY13 Value PY14 Value Market Effects 20% 10% Lighting Spillover 28% 14% "
HVAC | Number of program partners: 427 | From EM&V Draft Report: "For the PY13 evaluation, we estimated the first three NTG elements, but not market effects. Since the program is likely to generate market effects-program staff will work closely with local contractors and distributors to improve installation and stocking practices-we plan to estimate market effect as part of the PY14 evaluation." From Ameren: We use an optimizer tool that helps contractors show the value of tuneups to our customers and is a great tool for market transformation. Our HVAC tuneups require a nine step check, not a typically utilized tuneup protocol, but one that optimizes system performance. We are also providing training on system and duct sizing as well as proper air flow. These efforts are very valuable to change contractor practices and customer expectations. | Number of program partners: 513 | From EM&V Draft Report: " For the PY14 evaluation, we estimated the first three NTG elements, but not market effects. Because the program will likely to generate market effects—program staff work closely with local contractors and distributors to improve installation and stocking practices—we will estimate market effects as part of the PY15 evaluation." From Ameren Missouri: During 2014 we have worked to position the efficiency analysis that is done in conjunction with a tune-up as a way for a customer to understand the 'health' of their system and veirfy the capacity against the nameplate capacity of the system. This is a tool for the customers to better understand repair and/or replacement recommendations of the contractors. Contractors are indicating they are using this process as a best practice with customers outside of the Ameren Missouri Program.
| Number of tune-ups: 3,681 |  | Number of tune-ups: 8,895
| Number of HVAC installations: 6,738 |  | Number of HVAC installations: 8,718
* The financial information contained within this report is confidential and may contain immaterial revisions from other company financial statements.

## EM&V Annual Report
Annual Report: EM&V Report Summary (EO-2012-0142) | Utility: Ameren Missouri
Report Date: 02/26/2015
Period: 01/02/13 - 12/31/15
Portfolio Start Date: 01/02/2013
Status | Pgm Year 1 - 2013 | Pgm Year 2 - 2014 | Pgm Year 3 - 2015
Final EM&V Report Filed in EFIS (EO-2012-0142) | 2014-06-01 | Under Review
Final Approved Stipulation & Agreement Approved | 2015-02-01
* The financial information contained within this report is confidential and may contain immaterial revisions from other company financial statements.